# DEVELOPMENT AGREEMENT

## LAKEMONT STATION COMMONS

by and between

GRANITE CITY DEVELOPMENT LLC

and

CITY OF LAKEMONT, ILLINOIS

DRAFT FOR NEGOTIATION — PREPARED ON BEHALF OF DEVELOPER

This draft is circulated for discussion and negotiation purposes. Bracketed provisions and bracketed drafting notes reflect open items, cross-document conflicts, and matters requiring confirmation. Bracketed drafting notes are not part of the operative agreement and shall be deleted upon finalization.

## ARTICLE 1. PARTIES; RECITALS

1.1 Parties. This Development Agreement (this “Agreement”) is entered into as of [●], 2025 (the “Effective Date”), by and between Granite City Development LLC, an Illinois limited liability company formed March 14, 2019, with its principal office at 900 West Monroe Street, Suite 2200, Chicago, IL 60607 (“Developer”), and the City of Lakemont, Illinois, an Illinois home rule municipality, with offices at 200 Civic Center Drive, Lakemont, IL 60048 (“City”). Developer and City are each a “Party” and collectively the “Parties.”

1.2 Recitals.

(a) The City is the owner of certain real property located at 1400–1550 Lakemont Station Boulevard, Lakemont, IL 60048, consisting of three parcels identified by Lake County Parcel Identification Numbers 12-24-300-015, 12-24-300-016, and 12-24-300-017, totaling approximately 12.7 acres (553,212 square feet) (collectively, the “Site”).

[Drafting Note — Parcel Acquisition History Conflict: The Negotiated Term Sheet, City Council Resolution R-2025-017, and the TIF District Summary Memo state that Parcels 12-24-300-015 and 12-24-300-016 were acquired by the City through tax forfeiture proceedings in 2016, and Parcel 12-24-300-017 by direct purchase in 2018. The Phase II ESA Summary (Section 1.3) states that Parcel 12-24-300-015 was acquired by tax forfeiture in 2016, while Parcels 12-24-300-016 and 12-24-300-017 were both acquired by direct purchase in 2018. This discrepancy affects chain-of-title analysis, environmental indemnification scope, and consolidation. Confirm the correct acquisition history for each parcel and reconcile across all documents before finalizing.]

[Drafting Note — Per-Parcel Acreage Conflict: The RFP Response Narrative states Parcel 015 ≈ 3.8 acres, 016 ≈ 4.1 acres, 017 ≈ 4.8 acres. The Phase II ESA Summary states Parcel 015 ≈ 4.2 acres, 016 ≈ 4.1 acres, 017 ≈ 4.4 acres. Total is consistently 12.7 acres, but per-parcel figures differ. Confirm legal descriptions and acreage by survey (ALTA/NSPS survey required by Lender) before finalizing.]

(b) The Site is the former location of the Lakemont Ironworks manufacturing campus, which ceased operations in 2009, and is currently vacant and unimproved. The Site is located immediately adjacent to the Lakemont Central Metra station (Milwaukee District/North Line).

(c) The Site is currently zoned M-2 (General Manufacturing) and requires rezoning to PD-TOD (Planned Development — Transit Oriented District).

(d) Developer was selected by the City through a competitive Request for Proposals process.

[Drafting Note — RFP Number Conflict: The RFP Response Narrative identifies the solicitation as “RFP No. 2024-CD-07,” while the Negotiated Term Sheet identifies it as “RFP No. 2024-CD-018.” Confirm the correct RFP number and correct all references. The Resolution does not state a number.]

(e) The Parties executed a non-binding Negotiated Term Sheet dated January 22, 2025 (the “Term Sheet”), setting forth the principal business terms for the Project.

(f) The Lakemont City Council adopted Resolution No. R-2025-017 on February 18, 2025 (the “Resolution”), granting conditional approval of the Project and authorizing the City Manager to negotiate and execute this Agreement, subject to the conditions set forth in Section 3 of the Resolution.

(g) The Parties desire to set forth in this Agreement the definitive terms governing the development of the Project, the conveyance of the Site, the public incentives to be provided by the City, and the respective rights and obligations of the Parties.

1.3 Incorporation of Recitals. The foregoing recitals are incorporated into and made a part of this Agreement.

## ARTICLE 2. DEFINITIONS

In addition to terms defined elsewhere in this Agreement, the following terms shall have the meanings set forth below:

“AMI” means Area Median Income as published annually by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area, or any successor designation.

“Affordable Units” has the meaning set forth in Section 9.1.

“Appraisal” means the as-is market value appraisal of the Site prepared by Crossland Appraisal Services, dated January 15, 2025, establishing a value of $18,400,000.

“Construction Lender” means First Prairie National Bank, and any successor or assignee permitted under the Construction Loan Documents.

“Construction Loan Documents” means the definitive loan agreements, mortgage, assignments, guaranties, and related instruments evidencing and securing the construction loan facility for the Project.

“Construction Loan Term Sheet” means the preliminary term sheet for the construction loan facility dated March [●], 2025, issued by First Prairie National Bank to Developer.

“Equity Investors” means Lakeshore Capital Partners Fund III LP and the Pellegrini Family Trust, collectively, and their respective successors and permitted assigns.

“Force Majeure” has the meaning set forth in Section 11.2.

“IEPA” means the Illinois Environmental Protection Agency.

“Lakeshore Side Letter” means the side letter dated February 10, 2025 between Lakeshore Capital Partners Fund III LP and Developer.

“NFR Letter” means a No Further Remediation letter issued by IEPA under the Voluntary Site Remediation Program.

“Permitted Exceptions” means the title exceptions set forth in Exhibit [●], including: (i) real estate taxes not yet due and payable; (ii) standard utility and access easements not materially interfering with the Project; (iii) this Agreement; (iv) covenants and restrictions of the PD-TOD zoning ordinance; (v) environmental use controls or institutional controls recorded in connection with the IEPA NFR Letter for Parcel 12-24-300-016 and the engineered barrier for Parcel 12-24-300-017; and (vi) such other exceptions as Developer and the Construction Lender may approve in writing.

“Phase” or “Project Phase” means each of Phase I, Phase II, Phase III, and Phase IV, as described in Article 4.

“Phase II ESA” means the Phase II Environmental Site Assessment prepared by Greenfield Environmental Consultants LLC, report dated November 8, 2024.

“Project” means the Lakemont Station Commons mixed-use transit-oriented development described in Article 4.

“RAP” means a Remedial Action Plan for Parcel 12-24-300-016 submitted to and approved by IEPA under the Voluntary Site Remediation Program.

“Substantial Completion” means, with respect to a Project Phase, the completion of construction of such Phase to the point where the building or improvements can be occupied and used for their intended purpose, as evidenced by issuance of a temporary or final certificate of occupancy by the City’s Building Department for such Phase, subject only to punch-list items and minor incomplete work that does not prevent such occupancy and use.

“TIF Act” means the Illinois Tax Increment Allocation Redevelopment Act, 65 ILCS 5/11-74.4-1 et seq.

“TIF District” means the Lakemont Central TIF District established by City Ordinance No. 2019-42, expiring December 31, 2042.

“VSRP” means the IEPA Voluntary Site Remediation Program.

## ARTICLE 3. THE SITE; REZONING; CONSOLIDATION

3.1 The Site. The Site consists of the three parcels described in Section 1.2(a), to be consolidated into a single parcel of record prior to or concurrent with conveyance to Developer, as provided in Section 3.3.

3.2 Rezoning. The City shall, at its sole cost and expense (except for application fees reimbursable as a TIF-eligible cost), complete the rezoning of the Site from M-2 (General Manufacturing) to PD-TOD (Planned Development — Transit Oriented District), including plan commission review, public hearings, and City Council action, so that such rezoning is adopted by ordinance and effective prior to execution of this Agreement. The City shall use commercially reasonable efforts to obtain a PD-TOD ordinance that accommodates the density, building heights, use mix, and design standards contemplated by the Project described in Article 4 and the site plan attached as Exhibit [●].

[Drafting Note — Rezoning as Condition Precedent: The Term Sheet (Section 4 and 18.2) and Resolution (Condition #5) require rezoning to be completed and effective prior to execution of this Agreement. The Construction Loan Term Sheet (Section 7.1) requires rezoning to be “final and non-appealable, or that the applicable appeal period has expired without the filing of any appeal.” Confirm whether the Agreement should require expiration of the appeal period (Lender’s requirement) in addition to effectiveness, and allocate the risk of any appeal.]

3.3 Parcel Consolidation. The City shall complete, or cause to be completed, the consolidation of Parcels 12-24-300-015, 12-24-300-016, and 12-24-300-017 into a single parcel of record acceptable to Developer and the Construction Lender, prior to or concurrent with completion of the rezoning. The consolidation plat shall expressly reference any environmental land use controls (“ELUCs”) and institutional controls by legal description and recording information.

[Drafting Note — Phased Conveyance Option: The Phase II ESA Summary (Sections 4.1.3, 5.2, and 8.2(d)) recommends that the parties consider a phased conveyance approach — conveying clean Parcel 015 (and Parcel 017 after the engineered barrier) to Developer first, while Parcel 016 remediation proceeds, to allow early Phase I construction and reduce project-wide delay risk. Developer favors a phased conveyance option. This requires: (i) PD-TOD rezoning and consolidation to accommodate phased delivery or separate/interim land use approvals; (ii) resolution of per-parcel title issues arising from the differing acquisition histories; and (iii) Construction Lender approval of the scope and legal description of the mortgaged premises. Open item — negotiate phased conveyance mechanics and Lender approval.]

3.4 Title. The City shall deliver marketable and insurable fee simple title to the Site, free and clear of all liens, encumbrances, and exceptions, except Permitted Exceptions, and shall provide a standard owner’s title insurance policy in the amount of the purchase price. The City represents and warrants that it has good and marketable fee simple title to the Site, free and clear of all liens, encumbrances, and adverse claims (except Permitted Exceptions), and the legal authority to convey the Site to Developer.

[Drafting Note — Defeasible Fee / Reversionary Interest Prohibition: The Construction Loan Term Sheet (Sections 4.2, 7.1, and 12) absolutely prohibits any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other defeasible fee estate in favor of the City or any other party, on the grounds that such an interest would (i) render title uninsurable under standard ALTA policies, (ii) subordinate the Lender’s first-priority mortgage to the City’s right to reclaim, (iii) prevent foreclosure, and (iv) render the construction loan “impossible to close.” City Council Resolution R-2025-017, Condition #8, however, requires Developer to grant the City a “reversionary interest” in the Site if Phase I is not Substantially Complete within 36 months of conveyance. These two requirements are directly irreconcilable. This draft resolves the conflict in favor of insurable fee simple title by substituting an alternative clawback mechanism (Section 7.5) consistent with the Lender’s suggested alternatives. This is the single most significant open item and must be resolved with the City (and approved by the Lender) before this Agreement can be executed and the loan closed.]

## ARTICLE 4. THE PROJECT

4.1 Project Description. Developer shall design, construct, and develop the Project, a mixed-use transit-oriented development known as “Lakemont Station Commons,” consisting of approximately 1,620,000 gross square feet across four phases, with a total estimated hard construction cost of $340,000,000 and a total estimated Project cost of approximately $412,000,000, as more particularly described in this Article 4 and the site plan and phasing plan attached as Exhibit [●].

4.2 Phase I — Residential Tower A and Retail Podium. Phase I shall consist of: (i) 320 residential units (256 market-rate and 64 Affordable Units at or below 60% AMI); (ii) 45,000 square feet of ground-floor retail; (iii) a 480-space structured parking garage; and (iv) approximately 420,000 square feet of gross building area. Estimated hard construction cost: $105,000,000.

4.3 Phase II — Office Building and Retail. Phase II shall consist of: (i) 280,000 square feet of Class A office space; (ii) 18,000 square feet of retail; (iii) a 350-space structured parking garage; and (iv) approximately 380,000 square feet of gross building area. Estimated hard construction cost: $76,000,000.

4.4 Phase III — Residential Tower B and Hotel. Phase III shall consist of: (i) 210 residential units (168 market-rate and 42 Affordable Units at or below 60% AMI); (ii) a 150-room select-service hotel; and (iii) approximately 440,000 square feet of gross building area. Estimated hard construction cost: $88,000,000.

[Drafting Note — Hotel Brand: The Term Sheet (Section 3.3) states the hotel brand affiliation is “to be determined; Developer is in discussions with two national hospitality flags.” Open item — confirm whether City approval of the hotel brand/flag is required, and the standard for such approval. Developer’s position: brand selection is a Developer business decision, subject only to consistency with the PD-TOD ordinance and the Project program.]

4.5 Phase IV — Public Plaza, Community Center, and Parking Structure. Phase IV shall consist of: (i) a 2.5-acre public plaza with landscaping, hardscape, seating, and public art; (ii) a 28,000-square-foot community center; and (iii) a 600-space public parking structure serving the transit station, community center, and adjacent uses. Estimated hard construction cost: $71,000,000.

4.6 Project Totals. The Project, in the aggregate, shall include 530 residential units (106 Affordable Units, representing 20% of total residential units), 280,000 square feet of office, 63,000 square feet of retail, 150 hotel rooms, 1,430 structured parking spaces, a 2.5-acre public plaza, and a 28,000-square-foot community center.

[Drafting Note — Affordable Unit Count: The Term Sheet (Section 12) refers in one place to “at least 100 affordable units” while the detailed breakdown and the Resolution state 106 units (20%). The 106-unit figure satisfies the City’s 20% minimum. Recommend standardizing on “not less than 106 Affordable Units (representing not less than 20% of total residential units)” throughout.]

4.7 Design Review. Developer shall submit design plans for each Phase to the City’s Community Development Department for review and approval. The City shall review and respond to design submissions within [30] business days. The City’s approval shall not be unreasonably withheld, conditioned, or delayed, and shall be deemed granted if the City does not respond within such period, provided the submission is consistent with the PD-TOD ordinance and the approved site plan. The City’s design review authority is limited to consistency with the PD-TOD ordinance, applicable codes, and the approved site plan, and shall not extend to aesthetic preferences not embodied in the PD-TOD ordinance.

## ARTICLE 5. LAND CONVEYANCE

5.1 Conveyance. Following the Effective Date and satisfaction of all conditions precedent to closing set forth in Article 13, the City shall convey the Site (as consolidated into a single parcel, or, if the Parties elect phased conveyance under Section 3.3, the applicable parcels) to Developer by special warranty deed.

5.2 Sale Price. The purchase price for the Site shall be $9,200,000, representing 50% of the appraised as-is market value of $18,400,000 set forth in the Appraisal, consistent with the City’s economic development incentive policy for transit-oriented development. The difference between the appraised value and the sale price ($9,200,000) constitutes the land write-down incentive (the “Land Write-Down”). The purchase price shall be due and payable at closing, and Developer may fund it from equity, construction loan proceeds, or a combination thereof.

5.3 Closing. Closing shall occur within 30 days following the satisfaction or waiver of all conditions precedent to closing. The Parties’ target closing date is [mid-2025], subject to the timing of rezoning, IEPA approvals, and satisfaction of other conditions.

5.4 Conditions Precedent to Closing. The obligations of the Parties to close the conveyance of the Site shall be subject to the satisfaction or waiver of the following conditions precedent:

- Execution of this Agreement by both Parties and approval by the City Council;

- Completion and effectiveness of the rezoning of the Site from M-2 to PD-TOD (and, if required by the Construction Lender, expiration of the applicable appeal period without the filing of any appeal);

- Completion or authorization of parcel consolidation;

- IEPA approval of the RAP for Parcel 12-24-300-016;

- Developer’s demonstration of committed equity of at least $85,000,000, in form and substance reasonably acceptable to the City; and

- Developer’s posting of the Phase I Performance Security in accordance with Section 8.1.

[Drafting Note — Equity Demonstration Timing Conflict: Resolution R-2025-017, Condition #3(a), requires Developer to demonstrate committed equity of not less than $85,000,000 within 60 days of adoption of the Resolution (i.e., on or before April 19, 2025), verified by an independent certification from Clearmont Accounting Group LLP. The Term Sheet (Sections 7 and 18.2) requires demonstration within 60 days of City Council approval of the definitive Agreement. These are different triggers and deadlines. The Resolution’s deadline is earlier and tied to Resolution adoption. Developer’s position: the equity demonstration should be a condition precedent to closing (as drafted in Section 5.4(e)), with the timing tied to the definitive Agreement, and the Resolution’s April 19, 2025 deadline should be treated as a separate, earlier milestone that Developer will endeavor to satisfy. Confirm and reconcile.]

[Drafting Note — NFR Letter vs. RAP Approval: Resolution Condition #3(b) and Term Sheet Section 4 require IEPA approval of the RAP for Parcel 016 as a condition precedent to conveyance. The Phase II ESA Summary (Sections 4.2.4, 5.2, and 6.1) emphasizes that the NFR Letter (not merely RAP approval) is required for residential development, title insurability, and lender financing on Parcel 016, and that the 14–18 month remediation timeline may not align with the March 1, 2026 Phase I groundbreaking. The Construction Loan Term Sheet (Section 7.1) permits either (a) an NFR Letter or (b) VSRP enrollment with an approved RAP plus an environmental escrow/insurance product satisfactory to the Lender. Open items: (i) confirm whether the condition precedent is RAP approval or NFR Letter; (ii) whether phased conveyance (Section 3.3) allows conveyance of clean parcels before Parcel 016 NFR; and (iii) whether remediation delay constitutes Force Majeure or a basis for deadline extension (see Section 11.2).]

## ARTICLE 6. PUBLIC INCENTIVES

6.1 Land Write-Down. The City shall convey the Site at 50% of appraised as-is market value, resulting in the Land Write-Down of $9,200,000, as set forth in Section 5.2.

[Drafting Note — Land Write-Down and TIF Cap Interaction: The TIF District Summary Memo (Section VII) flags that it is unspecified whether the $9.2M Land Write-Down is charged against the $48M TIF reimbursement cap or constitutes a separate incentive funded from another source. If charged against the cap, less TIF capacity remains for Developer reimbursement of other eligible costs. Developer’s position: the Land Write-Down should be a separate incentive not charged against the TIF cap. Open item — confirm funding source and treatment against the cap. Same open item applies to the $12.5M City infrastructure commitment (Section 6.3) and the $1.4M permit fee waivers (Section 6.5).]

6.2 Tax Increment Financing.

- Pledge. The City shall pledge up to $48,000,000 in TIF increment over the remaining life of the TIF District to reimburse Developer for eligible TIF costs incurred in connection with the Project, including without limitation public infrastructure improvements, environmental remediation costs, parking structure construction costs, the Land Write-Down (if charged to TIF), and other eligible project costs under the TIF Act and the TIF District Redevelopment Plan.

- Pay-As-You-Go. TIF reimbursement shall be on a pay-as-you-go basis. Developer shall front all eligible costs and shall be reimbursed annually from available TIF increment as generated by the Project and other developments within the TIF District. The City shall not issue TIF bonds or notes for the Project.

- No Guarantee. TIF reimbursement is subject to the availability of increment. The City does not guarantee that the full $48,000,000 cap will be reached over the remaining life of the TIF District. Developer acknowledges that actual reimbursement will depend on the amount of increment generated and available in each year.

- Priority of Reimbursement. Notwithstanding the foregoing, the City shall reimburse eligible TIF costs in the following priority order: (i) first, environmental remediation costs for Parcels 016 and 017; (ii) second, public infrastructure costs, including the City’s $12,500,000 commitment and Developer’s eligible on-site infrastructure expenditures; (iii) third, Phase IV public parking structure, public plaza, and community center costs; and (iv) fourth, all other eligible costs.

- TIF District Extension. If, as of December 31, 2038, cumulative TIF reimbursement to Developer is tracking materially below the projections set forth in the TIF District Summary Memo, the City shall use good-faith efforts to seek an extension of the TIF District or the establishment of a successor TIF district, in each case subject to applicable law and the TIF Act. The City’s obligation under this Section 6.2(e) is one of good-faith effort only and shall not constitute a guarantee of extension or a basis for liability.

- Shortfall Not a Default. A shortfall in TIF reimbursement, whether due to the TIF District expiration, the impact of the Phase I property tax abatement on increment generation, assessment appeals, or otherwise, shall not constitute a default by the City under this Agreement.

[Drafting Note — TIF Shortfall Risk: The TIF District Summary Memo (Section IV) projects that, under an adjusted scenario incorporating the Phase I property tax abatement, cumulative increment through 2042 may fall $6,000,000 to $10,000,000 short of the $48,000,000 cap, and that under a worst-case timing scenario (with 18-month Force Majeure delays) the shortfall could be substantially greater. The Memo recommends (from the City’s perspective) that (i) TIF reimbursement not be a guaranteed City obligation, (ii) a priority structure be established, (iii) a good-faith TIF extension covenant be included, and (iv) a shortfall not constitute City default. This draft adopts the priority structure and good-faith extension covenant (Developer-favorable) while acknowledging that TIF is not a guaranteed obligation (a legal necessity under the TIF Act and pay-as-you-go structure). Developer should consider whether to seek additional protections, such as a City commitment to fund a portion of public infrastructure from non-TIF sources to reduce reliance on uncertain increment. Open item.]

[Drafting Note — Abatement/TIF Interaction: The TIF District Summary Memo (Sections IV.B and VII) identifies an internal tension: the Phase I property tax abatement reduces the assessed value of Phase I improvements, which reduces the TIF increment available for Developer reimbursement. Developer benefits from the abatement (lower property taxes) but it simultaneously reduces reimbursement capacity. The Memo suggests structuring the abatement to apply only to the non-TIF-captured portion of the tax bill, if legally permissible. Open item — confirm whether such structuring is legally permissible and, if not, include an express acknowledgment of the trade-off.]

6.3 Infrastructure Cost-Sharing.

- City Commitment. The City shall fund $12,500,000 for off-site infrastructure improvements necessary to support the Project, including road widening and streetscape improvements on Lakemont Station Boulevard between Oak Street and Maple Avenue, a new traffic signal at the Oak Street/Lakemont Station Boulevard intersection, water main extension along Lakemont Station Boulevard, and sanitary sewer upgrade and capacity expansion. The City’s infrastructure funding shall be appropriated and disbursed according to a schedule set forth in Exhibit [●], coordinated with the phased construction timeline.

- Developer Responsibility. Developer shall fund $8,300,000 for on-site infrastructure improvements, including internal roadways, utilities, stormwater management, pedestrian pathways, and landscape improvements within the Site.

- Total Infrastructure Budget. $20,800,000 ($12,500,000 City + $8,300,000 Developer).

[Drafting Note — City Infrastructure Funding Source: Confirm whether the City’s $12,500,000 infrastructure commitment is funded from general revenue/capital improvement funds (not charged against the TIF cap) or from TIF (charged against the cap). Developer’s position: fund from non-TIF sources to preserve TIF capacity. Open item.]

6.4 Property Tax Abatement. The City shall provide a 12-year declining property tax abatement on Phase I improvements only, as follows: Years 1–4, 75% abatement; Years 5–8, 50% abatement; Years 9–12, 25% abatement; Year 13 and thereafter, 0% (full assessment). The abatement shall apply to the incremental increase in assessed value attributable to the Phase I improvements, measured from the pre-development base equalized assessed value.

[Drafting Note — Abatement Scope: The Term Sheet (Section 5.4 and 18.4) limits the property tax abatement to Phase I only; no abatement is provided for Phases II, III, or IV. Developer may seek abatement or other incentives for later phases. Open item — whether to negotiate abatement for later phases, particularly given the TIF shortfall risk and the substantial public benefits delivered by later phases.]

6.5 Permit Fee Waiver. The City shall waive building permit fees for Phase I and Phase II of the Project, with an estimated combined value of $1,400,000 ($920,000 Phase I + $480,000 Phase II). No permit fee waiver is contemplated for Phase III or Phase IV.

## ARTICLE 7. ENVIRONMENTAL MATTERS

7.1 Phase II ESA. The Phase II ESA identified the following environmental conditions on the Site:

- Parcel 12-24-300-015: No contaminants of concern above applicable IEPA residential or commercial remediation objectives. No further action required.

- Parcel 12-24-300-016: Petroleum hydrocarbon contamination (BTEX compounds) in soil and shallow groundwater across approximately 1.8 acres, plus localized TCE contamination. Remediation is required under the VSRP. Estimated remediation cost: $2,800,000. Estimated remediation timeline: 14–18 months from IEPA approval of the RAP. An NFR Letter is required prior to residential construction on the affected area.

- Parcel 12-24-300-017: Low-level metals contamination (primarily arsenic, lead, and chromium) in shallow fill soil. An engineered barrier (clean fill cap) and an ELUC are required. Estimated cost: $340,000.

7.2 Total Estimated Environmental Remediation Costs. $3,140,000 ($2,800,000 for Parcel 016 + $340,000 for Parcel 017). Environmental remediation costs are eligible TIF-reimbursable costs under Section 6.2 and shall be reimbursed on a first-priority basis.

7.3 City Indemnification. The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to pre-existing environmental conditions on the City-owned parcels (Parcels 12-24-300-015, 12-24-300-016, and 12-24-300-017), including without limitation third-party claims, governmental enforcement actions, and contribution or cost-recovery actions under federal or state environmental laws. The contamination identified in the Phase II ESA is pre-existing and attributable to the former Lakemont Ironworks operations that ceased in 2009, prior to Developer’s involvement. This indemnification shall survive the expiration or termination of this Agreement and the conveyance of the Site.

7.4 Remediation Performance and Cost Overruns.

- Performance Responsibility. Developer shall perform or contract for the remediation of Parcel 016 and the engineered barrier for Parcel 017, and shall serve as the VSRP applicant, in each case in coordination with the City and Greenfield Environmental Consultants LLC. The City shall cooperate with Developer in all regulatory interactions with IEPA.

- Cost Overruns. The City shall be responsible for, and shall reimburse Developer for, environmental remediation costs that exceed the Total Estimated Environmental Remediation Costs of $3,140,000, including costs arising from discovery of additional contamination beyond the currently delineated plume extent, expanded excavation scope, extended groundwater treatment, supplemental regulatory requirements, vapor intrusion mitigation, and additional investigation recommended in the Phase II ESA. The Phase II ESA Summary recommends a contingency of 25%–35% above the base estimate, with total cost exposure potentially reaching $3,800,000–$4,200,000 for Parcel 016 alone.

- Reimbursement. Cost overruns reimbursable under this Section 7.4 shall be reimbursed by the City from TIF increment (on a first-priority basis under Section 6.2(d)) or, if TIF increment is insufficient, from other available City funds, subject to annual appropriation.

[Drafting Note — Environmental Cost Overrun Allocation: The Phase II ESA Summary (Sections 4.2.4, 5.3, and 8.2) recommends that the transactional documents clearly allocate responsibility for cost overruns and states that actual costs could exceed the base estimate by 25%–35%, with total Parcel 016 exposure potentially reaching $3.8M–$4.2M. The Term Sheet (Section 6) provides for City indemnification for pre-existing conditions but does not address cost overruns or performance responsibility. Developer’s position (drafted in Section 7.4): the City, as the owner at the time of contamination and the party indemnifying pre-existing conditions, should bear cost overrun risk, with reimbursement from TIF or other City funds. The City may resist bearing overrun risk beyond TIF availability. Open item — negotiate overrun allocation and whether the City’s obligation is capped or subject to annual appropriation.]

[Drafting Note — Additional Investigation Costs: The Phase II ESA Summary (Section 8.3) recommends additional investigation not included in the $3.14M estimate: (i) 6–8 pre-remediation plume delineation borings; (ii) at least two off-site groundwater monitoring points on Metra property (requiring Metra access coordination); and (iii) vapor intrusion screening with soil gas probes. These additional costs should be treated as eligible environmental costs reimbursable under Section 7.4. Open item — confirm treatment and Metra access arrangements.]

7.5 Completion Assurance (Alternative to Reversionary Interest).

- No Defeasible Fee. The Parties acknowledge that the Construction Lender requires that Developer hold insurable fee simple absolute title to the Site, free and clear of any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other defeasible fee estate. Accordingly, the Site shall be conveyed to Developer in fee simple absolute, and no provision of this Agreement shall create or be construed to create any such defeasible interest in favor of the City.

- City Repurchase Option. In lieu of any reversionary interest, and solely as a remedy for Developer’s failure to achieve Substantial Completion of Phase I, the City shall have a contractual option to repurchase the Site (the “Repurchase Option”), exercisable only upon the cumulative satisfaction of all of the following: (i) Developer’s failure to achieve Substantial Completion of Phase I within [36] months of the date of conveyance of the Site to Developer (the “Completion Deadline”), as such deadline may be extended by Force Majeure under Article 11; (ii) expiration of all applicable cure periods under Article 12, including the Construction Lender’s extended cure periods provided in Section 14.2; and (iii) either (A) the Construction Lender’s prior written consent or (B) full satisfaction of the outstanding construction loan balance. The Repurchase Option shall be subordinate in all respects to the Construction Lender’s first-priority mortgage and shall not impair the Construction Lender’s security interest or foreclosure remedies.

- Repurchase Price. The repurchase price shall be the lesser of (x) the original purchase price paid by Developer ($9,200,000) or (y) the then-current fair market value of the Site as determined by an independent MAI appraiser mutually selected by the Parties (or, if the Parties cannot agree, appointed in accordance with the dispute resolution provisions of Article 15), in each case net of any documented damages incurred by the City as a result of Developer’s failure to timely complete Phase I.

- Alternative/Supplemental Mechanisms. In addition to or in lieu of the Repurchase Option, the Parties may elect to substitute or supplement the completion assurance with one or more of the following mechanisms, as may be agreed: (i) an additional escrow deposit or irrevocable standby letter of credit held by a mutually acceptable escrow agent; (ii) liquidated damages in a predetermined amount representing a reasonable pre-estimate of the City’s actual damages, payable as an unsecured contractual obligation; (iii) an enhanced completion guaranty from Developer’s principals; or (iv) a right of first refusal in favor of the City with respect to a default-related disposition, subordinate to the Construction Lender’s mortgage.

[Drafting Note — Resolution #8 vs. Lender Prohibition (Critical): This Section 7.5 is the negotiated resolution of the central conflict between City Council Resolution R-2025-017, Condition #8 (requiring a reversionary interest with automatic reversion if Phase I is not Substantially Complete within 36 months of conveyance) and the Construction Loan Term Sheet (Sections 4.2, 7.1, and 12), which absolutely prohibits any reversionary or defeasible interest as a condition of the loan. The Lender states that incorporation of the Resolution’s reversionary interest “would make the Loan impossible to close.” This draft substitutes a contractual Repurchase Option (subordinate to the Lender’s mortgage and exercisable only after exhaustion of cure periods and Lender consent/loan satisfaction), consistent with the Lender’s suggested alternative (i) in Term Sheet Section 12. The City must agree to this substitution, and the Lender must confirm in writing that the substituted mechanism is acceptable. The 36-month Completion Deadline in the Resolution is measured from conveyance; the Term Sheet’s Phase I Substantial Completion deadline is September 30, 2028 (30 months from the March 1, 2026 groundbreaking). These measures are not identical — confirm the governing deadline and measurement start date. This is the highest-priority open item.]

## ARTICLE 8. PERFORMANCE SECURITY

8.1 Phase I Performance Security. Prior to conveyance of the Site, Developer shall post a $15,000,000 performance bond (issued by Ridgepoint Surety Corporation or another surety company reasonably acceptable to the City) or an irrevocable standby letter of credit issued by a nationally recognized financial institution (collectively, the “Phase I Performance Security”), securing Developer’s obligation to commence and substantially complete Phase I in accordance with the approved plans, specifications, and timeline.

8.2 Maintenance and Release. The Phase I Performance Security shall be maintained continuously from the date of conveyance until Phase I Substantial Completion, as evidenced by issuance of a temporary or final certificate of occupancy. Upon Phase I Substantial Completion, the Phase I Performance Security shall be released and returned to Developer within 30 days following written request and verification of Substantial Completion by the City.

8.3 Later Phases. Performance security for Phases II, III, and IV, if any, shall be established by the Parties in good faith prior to the commencement of each such Phase, taking into account the scope and cost of such Phase and the demonstrated performance of Developer on prior Phases. Developer’s position is that performance security for later phases should be modest or limited to specific public-benefit obligations (e.g., the community center conveyance), given the substantial private capital at risk and the release of the Phase I Performance Security upon Phase I Substantial Completion.

[Drafting Note — Later-Phase Performance Security: The Term Sheet (Section 8) addresses only the $15M Phase I Performance Security. The Lakeshore Side Letter (Section 4.3(e)) notes that performance bond/letter of credit amounts for later phases are “to be established in the Development Agreement.” Open item — negotiate later-phase performance security amounts and form. Developer favors limited or no additional security for later phases; the City may seek security tied to public-benefit deliverables (community center, public plaza, parking structure).]

## ARTICLE 9. COMMUNITY BENEFITS

9.1 Affordable Housing.

- Commitment. Developer shall include not less than 106 Affordable Units across the Project (64 in Phase I and 42 in Phase III), with rents restricted to households earning at or below 60% of AMI, representing not less than 20% of the 530 total residential units.

- Integration. Affordable Units shall be distributed proportionally across unit types (studio, one-bedroom, and two-bedroom) and shall not be segregated or concentrated on particular floors or in separate wings. Affordable Units shall be comparable in design, finishes, and amenity access to market-rate units within the same building, subject to reasonable variations consistent with industry practice.

- Restriction Period. Affordability restrictions shall remain in effect for a minimum of 30 years from the date of issuance of the certificate of occupancy for the applicable Phase, memorialized by a restrictive covenant recorded against the applicable parcel and running with the land, in a form attached as Exhibit [●].

- Compliance. Developer shall comply with the City’s Affordable Housing Compliance Program and shall provide annual income certification documentation to the City’s Community Development Department for all Affordable Units throughout the affordability restriction period.

9.2 Local Hiring.

- Goal. Developer shall use commercially reasonable efforts to achieve a goal of 35% Lakemont residents for construction workforce employment across all Phases of the Project, measured on a cumulative project-wide basis, encompassing both direct employees and employees of general contractors, subcontractors, and material suppliers performing construction work on the Site.

- Reporting. Developer shall submit quarterly reports to the City’s Community Development Department documenting local hiring percentages, including workforce data by trade category, residency information, and total labor hours, within 30 days following the end of each calendar quarter during which active construction is occurring.

- Good-Faith Compliance. Failure to achieve the 35% local hiring goal in any given quarter or on a cumulative basis shall not, in and of itself, constitute a default under this Agreement, provided Developer demonstrates good-faith efforts to achieve the goal, including at minimum posting job openings with the City’s workforce development partners, attending local job fairs, and providing reasonable notice of hiring opportunities to the Community Development Department.

- First-Source Hiring. Developer shall implement a first-source hiring program in partnership with the Lakemont Workforce Center, whereby the Workforce Center will serve as the initial referral source for construction positions generated by the Project.

[Drafting Note — Local Hiring Measurement Basis: The Term Sheet (Section 9) measures the 35% goal on a “cumulative project-wide basis” by reference to “construction workforce employment,” while Resolution R-2025-017, Condition #3(c)(i), measures it by “not less than 35% of all construction labor hours.” These are different metrics (headcount/employment vs. labor hours). Confirm the governing metric. Developer’s position: the good-faith, non-default formulation in the Term Sheet should govern.]

9.3 Living Wage and Permanent Employment.

- Living Wage. To the extent required by Resolution R-2025-017, Condition #3(c)(ii), and subject to the limitations set forth below, Developer shall use commercially reasonable efforts to require that all permanent employees employed at retail establishments and hotel operations within the Project be compensated at a wage rate of not less than $17.50 per hour.

- Scope Limitations. The living wage obligation in Section 9.3(a) shall apply only to: (i) employees of Developer or its affiliates directly employed in operations within the Project; and (ii) employees of commercial tenants to the extent such obligation is expressly imposed in the lease between Developer and such tenant. The living wage obligation shall not apply to: (A) employees of the hotel operator or franchisee, which is anticipated to be an independent third-party operator selected by Developer, unless expressly agreed in the hotel management or franchise agreement; (B) employees of subtenants or sublessees not controlled by Developer; (C) employees of independent contractors providing services to the Project; or (D) any person who is not an employee of a Project occupant.

- Good-Faith; Not a Default. Developer’s obligation under this Section 9.3 is one of commercially reasonable efforts to impose the living wage requirement through its leases and operating agreements. Failure to achieve full compliance due to the actions of third parties not controlled by Developer shall not constitute a default by Developer, provided Developer has used commercially reasonable efforts to impose and enforce the requirement.

- First-Source Hiring (Permanent). Developer shall use commercially reasonable efforts to partner with the Lakemont Workforce Center for the recruitment and hiring of individuals to fill permanent employment positions created within the Project, to the extent such positions are within Developer’s control.

[Drafting Note — Living Wage and Permanent-Employee Requirements (Resolution vs. Term Sheet): City Council Resolution R-2025-017, Condition #3(c), imposes three community-benefit requirements not addressed in the Negotiated Term Sheet: (i) a 35% local hiring goal for construction labor hours (addressed in Section 9.2); (ii) a living wage requirement of $17.50/hour for all permanent employees at retail establishments and hotel operations; and (iii) a first-source hiring program for permanent employment positions. The Term Sheet (Section 9) addresses only construction local hiring and states that “additional community benefit obligations, if any, shall be set forth in the definitive Agreement.” This draft incorporates the Resolution’s requirements but limits their scope to persons and entities within Developer’s control (Developer-favorable), excluding the hotel operator/franchisee, subtenants, and independent contractors, and framing the obligation as commercially reasonable efforts rather than an absolute guarantee. The City is likely to resist these limitations, particularly the exclusion of the hotel operator. Open item — negotiate scope, enforceability against third-party tenants/operators, and whether non-compliance is a default. This is a significant open item that may require a separate Community Benefits Agreement.]

9.4 Public Amenities.

- Public Plaza. Developer shall construct the 2.5-acre public plaza as described in Section 4.5, designed to accommodate seasonal programming, with high-quality landscaping, seating, water features, and public art.

- Community Center. Developer shall construct the 28,000-square-foot community center in consultation with the City’s Parks and Recreation Department, and shall convey the community center to the City upon Substantial Completion of Phase IV, in fee simple, by special warranty deed.

- Community Center Specifications and Cost. The program, design specifications, furnishings, and equipment for the community center shall be set forth in Exhibit [●], agreed by the Parties prior to commencement of Phase IV construction. Developer shall convey the community center fully furnished and equipped per the agreed specifications. The cost of the community center (including furnishings and equipment) shall be included within the Phase IV hard construction budget and shall be eligible for TIF reimbursement to the extent of its public-purpose allocation.

- Public Parking Structure. Developer shall construct the 600-space public parking structure serving the transit station, community center, and adjacent uses, as described in Section 4.5.

[Drafting Note — Community Center Conveyance Terms: The Term Sheet (Section 3.4) and RFP Response (Section 5.5) state the community center is to be “conveyed to the City upon completion at no additional cost” and “fully furnished and equipped per the agreed-upon specifications.” Open items: (i) the detailed program and design specifications (Exhibit [●]) are not yet agreed; (ii) the cost of furnishings and equipment and whether such cost is included in the $71M Phase IV budget or is additional; (iii) the timing of conveyance (upon Substantial Completion of Phase IV vs. upon completion of the community center itself, which may precede Phase IV Substantial Completion); (iv) operating and maintenance responsibility after conveyance; and (v) whether the conveyance is “at no additional cost” to the City beyond the land write-down and other incentives, or whether the City pays a nominal consideration. Developer’s position: specifications and cost should be capped and agreed in advance; conveyance upon Phase IV Substantial Completion; City assumes operating responsibility upon conveyance. Open item.]

## ARTICLE 10. PROJECT FINANCING

10.1 Sources of Funds. Developer’s preliminary sources and uses for the Project are summarized as follows:

| Source | Amount |
| --- | --- |
| Lakeshore Capital Partners Fund III LP — Equity | $51,000,000 |
| Pellegrini Family Trust — Equity | $34,000,000 |
| Total Committed Equity | $85,000,000 |
| Construction Loan — First Prairie National Bank | $210,000,000 |
| TIF Reimbursement (over time, up to) | $48,000,000 |
| Land Write-Down | $9,200,000 |
| Permit Fee Waivers | $1,400,000 |
| Additional Debt/Mezzanine (later phases, to be determined) | $58,400,000 |
| Total Sources | $412,000,000 |

10.2 Construction Loan. First Prairie National Bank has provided a preliminary commitment of $210,000,000 for the Project’s construction financing, subject to execution of this Agreement in a form acceptable to the lender, satisfactory completion of due diligence, and customary loan conditions. Developer anticipates the construction loan will be drawn in tranches corresponding to each Phase. The construction loan facility covers Phase I ($105,000,000), Phase II ($76,000,000), and infrastructure/contingency ($29,000,000); availability for Phases III and IV is subject to a separate supplemental commitment or amendment.

10.3 Equity Demonstration. Developer shall demonstrate committed equity of at least $85,000,000 in the form of audited account statements, executed subscription agreements, or other evidence reasonably acceptable to the City, as a condition precedent to closing under Section 5.4(e).

10.4 Additional Financing for Later Phases. Approximately $58,400,000 in additional debt or mezzanine financing will be required for Phases II through IV. Developer anticipates sourcing this capital through a combination of mezzanine loans, institutional co-investment, and cash flow from completed earlier Phases. The structure and terms of this additional financing have not yet been determined and will be finalized as the Project progresses, subject to the Construction Lender’s consent rights and the Equity Investors’ consent and anti-dilution rights.

[Drafting Note — Additional Financing and Consent Interplay: The Construction Loan Term Sheet (Section 6.3) requires the Lender’s prior written consent to any additional indebtedness secured by the Project, including mezzanine debt and preferred equity treated as debt. The Lakeshore Side Letter (Sections 5.1 and 7(a)) grants Lakeshore preemptive rights in new equity issuances, anti-dilution adjustments, and a consent right over Project-level indebtedness exceeding $268,400,000 in the aggregate. Any additional financing for later phases must be structured to comply with both the Lender’s and Lakeshore’s consent rights, and any equity raise that dilutes the Pellegrini Interest may trigger change-of-control concerns under Article 16 and the Lender’s change-of-control provisions. Open item — coordinate capital structure for later phases with Lender and Equity Investors.]

10.5 Financial Capacity. Developer’s audited financials are prepared by Clearmont Accounting Group LLP. The Developer entity’s net worth is approximately $185,000,000. Developer’s bonding capacity through Ridgepoint Surety Corporation is up to $75,000,000.

## ARTICLE 11. PHASING, TIMELINES, AND FORCE MAJEURE

11.1 Phasing Schedule. The Project shall be constructed in four Phases in accordance with the following schedule:

| Phase | Commencement Deadline | Substantial Completion Deadline |
| --- | --- | --- |
| Phase I | Groundbreaking no later than March 1, 2026 | September 30, 2028 |
| Phase II | Within 12 months of Phase I Substantial Completion | Within 24 months of Phase II commencement |
| Phase III | Within 12 months of Phase II Substantial Completion | Within 30 months of Phase III commencement |
| Phase IV | Concurrent with Phase III commencement | Within 24 months of Phase IV commencement |

The commencement deadline for each subsequent Phase is measured from the Substantial Completion date of the immediately preceding Phase, as may be extended by Force Majeure. Developer shall provide quarterly construction progress reports to the City’s Community Development Department, including percentage of completion, updated schedule, and identification of delays, within 30 days following the end of each calendar quarter.

11.2 Force Majeure.

- Definition. “Force Majeure” means events beyond Developer’s reasonable control, including without limitation: acts of God, fire, flood, earthquake, severe weather, pandemic, epidemic, quarantine, governmental health orders, war, terrorism, civil unrest, insurrection, strikes or labor disputes (other than those caused by Developer’s labor practices or failure to comply with applicable labor laws), industry-wide supply chain disruptions beyond Developer’s reasonable control, governmental moratoria on construction, actions or inactions of governmental authorities (other than the City of Lakemont) that prevent or materially delay construction, and delays in IEPA approval of the RAP or issuance of the NFR Letter for Parcel 016 that are not attributable to Developer’s failure to diligently pursue remediation.

- Effect. Force Majeure events shall extend the applicable deadlines for commencement and Substantial Completion on a day-for-day basis for the duration of the Force Majeure event.

- Aggregate Cap. The maximum extension of time available under this Section 11.2 shall not exceed 18 months in the aggregate across the Project.

- Notice. Developer shall provide written notice to the City within 15 business days of the occurrence of a Force Majeure event, describing the nature, anticipated duration, and expected impact on the Project timeline, with updated notices as circumstances change.

- Mitigation. Developer shall use commercially reasonable efforts to mitigate the effects of any Force Majeure event.

- Exclusions. Force Majeure shall not include: financial inability to perform, changes in market conditions, increases in the cost of labor or materials (unless attributable to an industry-wide supply chain disruption), Developer’s failure to obtain financing, or any event caused by Developer’s negligence or willful misconduct.

[Drafting Note — Force Majeure Cap Conflict (Term Sheet vs. Lender): The Term Sheet (Section 14) provides an aggregate Force Majeure extension cap of 18 months across the Project. The Construction Loan Term Sheet (Section 9, Event of Default #9) provides that failure to achieve Phase I Substantial Completion by September 30, 2028 is an Event of Default “subject to force majeure extensions of up to 180 days” (6 months) for Phase I. If Developer relies on the full 18-month project-wide Force Majeure allowance and a substantial portion is consumed by Phase I delays, Developer could exceed the Lender’s 180-day Phase I cap and trigger a loan Event of Default, even though the Development Agreement permits the extension. This is a direct conflict between the Development Agreement and the Construction Loan Documents. Developer must reconcile the Force Majeure caps with the Lender, or negotiate a higher Phase I cap in the Construction Loan Documents. Open item — high priority.]

[Drafting Note — IEPA/NFR Delay as Force Majeure: This draft (Section 11.2(a)) expressly includes delays in IEPA approval of the RAP or issuance of the NFR Letter as Force Majeure, provided Developer diligently pursues remediation. The Phase II ESA Summary (Section 8.2(d)) recommends that the transactional documents establish whether remediation delay constitutes Force Majeure, a basis for deadline extension, or a potential default. Developer’s position: IEPA/regulatory delay not attributable to Developer should be Force Majeure. The City may seek to limit this. Open item.]

## ARTICLE 12. DEFAULT AND CURE

12.1 Monetary Defaults. In the event of a monetary default by either Party (including Developer’s failure to pay the land purchase price or the City’s failure to fund committed infrastructure amounts), the non-defaulting Party shall provide written notice specifying the nature and amount of the default. The defaulting Party shall have 60 days from receipt of such notice to cure the default.

12.2 Non-Monetary Defaults. In the event of a non-monetary default by either Party (including failure to commence construction within applicable deadlines, failure to comply with affordable housing requirements, or failure to maintain required insurance), the non-defaulting Party shall provide written notice specifying the nature of the default in reasonable detail. The defaulting Party shall have 90 days from receipt of such notice to cure the default; provided, that if the nature of the default is such that it cannot reasonably be cured within 90 days, the defaulting Party shall have such additional time as is reasonably necessary to effect a cure, so long as the defaulting Party has commenced cure efforts within the initial 90-day period and is diligently and continuously pursuing cure to completion.

12.3 Termination by City. The City shall have the right to terminate this Agreement upon: (a) a material breach by Developer that remains uncured after the expiration of the applicable cure period (including the Construction Lender’s extended cure periods under Section 14.2); (b) Developer’s failure to commence Phase I construction within 6 months following land conveyance; (c) Developer’s abandonment of the Project, evidenced by cessation of all construction activity for 180 consecutive days (other than cessation caused by Force Majeure); and (d) such other events of default as may be specified in this Agreement. Upon a termination under this Section 12.3 arising from Developer’s completion failure, the City’s sole and exclusive real-property remedy shall be the Repurchase Option set forth in Section 7.5, and the City shall have no right to compel reconveyance or assert any reversionary interest.

12.4 Termination by Developer. Developer shall have the right to terminate this Agreement upon: (a) the City’s failure to deliver clean, marketable, and insurable title to the Site at closing in accordance with Article 5; (b) the City’s failure to fund its committed infrastructure obligations ($12,500,000) within the timelines specified in Exhibit [●]; (c) a condemnation or taking by eminent domain (by any entity other than the City) of more than 15% of the Site; and (d) such other events of default as may be specified in this Agreement.

12.5 Remedies. Upon termination of this Agreement by a non-defaulting Party, the non-defaulting Party shall have all remedies available at law or in equity, including damages, specific performance, and injunctive relief, subject in all cases to the dispute resolution provisions of Article 15. Except as expressly provided in Section 7.5, neither Party shall have any reversionary interest in the Site or any improvements thereon.

## ARTICLE 13. CONDITIONS PRECEDENT TO EXECUTION

The execution of this Agreement shall be subject to the satisfaction or waiver of the following conditions precedent:

- Rezoning of the Site from M-2 to PD-TOD approved by the City Council and effective under applicable law (and, if required by the Construction Lender, expiration of the applicable appeal period);

- Parcel consolidation completed or authorized by the applicable county authority;

- IEPA approval of the RAP for Parcel 12-24-300-016 under the VSRP;

- Developer’s demonstration of committed equity of at least $85,000,000, in form and substance reasonably acceptable to the City;

- Approval of this Agreement by the Lakemont City Council; and

- Confirmation from First Prairie National Bank that this Agreement is in a form acceptable to the lender as a condition of the construction loan commitment.

## ARTICLE 14. CONSTRUCTION LENDER PROTECTIONS

14.1 Lender Review. This Agreement shall be delivered to the Construction Lender in draft form not less than 15 business days prior to its proposed execution date and shall not be executed until the Construction Lender has confirmed in writing that it is in form and substance acceptable to the Construction Lender.

14.2 Lender Cure Rights. The Construction Lender shall have the right (but not the obligation) to receive prompt written notice of any Developer default under this Agreement and a reasonable opportunity to cure such default. The Construction Lender’s additional cure period shall be not less than 30 days beyond Developer’s cure period for monetary defaults and not less than 60 days beyond Developer’s cure period for non-monetary defaults, with such periods extended as necessary if the Construction Lender is diligently pursuing a cure that requires additional time (including time necessary to obtain possession of the Site through foreclosure or appointment of a receiver).

14.3 Lender Consent to Amendments. No material amendment, modification, supplement, or termination of this Agreement shall be effective without the Construction Lender’s prior written consent, which shall not be unreasonously withheld, conditioned, or delayed.

14.4 Subordination of City Interests. Any lien, encumbrance, or security interest that the City may hold or acquire in the Site (other than the Repurchase Option, which is subordinate to the Construction Lender’s mortgage by its terms under Section 7.5) shall be subordinated to the Construction Lender’s mortgage pursuant to a subordination and intercreditor agreement in form and substance acceptable to the Construction Lender. TIF reimbursement obligations under this Agreement are contractual rights and not liens on real property.

14.5 Foreclosure / Deed-in-Lieu. This Agreement shall permit assignment to a Construction Lender-designee or to a third-party purchaser at a foreclosure sale (or pursuant to a deed-in-lieu of foreclosure) without the City’s prior consent; or, if City consent is required, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within 30 days of request.

14.6 Estoppel Certificates. The City shall deliver estoppel certificates to the Construction Lender upon reasonable request (not more than twice per calendar year), certifying the status of this Agreement, the existence or absence of any outstanding defaults, and such other customary matters as the Construction Lender may reasonably request.

[Drafting Note — Lender Protections: The Construction Loan Term Sheet (Section 12) requires the foregoing Lender protections as conditions of the loan: Lender review right, cure rights (30/60 days beyond Developer’s cure periods), consent to material amendments, subordination of City interests, foreclosure/deed-in-lieu assignment rights, and estoppel certificates. These provisions are essential to close the construction loan and are incorporated here. The City must agree to these provisions, which limit the City’s ability to terminate or amend the Agreement without Lender involvement. Open item — confirm City acceptance.]

## ARTICLE 15. INDEMNIFICATION; DISPUTE RESOLUTION

15.1 Mutual Indemnification. Each Party shall indemnify, defend, and hold harmless the other Party, and its officers, employees, agents, and representatives, from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to the indemnifying Party’s negligent acts or omissions, reckless conduct, or willful misconduct in connection with the performance of its obligations under this Agreement.

15.2 Developer Indemnification of City. Developer shall indemnify, defend, and hold harmless the City from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to construction activities on the Site, including without limitation claims for personal injury, death, property damage, and workers’ compensation, regardless of whether brought by Developer’s employees, contractors, subcontractors, or third parties.

15.3 City Indemnification of Developer. The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to pre-existing environmental conditions on the City-owned parcels, as more particularly set forth in Section 7.3.

15.4 Survival. The indemnification obligations set forth in this Article 15 and Section 7.3 shall survive the expiration or termination of this Agreement.

15.5 Dispute Resolution.

- Negotiation. The Parties shall first attempt to resolve any dispute arising under or related to this Agreement through good-faith negotiation between the City Manager (or designee) and Developer’s CEO (or designee) for a period of 30 days following written notice of the dispute.

- Mediation. If the dispute is not resolved through negotiation within the 30-day period, the dispute shall be submitted to non-binding mediation before the Lakemont Mediation Center, or such other neutral mediator as the Parties may agree. The costs of mediation shall be shared equally by the Parties, and each Party shall bear its own attorneys’ fees.

- Binding Arbitration. If the dispute is not resolved through mediation within 60 days following submission to the mediator, the dispute shall be submitted to final and binding arbitration administered under the Commercial Arbitration Rules of the American Arbitration Association, conducted by a single arbitrator with experience in real estate development matters.

- Venue. All mediation and arbitration proceedings shall be conducted in Cook County or Lake County, Illinois.

- Provisional Remedies. Nothing in this Section 15.5 shall prevent either Party from seeking temporary restraining orders, preliminary injunctions, or other provisional judicial relief where necessary to prevent irreparable harm, pending resolution of the dispute through the procedures set forth above.

[Drafting Note — Dispute Resolution Administrator: The Term Sheet (Section 17) specifies mediation before the “Lakemont Mediation Center,” while the Lakeshore Side Letter (Section 10.2) specifies mediation “administered by the American Arbitration Association.” Both proceed to binding AAA arbitration. The mediation administrator differs. Minor open item — confirm the mediation administrator. Developer’s position: the Term Sheet’s Lakemont Mediation Center (or a mutually agreed neutral) is acceptable.]

## ARTICLE 16. ASSIGNMENT AND CHANGE OF CONTROL

16.1 Restriction. Developer may not assign this Agreement or any interest therein, in whole or in part, without the prior written consent of the City, which consent may be withheld in the City’s reasonable discretion.

16.2 Permitted Assignment. Notwithstanding Section 16.1, Developer may assign this Agreement without the City’s prior written consent to an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds at least a [50]% controlling interest and which entity expressly assumes in writing all of Developer’s obligations under this Agreement. Developer shall provide the City with written notice of any such permitted assignment, together with a copy of the assignment and assumption agreement, within 15 days of the effective date.

16.3 Additional Permitted Transfers. In addition to the permitted assignment in Section 16.2, and without the City’s consent, the following transfers shall not constitute an assignment or change of control for purposes of this Agreement:

- Transfers of membership interests among the existing members of Developer (Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, and TransitWorks Equity Group LLC), provided the Pellegrini Interest is not reduced below [50]%; and

- Transfers by Marcus J. Pellegrini for estate planning purposes to family trusts or entities controlled by Pellegrini, provided Pellegrini retains management control; and

- Capital raises and admissions of new members that have been approved by both the Equity Investors (pursuant to the Lakeshore Side Letter) and the City, including capital raises for Phases III and IV, provided that the Pellegrini Interest is not reduced below [50]% without the City’s prior written consent; and

- Transfers to a Construction Lender-designee or third-party purchaser pursuant to a foreclosure or deed-in-lieu of foreclosure, in accordance with Section 14.5.

16.4 Key Person Provision. As an alternative or supplement to the percentage-of-interest thresholds in this Article 16, the Parties acknowledge that the City’s selection of Developer was based, in substantial part, on the qualifications, experience, and financial capacity of Marcus J. Pellegrini. Accordingly, Marcus J. Pellegrini shall serve as Manager and Chief Executive Officer of Developer and shall exercise day-to-day management authority over the Project. If Pellegrini ceases to serve in such role, he shall be replaced by a person reasonably approved by the City within 60 days; failure to so replace shall constitute a default subject to the cure provisions of Article 12.

16.5 Cure Period. Any purported assignment in violation of this Article 16 shall be void and of no force and effect. Before any assignment default is triggered, Developer shall have a cure period of not less than 60 days to remedy any violation, including by unwinding the non-permitted transfer or obtaining the City’s consent.

16.6 Definition. For purposes of this Article 16, “assignment” includes any direct or indirect transfer, conveyance, pledge, hypothecation, or other disposition of this Agreement or any interest therein, whether voluntary or involuntary, by operation of law or otherwise. “Pellegrini Interest” means the aggregate direct and indirect membership interest in Developer held by Marcus J. Pellegrini and/or the Pellegrini Family Trust.

[Drafting Note — Change-of-Control Threshold Conflict (Three-Way): Three different controlling-interest thresholds appear across the source documents: (i) the Term Sheet (Section 10) permits assignment to an entity in which Pellegrini holds “at least a 50% controlling interest”; (ii) the Construction Loan Term Sheet (Section 8.1) defines a Change of Control if Pellegrini ceases to hold “at least a [50]%” interest (bracketed, under negotiation), and separately if any new investor acquires 25% or more; and (iii) the Lakeshore Side Letter (Sections 4.4 and 5.2) triggers enhanced consent rights and a Change of Control if the Pellegrini Interest falls below 51%. The Lakeshore Side Letter (Section 8.3) expressly contemplates that the Development Agreement’s assignment and change-of-control provisions must be harmonized with Lakeshore’s rights, anticipated future capital raises, and the Lender’s covenants, including (i) carve-outs for internal transfers, (ii) carve-outs for capital raises approved by both Lakeshore and the City, (iii) a Key Person provision as an alternative to rigid percentage thresholds, and (iv) a 60-day cure period. This draft incorporates all of those elements. The 50%/51%/[50]% discrepancy must be reconciled. Developer’s position: a single 50% threshold with a Key Person alternative and broad permitted-transfer carve-outs provides the flexibility needed for later-phase capital raises while preserving Pellegrini’s control. Open item — reconcile threshold with City, Lender, and Lakeshore.]

## ARTICLE 17. CONSTRUCTION STANDARDS

17.1 Prevailing Wage. All construction performed on the Project shall comply with the Illinois Prevailing Wage Act, 820 ILCS 130/0.01 et seq. Developer shall include prevailing wage requirements in all contracts and subcontracts for construction work, shall maintain certified payroll records and make them available to the City and the Illinois Department of Labor upon request, and shall post prevailing wage rate schedules at the construction site.

[Drafting Note — Prevailing Wage Scope: The TIF District Summary Memo (Section V) recommends that, given the substantial public financial assistance (land write-down, TIF, abatement, fee waivers), the Prevailing Wage Act likely applies to all construction activity on the Project site, not merely TIF-reimbursed components, and that the Term Sheet’s “all construction” language converts a debatable statutory question into an unambiguous contractual obligation. The Memo notes this may increase costs for purely private components (market-rate residential, office, hotel). This draft adopts the Term Sheet’s “all construction” formulation. Developer should be aware of the cost implications. Open item — confirm scope and whether any purely private components may be carved out, subject to legal advice.]

17.2 LEED Certification. All buildings within the Project shall be designed and constructed to achieve LEED Gold certification (or an equivalent green building certification as may be approved by the City in writing) as administered by the U.S. Green Building Council. Developer shall provide evidence of LEED registration for each building prior to commencement of construction and shall submit documentation of certification status upon receipt, or a status report if certification has not been achieved. The specific LEED rating system applicable to each building component shall be identified in Exhibit [●].

17.3 Insurance. Developer shall maintain, or cause its general contractor to maintain, throughout the construction period for each Phase, the following minimum insurance coverages:

- Commercial General Liability (CGL): $10,000,000 per occurrence and $25,000,000 in the aggregate, including coverage for premises/operations, products/completed operations, contractual liability, and broad-form property damage;

- Umbrella/Excess Liability: $25,000,000 per occurrence and in the aggregate, in excess of the CGL policy;

- Builder’s Risk: Full replacement value of each Phase under construction, on an all-risk basis;

- Workers’ Compensation: Statutory limits as required by Illinois law;

- Automobile Liability: $5,000,000 combined single limit; and

- Pollution Legal Liability: $10,000,000, naming the City and the Construction Lender as additional insured.

The City of Lakemont shall be named as an additional insured on the CGL and umbrella/excess liability policies. Certificates of insurance shall be provided to the City prior to land conveyance and updated annually and upon renewal. All policies shall provide at least 30 days’ prior written notice to the City of cancellation, non-renewal, or material modification.

[Drafting Note — Insurance Aggregate Conflict: The Term Sheet (Section 11.3) specifies CGL coverage of $10,000,000 per occurrence and $20,000,000 in the aggregate, while the Construction Loan Term Sheet (Section 5) specifies $10,000,000 per occurrence and $25,000,000 in the aggregate. This draft adopts the higher $25,000,000 aggregate (the Lender’s requirement) to satisfy both. The Term Sheet also does not require Pollution Legal Liability, which the Construction Loan Term Sheet (Section 4.3) requires at $10,000,000; this draft includes it. Confirm and reconcile.]

## ARTICLE 18. REPRESENTATIONS AND WARRANTIES

18.1 Mutual. Each Party represents and warrants that it has full power and authority to enter into this Agreement and to perform its obligations hereunder, and that the execution and delivery of this Agreement has been duly authorized by all necessary action.

18.2 Developer. Developer represents and warrants that it has the financial capacity, development experience, and organizational resources necessary to complete the Project in accordance with the terms of this Agreement.

18.3 City. The City represents and warrants that: (a) it has good and marketable fee simple title to the Site, free and clear of all liens, encumbrances, and adverse claims (except Permitted Exceptions), and the legal authority to convey the Site to Developer; and (b) the Site is located within the TIF District and TIF funds are legally available for the purposes described in this Agreement, subject to annual appropriation and the availability of increment.

## ARTICLE 19. MISCELLANEOUS

19.1 Notices. All notices shall be in writing and deemed delivered upon personal delivery, upon delivery by nationally recognized overnight courier, or three business days following deposit in the U.S. mail, registered or certified, return receipt requested, postage prepaid, addressed as follows:

If to Developer: Granite City Development LLC 900 West Monroe Street, Suite 2200 Chicago, IL 60607 Attn: Marcus J. Pellegrini, Manager and CEO With a copy to: Thornfield & Pratt LLP 311 South Wacker Drive, Suite 5400 Chicago, IL 60606 Attn: Catherine M. Albrecht

If to City: City of Lakemont Office of the City Manager 200 Civic Center Drive Lakemont, IL 60048 Attn: Gerald T. Fong, City Manager With a copy to: Office of Corporation Counsel City of Lakemont 200 Civic Center Drive Lakemont, IL 60048 Attn: Rebecca A. Sinclair, Esq. With a copy to: Ashford, Keene & Mulvaney LLP 150 North Michigan Avenue, Suite 3200 Chicago, IL 60601 Attn: Jonathan Ashford

Either Party may change its notice address by written notice to the other Party.

19.2 Governing Law. This Agreement shall be governed by and construed in accordance with the laws of the State of Illinois.

19.3 Confidentiality. The terms and contents of this Agreement are confidential and shall not be disclosed by either Party to any third party, except: (a) to each Party’s legal counsel, financial advisors, accountants, lenders, and equity investors, as reasonably necessary; (b) as required by applicable law or governmental regulation, including the Illinois Freedom of Information Act (5 ILCS 140/) as applicable to the City; and (c) to the extent necessary for City Council proceedings and other governmental approvals related to the Project.

19.4 Severability. If any provision of this Agreement is held invalid or unenforceable, such invalidity shall not affect other provisions that can be given effect without the invalid provision, and to this end the provisions of this Agreement are severable.

19.5 Entire Agreement; Amendment. This Agreement, together with its exhibits, constitutes the entire agreement between the Parties with respect to the subject matter hereof and supersedes the Term Sheet upon execution and delivery by both Parties. This Agreement may be amended only by a written instrument executed by both Parties (and, with respect to material amendments, with the Construction Lender’s consent under Section 14.3). Each Party shall bear its own costs and expenses incurred in connection with the negotiation and preparation of this Agreement.

19.6 Counterparts. This Agreement may be executed in counterparts, each of which shall be deemed an original and all of which together shall constitute one instrument. Signatures transmitted by electronic means shall be deemed original signatures.

19.7 Survival. The provisions of this Agreement that by their nature are intended to survive termination or expiration shall survive, including without limitation Article 7 (Environmental Matters), Article 15 (Indemnification), and Section 9.1 (Affordable Housing).

## ARTICLE 20. EXHIBITS

The following exhibits are attached to and incorporated into this Agreement:

- Exhibit A — Legal Description of the Site [to be attached]

- Exhibit B — Site Plan and Phasing Plan [to be attached]

- Exhibit C — Project Budget [to be attached]

- Exhibit D — Form of Restrictive Covenant for Affordable Housing [to be attached]

- Exhibit E — Form of Phase I Performance Security [to be attached]

- Exhibit F — Infrastructure Funding and Disbursement Schedule [to be attached]

- Exhibit G — Community Center Program and Design Specifications [to be attached]

- Exhibit H — Permitted Exceptions to Title [to be attached]

- Exhibit I — LEED Rating System Applicable to Each Building [to be attached]

[Drafting Note — Exhibits: The Term Sheet (Section 19) contemplates exhibits including a site plan, phasing plan, project budget, and form of restrictive covenant for affordable housing. Several additional exhibits are required by the source documents: infrastructure funding schedule (Term Sheet Section 5.3), community center specifications (Section 9.4), Permitted Exceptions (Lender Section 4.2), and LEED rating systems (Term Sheet Section 11.2). All exhibits are placeholders to be prepared and attached.]

SIGNATURE PAGE FOLLOWS

## SIGNATURE PAGE

DEVELOPMENT AGREEMENT — LAKEMONT STATION COMMONS

GRANITE CITY DEVELOPMENT LLC

By: _______________________

Name: Marcus J. Pellegrini

Title: Manager and Chief Executive Officer

Date: _______________________

CITY OF LAKEMONT, ILLINOIS

By: _______________________

Name: Gerald T. Fong

Title: City Manager

Date: _______________________

APPROVED AS TO FORM:

Rebecca A. Sinclair, Esq.

Corporation Counsel, City of Lakemont

Date: _______________________

## APPENDIX — INDEX OF DRAFTING NOTES AND OPEN ITEMS

The following index summarizes the bracketed drafting notes appearing throughout this draft, organized by topic, to facilitate negotiation. These notes are not part of the operative agreement.

A. Critical / High-Priority Open Items

- Reversionary Interest vs. Lender Prohibition (Section 7.5; Notes at Sections 3.4, 7.5). City Council Resolution R-2025-017, Condition #8 requires a reversionary interest with automatic reversion if Phase I is not Substantially Complete within 36 months of conveyance. The Construction Loan Term Sheet (Sections 4.2, 7.1, 12) absolutely prohibits any reversionary or defeasible interest as a condition of the loan, stating it would make the loan “impossible to close.” This draft substitutes a contractual Repurchase Option subordinate to the Lender’s mortgage. Requires City agreement and Lender written confirmation. Highest priority.

- Force Majeure Cap Conflict (Section 11.2; Note at Section 11.2). Term Sheet provides 18-month aggregate cap; Construction Loan Term Sheet provides 180-day Phase I cap. Direct conflict between the Development Agreement and the Construction Loan Documents. Must reconcile with Lender.

- Living Wage and Permanent-Employee Requirements (Section 9.3; Note at Section 9.3). Resolution R-2025-017, Condition #3(c) imposes a $17.50/hour living wage and first-source hiring for permanent employees — not addressed in the Term Sheet. This draft limits scope to persons/entities within Developer’s control. City likely to resist. May require a separate Community Benefits Agreement.

- Change-of-Control Threshold (Section 16; Note at Section 16). Three thresholds: 50% (Term Sheet), [50]% bracketed (Lender), 51% (Lakeshore Side Letter). Must reconcile with City, Lender, and Lakeshore.

B. Cross-Document Conflicts Requiring Confirmation

- RFP Number (Section 1.2(d); Note at Section 1.2(d)). RFP Response Narrative: “RFP No. 2024-CD-07”; Term Sheet: “RFP No. 2024-CD-018.” Confirm correct number.

- Parcel Acquisition History (Section 1.2(a); Note at Section 1.2(a)). Term Sheet/Resolution/TIF Memo: Parcels 015 and 016 by tax forfeiture (2016), 017 by direct purchase (2018). Phase II ESA: Parcel 015 by tax forfeiture (2016), Parcels 016 and 017 by direct purchase (2018). Affects title, indemnification, consolidation.

- Per-Parcel Acreage (Section 1.2(a); Note at Section 1.2(a)). RFP Response and Phase II ESA give different per-parcel acreages. Confirm by ALTA/NSPS survey.

- Insurance CGL Aggregate (Section 17.3; Note at Section 17.3). Term Sheet: $20M aggregate; Lender: $25M aggregate. Draft adopts $25M. Confirm.

- Equity Demonstration Timing (Section 5.4(e); Note at Section 5.4). Resolution: within 60 days of Resolution adoption (by April 19, 2025); Term Sheet: within 60 days of DA approval. Reconcile triggers/deadlines.

- Local Hiring Measurement Basis (Section 9.2; Note at Section 9.2). Term Sheet: cumulative construction workforce employment; Resolution: 35% of construction labor hours. Confirm metric.

- Affordable Unit Count (Section 4.6; Note at Section 4.6). Term Sheet references “at least 100” in one place; breakdown and Resolution state 106 (20%). Standardize on 106.

C. Open Items Requiring Negotiation / Further Documentation

- NFR Letter vs. RAP Approval; Phased Conveyance (Sections 3.3, 5.4, 11.2; Notes at Sections 3.3, 5.4). Whether the condition precedent is RAP approval or NFR Letter; whether phased conveyance of clean parcels is feasible; whether remediation delay is Force Majeure. 14–18 month remediation timeline vs. March 1, 2026 groundbreaking.

- Environmental Cost Overrun Allocation (Section 7.4; Note at Section 7.4). Phase II ESA recommends 25%–35% contingency; total exposure potentially $3.8M–$4.2M for Parcel 016 alone. Developer’s position: City bears overrun risk. City may resist.

- Additional Investigation Costs (Section 7.4; Note at Section 7.4). Plume delineation, off-site Metra groundwater monitoring, vapor intrusion screening — not in $3.14M estimate. Confirm treatment and Metra access.

- TIF Shortfall Risk (Section 6.2; Note at Section 6.2). TIF Memo projects $6M–$10M shortfall under abatement scenario; greater under worst-case timing. Priority structure and good-faith extension covenant included; consider additional protections.

- Land Write-Down / Infrastructure Funding Source vs. TIF Cap (Sections 6.1, 6.3; Notes at Sections 6.1, 6.3). Whether $9.2M write-down and $12.5M infrastructure are charged against the $48M TIF cap. Developer’s position: separate, non-TIF sources.

- Abatement/TIF Interaction (Section 6.4; Note at Section 6.4). Phase I abatement reduces TIF increment. Consider structuring abatement to apply only to non-TIF-captured portion, if legally permissible.

- Abatement Scope for Later Phases (Section 6.4; Note at Section 6.4). Abatement limited to Phase I. Developer may seek abatement for later phases.

- Hotel Brand Approval (Section 4.4; Note at Section 4.4). Brand “to be determined.” Confirm whether City approval required.

- Community Center Conveyance Terms (Section 9.4; Note at Section 9.4). Specifications, furnishings cost, timing, operating responsibility, consideration. Open items.

- Later-Phase Performance Security (Section 8.3; Note at Section 8.3). Amounts/form for Phases II–IV to be established. Developer favors limited security.

- Additional Financing and Consent Interplay (Section 10.4; Note at Section 10.4). $58.4M later-phase financing subject to Lender and Lakeshore consent rights; equity raises may trigger change-of-control. Coordinate capital structure.

- Rezoning Appeal Period (Section 3.2; Note at Section 3.2). Lender requires expiration of appeal period; Term Sheet requires effectiveness only. Allocate appeal risk.

- Lender Protections (Article 14; Note at Section 14.6). Lender review, cure, consent, subordination, foreclosure, estoppel — required to close loan. Confirm City acceptance.

- Prevailing Wage Scope (Section 17.1; Note at Section 17.1). TIF Memo recommends “all construction” coverage; cost implications for private components. Confirm scope.

- Dispute Resolution Mediation Administrator (Section 15.5; Note at Section 15.5). Term Sheet: Lakemont Mediation Center; Lakeshore Side Letter: AAA. Confirm.

- Exhibits (Article 20; Note at Article 20). All exhibits are placeholders to be prepared and attached.

[END OF DRAFT]

This draft was prepared on behalf of Granite City Development LLC by Thornfield & Pratt LLP (Catherine M. Albrecht, lead partner) for negotiation purposes. It is circulated subject to the bracketed drafting notes and open items identified herein and is not a final or binding agreement until executed by both Parties and approved by the Lakemont City Council.