# DEVELOPMENT AGREEMENT

## LAKEMONT STATION COMMONS MIXED-USE TRANSIT-ORIENTED DEVELOPMENT

by and between

GRANITE CITY DEVELOPMENT LLC (an Illinois limited liability company)

and

THE CITY OF LAKEMONT, ILLINOIS (an Illinois home rule municipality)

Dated as of [•], 2025

[Drafting Note — Open Item: The target execution date reflected across the source documents is June 2025 (Negotiated Term Sheet §19; Lakeshore Side Letter §1(E)). Execution is contingent on satisfaction of the conditions precedent set forth in Article IX, including completion of the PD-TOD rezoning, IEPA approval of the Remedial Action Plan for Parcel 016, equity demonstration, and Lender/Investor review of this Agreement. The date should be confirmed once those conditions are satisfied.]

## RECITALS

A. The Property. The City of Lakemont, Illinois (the “City”) is the owner in fee simple of certain real property commonly known as 1400–1550 Lakemont Station Boulevard, Lakemont, Illinois 60048, consisting of three (3) separate parcels of record identified by Parcel Identification Numbers 12-24-300-015, 12-24-300-016, and 12-24-300-017, totaling approximately 12.7 acres (553,212 square feet) (collectively, the “Property”). The Property constitutes the former site of the Lakemont Ironworks manufacturing campus, which ceased industrial operations in 2009, and is situated immediately adjacent to the Lakemont Central Metra commuter rail station on the Metra Milwaukee District/North Line.

[Drafting Note — Cross-Document Conflict: The source documents conflict regarding (i) the individual acreage of the parcels and (ii) the City’s acquisition history for Parcel 016. As to acreage, the Phase II ESA (Greenfield, Nov. 8, 2024) reports Parcel 015 at ~4.2 acres and Parcel 017 at ~4.4 acres, while the RFP Response Narrative (Dec. 16, 2024) reports Parcel 015 at ~3.8 acres and Parcel 017 at ~4.8 acres; the total of ~12.7 acres is consistent. As to acquisition, the City Council Resolution R-2025-017, the Negotiated Term Sheet, and the TIF District Summary Memo all state that Parcels 015 and 016 were acquired by tax forfeiture in 2016 and Parcel 017 by direct purchase in 2018, whereas the Phase II ESA states that Parcel 015 was acquired by tax forfeiture in 2016 and Parcels 016 and 017 by direct purchase in 2018. The acquisition history affects each parcel’s chain of title and any liens or encumbrances arising from the tax-forfeiture versus direct-purchase mechanisms. The City should be required to deliver, as a condition precedent, a current title commitment for each individual parcel and to certify the acquisition history, and the legal descriptions in Exhibit A should be confirmed by survey.]

B. The RFP and Selection of Developer. The City, through its Community Development Department, conducted a competitive Request for Proposals process for the redevelopment of the Property as a mixed-use transit-oriented development. In response, Granite City Development LLC, an Illinois limited liability company (the “Developer”), submitted a proposal and was selected as the preferred developer based on its qualifications, experience, project proposal, and demonstrated financial capacity.

[Drafting Note — Cross-Document Conflict: The RFP Response Narrative identifies the solicitation as “RFP No. 2024-CD-07,” while the Negotiated Term Sheet refers to “RFP No. 2024-CD-018.” The correct RFP number should be confirmed with the City’s Community Development Department and stated consistently throughout the Agreement and the authorizing resolution.]

C. The Negotiated Term Sheet. On January 22, 2025, the Developer, by its Manager, Marcus J. Pellegrini, and the City, by its City Manager, Gerald T. Fong, executed a non-binding Negotiated Term Sheet setting forth the principal economic and legal terms proposed to govern this Agreement.

D. City Council Conditional Approval. On February 18, 2025, the City Council adopted Resolution No. R-2025-017 (the “Resolution”), granting conditional approval for the Project and authorizing the City Manager to negotiate and execute this Agreement, subject to the conditions set forth in Section 3 of the Resolution.

E. The Project. The Developer proposes to develop the Property as a four-phase mixed-use transit-oriented development to be known as “Lakemont Station Commons” (the “Project”), with a total gross building area of approximately 1,620,000 square feet and a total estimated Project cost of approximately Four Hundred Twelve Million Dollars ($412,000,000), as more particularly described in Article IV.

F. Public Incentives. In consideration of the Developer’s undertaking to redevelop a vacant, environmentally contaminated former industrial site and to deliver substantial public benefits, the City has agreed to provide certain public incentives, including a land write-down, tax increment financing reimbursement, infrastructure cost-sharing, property tax abatement, and permit fee waivers, as more particularly described in Article VI.

G. Environmental Conditions. A Phase II Environmental Site Assessment was completed by Greenfield Environmental Consultants LLC in a report dated November 8, 2024 (the “Phase II ESA”), identifying petroleum hydrocarbon (BTEX) contamination on Parcel 016 and low-level metals contamination in fill material on Parcel 017, as more particularly described in Article VII.

H. Financing. The Developer has obtained a preliminary (non-binding) commitment from First Prairie National Bank (the “Construction Lender”) for a construction loan facility of up to Two Hundred Ten Million Dollars ($210,000,000), and has committed equity of Eighty-Five Million Dollars ($85,000,000) from Lakeshore Capital Partners Fund III LP and the Pellegrini Family Trust, in each case subject to execution of this Agreement in form and substance acceptable to the Construction Lender and the equity investors.

I. Authority. The City is a home rule municipality organized under the Constitution and laws of the State of Illinois, including Article VII, Section 6 of the Illinois Constitution of 1970, and is authorized to enter into this Agreement pursuant to its home rule powers and the Illinois Tax Increment Allocation Redevelopment Act, 65 ILCS 5/11-74.4-1 et seq. (the “TIF Act”).

NOW, THEREFORE, in consideration of the mutual covenants and agreements set forth herein, and other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the City and the Developer (each a “Party” and collectively the “Parties”) agree as follows:

## ARTICLE I. DEFINITIONS AND INTERPRETATION

Section 1.1 Definitions. In addition to terms defined elsewhere in this Agreement, the following capitalized terms shall have the meanings set forth below:

- “Affordable Unit” means a residential dwelling unit restricted to occupancy by households earning at or below sixty percent (60%) of Area Median Income, as more particularly described in Article VIII.

- “AMI” means Area Median Income as published annually by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area, or any successor designation.

- “Appraised Value” means the as-is fair market value of the Property of Eighteen Million Four Hundred Thousand Dollars ($18,400,000), as established in the appraisal report of Crossland Appraisal Services dated January 15, 2025.

- “Change of Control” has the meaning set forth in Section 12.2.

- “Construction Lender” means First Prairie National Bank, and any successor construction lender or assignee approved in accordance with the loan documents and this Agreement.

- “Construction Loan Documents” means the definitive loan agreements, mortgages, assignments, guaranties, and other instruments evidencing and securing the construction loan facility.

- “ELUC” means an environmental land use control, in the form of a restrictive covenant recorded against the Property in accordance with the IEPA Voluntary Site Remediation Program and 35 Illinois Administrative Code Part 742.

- “Force Majeure” has the meaning set forth in Section 14.1.

- “IEPA” means the Illinois Environmental Protection Agency.

- “Lender-Approved Form” means, with respect to this Agreement or any amendment, modification, or ancillary instrument, a form that has been reviewed and confirmed in writing by the Construction Lender as acceptable to it.

- “NFR Letter” means a No Further Remediation letter issued by the IEPA under the Voluntary Site Remediation Program.

- “Operating Agreement” means the Amended and Restated Operating Agreement of the Developer, dated as of September 8, 2023, as amended from time to time.

- “Pellegrini Interest” means the aggregate direct and indirect membership interest in the Developer held by Marcus J. Pellegrini and/or the Pellegrini Family Trust, whether held of record or beneficially.

- “Permitted Exceptions” means the exceptions to title set forth in Exhibit B, as the same may be updated in accordance with Section 5.3.

- “Phase I,” “Phase II,” “Phase III,” and “Phase IV” have the meanings and components set forth in Section 4.1.

- “Project Budget” means the detailed line-item budget for the Project set forth in Exhibit C, as the same may be adjusted in accordance with this Agreement.

- “RAP” means a Remedial Action Plan for the environmental remediation of Parcel 016, prepared for submission to and approval by the IEPA under the Voluntary Site Remediation Program.

- “Substantial Completion” means, with respect to a phase of the Project, the completion of construction of that phase to the point where the buildings and improvements can be occupied and used for their intended purposes, as evidenced by the issuance of a temporary or final certificate of occupancy by the City’s Building Department for that phase.

- “TIF District” means the Lakemont Central Tax Increment Financing District established by City Ordinance No. 2019-42, expiring December 31, 2042.

- “TIF Reimbursement” means the reimbursement of eligible redevelopment project costs from tax increment revenues deposited in the Special Tax Allocation Fund of the TIF District, as more particularly described in Section 6.2.

- “VSRP” means the IEPA Voluntary Site Remediation Program established under the Illinois Environmental Protection Act (415 ILCS 5/) and 35 Illinois Administrative Code Part 740.

Section 1.2 Interpretation. The headings used in this Agreement are for convenience only and shall not affect interpretation. References to “Sections,” “Articles,” and “Exhibits” are to sections, articles, and exhibits of this Agreement unless otherwise stated. The words “include,” “includes,” and “including” shall be deemed to be followed by “without limitation.” References to statutes include the rules and regulations promulgated thereunder and any successor provisions. This Agreement shall be construed without regard to any presumption or rule requiring construction against the Party causing this Agreement to be drafted.

## ARTICLE II. THE PROPERTY

Section 2.1 Description. The Property consists of the three parcels identified in Recital A, to be consolidated into a single parcel of record prior to or concurrent with the conveyance of the Property to the Developer, as provided in Article V.

Section 2.1 Conveyance of Clean Parcels; Phased Conveyance Option.

[Drafting Note — Open Item / Cross-Document Conflict: The Phase II ESA (§4.1.3, §5.2, §8.2(d)) strongly recommends a phased conveyance approach—conveying the clean Parcel 015 and Parcel 017 (after engineered barrier) to the Developer first, while Parcel 016 remediation proceeds, so that Phase I construction can commence on the clean portions of the Property without waiting for the 14-to-18-month Parcel 016 remediation and NFR Letter. This protects the March 1, 2026 Phase I groundbreaking deadline. However, a phased conveyance creates tension with (i) the Resolution’s and Term Sheet’s requirement that the three parcels be consolidated into a single parcel prior to or concurrent with rezoning and conveyance, and (ii) the Construction Lender’s requirement (Loan Term Sheet §7.1(3)) that the parcels be consolidated into a single tax parcel acceptable to the Lender and title company as a condition to closing. The Developer’s preferred position is to preserve the option for phased conveyance if the consolidated-conveyance timeline would jeopardize the Phase I schedule; the City and the Construction Lender should be engaged to determine whether a phased conveyance with interim land-use approvals and a mortgage that expands as parcels are conveyed is feasible. This Article should be finalized once the City, Developer, and Construction Lender have confirmed the conveyance structure.]

Section 2.2 Title. The City shall convey the Property to the Developer by special warranty deed, delivering marketable and insurable fee simple absolute title, free and clear of all liens, encumbrances, restrictions, reversionary interests, rights of re-entry, possibilities of reverter, defeasible conditions, and other title defects or exceptions, except for the Permitted Exceptions. The City shall provide, at the City’s expense, an owner’s title insurance policy in the amount of the Purchase Price issued by a nationally recognized title insurance company.

[Drafting Note — Cross-Document Conflict: The Construction Lender (Loan Term Sheet §4.2) and the Developer’s position require that the conveyed title be fee simple absolute and expressly prohibit any reversionary interest, right of re-entry, possibility of reverter, or other defeasible fee estate in favor of the City or any other party, on the ground that such an interest would render the title uninsurable and the Construction Loan unsecurable. This directly conflicts with Resolution R-2025-017, Condition No. (h), which contemplates a reversionary interest as a clawback mechanism. The resolution of this conflict is addressed in Section 5.5 (Alternative Completion Assurance) and is the single most critical open item in this transaction.]

[Drafting Note — Open Item: The Phase II ESA (§1.3) notes that each parcel has a distinct chain of title arising from the different acquisition mechanisms (tax forfeiture versus direct purchase) and recommends a comprehensive per-parcel title review before consolidation to identify any environmental liens, utility easements, unresolved tax claims, or mechanic’s liens from the City’s prior demolition/clearing work. The City should be required to deliver per-parcel title commitments and to clear any such encumbrances at its expense as a condition precedent to conveyance.]

Section 2.3 Environmental Land Use Controls. The ELUC to be recorded against Parcel 017 (and any institutional control recorded in connection with the Parcel 016 NFR Letter) shall be a Permitted Exception. The consolidation plat and the PD-TOD development standards shall expressly reference the institutional control area by legal description. The City acknowledges that below-grade construction within the engineered barrier area on Parcel 017 must comply with an approved soil management plan and IEPA notification requirements, and the City shall cooperate in obtaining any land-use approvals necessary to accommodate such construction.

## ARTICLE III. REZONING AND PARCEL CONSOLIDATION

Section 3.1 City Obligation to Rezone. The City shall, at the City’s sole cost and expense, initiate and pursue to completion the rezoning of the Property from M-2 (General Manufacturing) to PD-TOD (Planned Development–Transit Oriented District), including application filing, plan commission review, public hearings, and City Council action. The rezoning shall be completed, adopted by ordinance, and effective, with any applicable appeal period expired without the filing of any appeal, prior to the execution of this Agreement or as otherwise provided in Article IX.

[Drafting Note — Developer’s Position: The rezoning and parcel consolidation are City governmental actions that the Developer cannot control. The Developer’s interest is to impose a clear City obligation to pursue and complete the rezoning and consolidation at the City’s cost, with the Developer’s reasonable cooperation, and to provide the Developer a termination right (Section 13.2) if the rezoning is not achieved or is materially adverse. The Term Sheet (§18.2) and Resolution (Condition (e)) both make rezoning a condition precedent to execution of the definitive Agreement.]

Section 3.2 City Obligation to Consolidate. The City shall, at the City’s sole cost and expense, complete or authorize the consolidation of Parcels 12-24-300-015, 12-24-300-016, and 12-24-300-017 into a single parcel of record, in coordination with the applicable county authority, prior to or concurrent with the rezoning. The City shall resolve, at its expense, any liens, encumbrances, or title issues unique to the respective chains of title of the individual parcels arising from the tax-forfeiture and direct-purchase acquisitions.

Section 3.3 PD-TOD Development Standards. The PD-TOD ordinance and development standards shall accommodate the density, building heights, use mix, parking ratios, and design standards contemplated by the Project program described in Article IV. The City shall not adopt PD-TOD standards that materially restrict the Developer’s ability to construct the Project as described in this Agreement.

Section 3.4 Cooperation. The Developer shall reasonably cooperate with the City in the rezoning and consolidation proceedings, including providing site plans, phasing plans, and program information reasonably necessary to support the City’s applications. The City shall bear all application fees, hearing costs, and consultant costs associated with the rezoning and consolidation.

## ARTICLE IV. THE PROJECT

Section 4.1 Project Program. The Project shall consist of a mixed-use transit-oriented development constructed in four phases, with the following components and estimated hard construction costs:

| Phase | Components | Gross Building Area | Est. Hard Cost |
| --- | --- | --- | --- |
| Phase I | 320 residential units (256 market-rate + 64 Affordable Units); 45,000 sq ft ground-floor retail; 480-space structured parking | ~420,000 sq ft | $105,000,000 |
| Phase II | 280,000 sq ft Class A office; 18,000 sq ft retail; 350-space structured parking | ~380,000 sq ft | $76,000,000 |
| Phase III | 210 residential units (168 market-rate + 42 Affordable Units); 150-room select-service hotel | ~440,000 sq ft | $88,000,000 |
| Phase IV | 2.5-acre public plaza; 28,000 sq ft community center (conveyed to City); 600-space public parking structure | ~380,000 sq ft | $71,000,000 |
| Total | 530 residential units (106 Affordable); 63,000 sq ft retail; 280,000 sq ft office; 150 hotel rooms; 1,430 parking spaces; 2.5-acre plaza; 28,000 sq ft community center | ~1,620,000 sq ft | $340,000,000 |

Section 4.2 Project Totals. The Project, in the aggregate, shall include five hundred thirty (530) residential dwelling units, of which one hundred six (106) shall be Affordable Units (representing twenty percent (20%) of total residential units); sixty-three thousand (63,000) square feet of retail space; two hundred eighty thousand (280,000) square feet of Class A office space; one hundred fifty (150) hotel rooms; one thousand four hundred thirty (1,430) structured parking spaces; a 2.5-acre public plaza; and a 28,000-square-foot community center. The total estimated hard construction cost is Three Hundred Forty Million Dollars ($340,000,000), and the total estimated Project cost, inclusive of soft costs, land, financing, and environmental remediation, is approximately Four Hundred Twelve Million Dollars ($412,000,000).

[Drafting Note — Cross-Document Conflict: The Negotiated Term Sheet (§12) states that the Developer shall include “at least 100 affordable units” across the Project, while the same section’s breakdown and the Resolution (Condition (g)) and the RFP Response Narrative all specify 106 Affordable Units (20% of 530). Twenty percent of 530 equals 106. The “at least 100” language is internally inconsistent and lower than the 20% minimum. The Developer’s position is to fix the number at 106 Affordable Units (64 in Phase I and 42 in Phase III), which satisfies the 20% affordability requirement, and to remove the ambiguous “at least 100” formulation. The City should confirm.]

Section 4.3 Phasing Schedule. The Project shall be constructed in four phases in accordance with the following schedule:

| Phase | Commencement Deadline | Substantial Completion Deadline |
| --- | --- | --- |
| Phase I | Groundbreaking no later than March 1, 2026 | September 30, 2028 (30 months) |
| Phase II | Within 12 months of Phase I Substantial Completion | Within 24 months of Phase II commencement |
| Phase III | Within 12 months of Phase II Substantial Completion | Within 30 months of Phase III commencement |
| Phase IV | Concurrent with Phase III commencement | Within 24 months of Phase IV commencement |

The commencement deadline for each subsequent phase is measured from the Substantial Completion date of the immediately preceding phase, as may be extended by Force Majeure under Article XIV. The Developer shall provide quarterly construction progress reports to the City’s Community Development Department within thirty (30) days following the end of each calendar quarter during which active construction is occurring.

[Drafting Note — Developer’s Position: The Developer maintains a target accelerated schedule approximately two years ahead of these contractual maximum deadlines (RFP Response Narrative §5.1, §10). The contractual maximums above are the outer boundary and provide schedule resilience. The Developer’s interest is to preserve these maximums as the binding deadlines and to ensure that the commencement and completion triggers are measured from the dates stated above, not from the date of land conveyance (see the conflict flagged in Section 13.1 regarding the Term Sheet’s “six months following land conveyance” commencement trigger).]

Section 4.4 Design Review. The Developer shall submit schematic design, design development, and construction documents for each phase to the City’s Community Development Department for review and approval. The City shall complete its review within thirty (30) business days of submission and shall not unreasonably withhold, condition, or delay approval. The City’s approval shall not be required for matters that are consistent with the PD-TOD development standards and this Agreement. The Developer shall retain design control over the Project, subject to compliance with the PD-TOD standards and the public-benefit commitments in this Agreement.

Section 4.5 LEED Certification. All buildings constructed as part of the Project shall be designed and constructed to achieve LEED Gold certification, or an equivalent green building certification as approved by the Director of the Community Development Department. The Developer shall register each building with the U.S. Green Building Council prior to commencement of construction of the applicable building and shall submit documentation of certification status upon receipt of certification or a status report detailing any deficiencies.

Section 4.6 Community Center Conveyance. The 28,000-square-foot community center constructed as part of Phase IV shall be designed in consultation with the City’s Parks and Recreation Department and shall be conveyed to the City in fee simple upon Substantial Completion of Phase IV, at no additional cost to the City, subject to the TIF reimbursement rights set forth in Section 6.2.

[Drafting Note — Open Item: The Term Sheet and RFP state the community center will be conveyed “at no additional cost” to the City. The community center is included within the Phase IV hard construction cost ($71,000,000) and is a TIF-eligible public facility (TIF District Summary Memo §III.B). The Developer’s interest is to (i) confirm that the community center construction costs are TIF-eligible and reimbursable to the Developer under the priority in Section 6.2, (ii) establish the design specifications and equipment/furnishing scope by agreement before construction, and (iii) ensure that conveyance does not occur until the Developer’s TIF reimbursement rights with respect to the community center are preserved. The timing and mechanics of conveyance, and responsibility for any operating deficits prior to conveyance, should be finalized.]

Section 4.7 Public Parking. The 600-space public parking structure in Phase IV shall be publicly accessible and shall serve the Metra station, the community center, the public plaza, and adjacent commercial uses. The Phase I (480-space) and Phase II (350-space) structured parking facilities shall be made publicly accessible or contractually committed to public use to the extent necessary to qualify as TIF-eligible public improvements, subject to reasonable access agreements and deed restrictions.

[Drafting Note — Open Item: The TIF District Summary Memo (§III.B) notes that the Phase I and Phase II parking structures are “potentially eligible” for TIF reimbursement only to the extent they are publicly accessible or contractually committed to public use, and that access agreements and deed restrictions may be required to confirm eligibility. The Developer’s interest is to structure the parking facilities to maximize TIF eligibility while preserving operational flexibility and revenue. The form of access agreements and deed restrictions should be negotiated and attached as an exhibit.]

## ARTICLE V. LAND CONVEYANCE AND COMPLETION ASSURANCE

Section 5.1 Purchase Price. The City shall convey the Property to the Developer for a purchase price of Nine Million Two Hundred Thousand Dollars ($9,200,000) (the “Purchase Price”), representing fifty percent (50%) of the Appraised Value. The difference between the Appraised Value and the Purchase Price (Nine Million Two Hundred Thousand Dollars ($9,200,000)) constitutes a land write-down incentive (the “Land Write-Down”). The Purchase Price shall be due and payable at closing. The Developer may fund the Purchase Price from equity, construction loan proceeds, or a combination thereof.

Section 5.2 Closing. Closing of the conveyance of the Property (the “Closing”) shall occur within thirty (30) days following the satisfaction or waiver of all conditions precedent set forth in Article IX. The Parties’ target Closing date is mid-2025, subject to the timing of rezoning, IEPA approvals, and the satisfaction of other conditions.

Section 5.3 Permitted Exceptions. The Permitted Exceptions shall be limited to: (i) real estate taxes not yet due and payable; (ii) standard utility and access easements that do not materially interfere with the development, use, or value of the Project; (iii) this Agreement; (iv) covenants and restrictions of the PD-TOD zoning ordinance; (v) the ELUC and institutional controls recorded in connection with the IEPA VSRP NFR Letter for Parcel 016 and the engineered barrier for Parcel 017, in each case as reviewed and approved by the Construction Lender’s counsel; and (vi) such other exceptions as the Developer and the Construction Lender may approve in writing. No reversionary interest, right of re-entry, possibility of reverter, defeasible condition, or other defeasible fee estate in favor of the City or any other party shall be a Permitted Exception.

Section 5.4 Conditions Precedent to Closing. The obligations of the Parties to close the conveyance of the Property are subject to the satisfaction (or waiver by the Party entitled to the benefit) of the conditions precedent set forth in Article IX.

Section 5.5 Alternative Completion Assurance (in lieu of Reversionary Interest).

[Drafting Note — Cross-Document Conflict (CRITICAL): Resolution R-2025-017, Condition No. (h), requires the Developer to grant the City a reversionary interest in the Property such that, if Phase I is not Substantially Complete within thirty-six (36) months of the date of conveyance, fee simple title to the Property (together with improvements) automatically reverts to the City, subject to the City refunding the Purchase Price (net of damages). The Construction Lender’s Term Sheet (§4.2, §7.1(1), §12(a)) expressly prohibits any reversionary interest, right of re-entry, possibility of reverter, or defeasible fee estate, stating that such an interest would (i) be uninsurable under standard ALTA title policies, (ii) subordinate the Construction Lender’s first-priority mortgage to the City’s right to reclaim the property, (iii) prevent foreclosure, and (iv) render the Construction Loan “impossible to close.” The Lakeshore Side Letter (§7(d)) further provides that the Developer may not agree to any clawback, reversionary interest, right of re-entry, repurchase option, or similar mechanism without the Investor’s consent, and requires terms compatible with the Construction Lender’s requirements. The Developer’s position—consistent with both the Construction Lender’s and the Investor’s requirements—is to substitute an alternative completion-assurance mechanism that satisfies the City’s legitimate interest in ensuring timely Phase I completion while preserving the Developer’s fee simple absolute title and the Construction Lender’s first-priority security interest. The mechanism below is drafted as a contractual repurchase option plus liquidated damages, which the Construction Lender has identified as acceptable alternatives (Loan Term Sheet §12(a)(i), (iii)). This is the most significant open item and must be negotiated and confirmed with the City, the Construction Lender, and the Investor before execution.]

[Drafting Note — Cross-Document Conflict (timing): The Resolution’s thirty-six (36) month reversion clock runs from the date of conveyance. If Closing occurs in mid-2025 (as targeted), thirty-six months expires in mid-2028—before the Phase I Substantial Completion deadline of September 30, 2028. The reversion trigger and the Substantial Completion deadline are therefore internally inconsistent. The Developer’s position is that any completion-assurance trigger should be tied to the Phase I Substantial Completion deadline of September 30, 2028 (as extended by Force Majeure and the cure periods in Article XIII), not to a separate thirty-six-month clock from conveyance. The City should confirm.]

- No Reversionary Interest. The Parties acknowledge and agree that the City shall not hold, and the Developer shall not grant, any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other defeasible fee estate in the Property. The Developer’s title to the Property shall be fee simple absolute and indefeasible, subject only to the Permitted Exceptions.

- City Repurchase Option. In lieu of any reversionary interest, and solely as a remedy for the Developer’s uncured failure to achieve Substantial Completion of Phase I by September 30, 2028 (as such date may be extended pursuant to Article XIV (Force Majeure) and the cure periods in Article XIII), the City shall have a contractual option to repurchase the Property (the “Repurchase Option”), exercisable only upon all of the following: (i) the Developer’s failure to achieve Phase I Substantial Completion by the deadline, as extended; (ii) the expiration of all applicable cure periods, including the Construction Lender’s extended cure periods provided in Section 12.4; and (iii) the Construction Lender’s prior written consent or the full satisfaction and release of the Construction Loan. The Repurchase Option shall be exercisable for a period of one hundred eighty (180) days after the satisfaction of clauses (i) through (iii). The repurchase price shall be the lesser of (A) the Purchase Price paid by the Developer, or (B) the then-current fair market value of the Property as determined by an independent MAI appraiser mutually selected by the Parties. The Repurchase Option shall be subordinate to the Construction Lender’s mortgage and shall not be exercisable until the Construction Lender’s lien is satisfied or the Construction Lender has consented.

- Liquidated Damages Alternative. As an alternative to the Repurchase Option, and at the Developer’s election, the Developer may satisfy the City’s completion-assurance objective by paying to the City liquidated damages in a predetermined amount representing a reasonable pre-estimate of the City’s actual damages resulting from the failure to timely complete Phase I. The Parties acknowledge that the actual damages to the City from a completion delay would be difficult to ascertain and that the liquidated damages amount set forth in Exhibit D is a reasonable pre-estimate and not a penalty. Such liquidated damages shall constitute an unsecured contractual obligation of the Developer and shall not constitute a lien on the Property.

- Performance Security. The Developer’s completion obligations are additionally secured by the Performance Security provided in Article XI. The Parties acknowledge that the Performance Security, the Repurchase Option, and the liquidated damages alternative, together with the Construction Lender’s completion guaranty, collectively provide the City with substantial assurance of timely Phase I completion without impairing the Developer’s fee simple title.

[Drafting Note — Open Item: The specific liquidated damages amount (Exhibit D) and the precise mechanics of the Repurchase Option (including the appraisal procedure, the Construction Lender consent condition, and the interplay with the Construction Lender’s foreclosure rights) must be finalized in consultation with the City, the Construction Lender, and the Investor. The Construction Lender has also suggested an enhanced completion guaranty and a right of first refusal as additional acceptable alternatives (Loan Term Sheet §12(a)(iv), (v)); the Developer may propose one or more of these in lieu of, or in addition to, the mechanisms above.]

## ARTICLE VI. PUBLIC INCENTIVES

Section 6.1 Land Write-Down. The Land Write-Down of Nine Million Two Hundred Thousand Dollars ($9,200,000) is a separate and distinct public incentive and shall not be charged against, or counted toward, the TIF Reimbursement cap set forth in Section 6.2.

[Drafting Note — Cross-Document Conflict / Open Item: The TIF District Summary Memo (§VII) recommends that the Development Agreement “clearly specify whether the land write-down is charged against the TIF cap or constitutes a separate incentive funded from another source.” The Developer’s position is that the Land Write-Down is a separate incentive (a conveyance at a discounted price) and must not reduce the $48,000,000 TIF Reimbursement cap available to the Developer. The City should confirm that the Land Write-Down is funded from a source other than the Special Tax Allocation Fund, or, if it is treated as a TIF expenditure, that the $48,000,000 cap is increased accordingly. This is an open item.]

Section 6.2 Tax Increment Financing Reimbursement.

- Pledge. The City shall pledge up to Forty-Eight Million Dollars ($48,000,000) in tax increment revenues over the remaining life of the TIF District to reimburse the Developer for eligible redevelopment project costs incurred in connection with the Project, on a pay-as-you-go basis. The Developer shall front all eligible costs and shall be reimbursed annually from available tax increment as generated by the Project and other developments within the TIF District. The City shall not issue TIF bonds or notes for the Project.

- Eligible Costs. Eligible TIF costs shall include, without limitation: environmental remediation costs; public infrastructure improvements (on-site and off-site); parking structure construction costs (to the extent publicly accessible or committed to public use); the public plaza and community center; professional services and planning costs; and other eligible project costs under the TIF Act and the Lakemont Central TIF District Redevelopment Plan adopted by Ordinance No. 2019-42. Private residential, office, retail, and hotel construction costs are not eligible.

- Reimbursement Priority. TIF Reimbursement shall be made in the following priority order: (1) environmental remediation costs for Parcels 016 and 017; (2) the Developer’s eligible on-site infrastructure expenditures; (3) Phase IV public parking structure, public plaza, and community center costs; and (4) all other eligible costs, including professional services and financing costs.

[Drafting Note — Developer’s Position: The TIF District Summary Memo (§VI.B) recommends a reimbursement priority that places environmental remediation first (which the Developer supports, as the Developer fronts remediation costs), followed by public infrastructure. The Developer’s position is that the Developer’s own fronted eligible costs (remediation, on-site infrastructure, and the Phase IV public components) should be prioritized ahead of the City’s off-site infrastructure commitment to the extent the City’s off-site infrastructure is funded from the Special Tax Allocation Fund, so that the Developer’s risk-bearing expenditures are reimbursed first. The City’s $12,500,000 off-site infrastructure commitment should, in the Developer’s view, be funded from the City’s general or capital improvement funds rather than from TIF, so that it does not consume the $48,000,000 cap (see Section 6.3 and the open item flagged there).]

- No Guarantee; Good-Faith Extension Effort. The Parties acknowledge that TIF Reimbursement is payable solely from available tax increment actually generated and deposited in the Special Tax Allocation Fund, and is not a general obligation of the City. The City does not guarantee that the full $48,000,000 cap will be reached. A shortfall in TIF Reimbursement shall not, in itself, constitute a default by the City; provided, however, that the City covenants to use good-faith efforts to seek an extension of the TIF District (or the adoption of a successor TIF district) if, as of a benchmark date of December 31, 2038, cumulative TIF Reimbursement is tracking materially below the projections set forth in Exhibit E.

[Drafting Note — Cross-Document Conflict / Open Item: The TIF District Summary Memo (§IV.B, §IV.C, §VIII.1) projects that, under a base case without the Phase I abatement, cumulative increment reaches approximately $54.2 million by the TIF District’s December 31, 2042 expiration (exceeding the $48 million cap); but under an adjusted scenario incorporating the Phase I property tax abatement, cumulative increment may be only approximately $38 million to $42 million—potentially $6 million to $10 million short of the cap. The Developer bears the timing and shortfall risk under the pay-as-you-go structure. The Corporation Counsel’s recommendation is that a TIF shortfall not constitute a City default and that the City covenant only to use “good-faith efforts” to explore an extension. The Developer’s position, reflected above, accepts that TIF is not a guaranteed obligation but seeks (i) a City good-faith covenant to pursue a TIF extension if reimbursement is tracking below projections, (ii) the reimbursement priority in subsection (c) to protect the Developer’s most critical fronted costs, and (iii) confirmation that the Land Write-Down and the City’s off-site infrastructure are not charged against the cap. The benchmark date, the definition of “materially below projections,” and the consequences (if any) of the City’s failure to pursue an extension in good faith should be finalized.]

- Certified Cost Documentation. The Developer shall submit TIF Reimbursement requests accompanied by certified cost documentation prepared by the Developer’s auditing firm, Clearmont Accounting Group LLP, substantiating the eligible costs incurred. The City shall have the right to audit such documentation upon reasonable notice; provided that any such audit shall be conducted at the City’s expense unless it reveals a material discrepancy, and shall not unreasonably delay reimbursement of undisputed amounts.

Section 6.3 Infrastructure Cost-Sharing.

- City Off-Site Infrastructure. The City shall fund Twelve Million Five Hundred Thousand Dollars ($12,500,000) for off-site infrastructure improvements, including the widening of Lakemont Station Boulevard, installation of a new traffic signal at the Oak Street intersection, extension of the water main, and upgrade of sanitary sewer capacity. The City’s off-site infrastructure funding shall be appropriated from the City’s general fund or capital improvement funds and shall not be charged against the TIF Reimbursement cap in Section 6.2. The City shall complete the off-site improvements on a schedule coordinated with the Phase I construction timeline.

- Developer On-Site Infrastructure. The Developer shall fund Eight Million Three Hundred Thousand Dollars ($8,300,000) for on-site infrastructure improvements, including internal roadways, utilities, stormwater management, pedestrian pathways, and landscape improvements. The Developer’s on-site infrastructure expenditures are eligible for TIF Reimbursement to the extent they serve a documented public purpose, and the Developer shall substantiate the public character of each on-site infrastructure component in its reimbursement requests.

[Drafting Note — Cross-Document Conflict / Open Item: The TIF District Summary Memo (§VII) recommends that the Development Agreement specify the funding source for the City’s $12,500,000 off-site infrastructure commitment, because if it is funded from TIF it counts against the $48,000,000 cap (reducing the Developer’s reimbursement), whereas if it is funded from general revenue or capital improvement funds it does not. The Developer’s position, reflected above, is that the City’s off-site infrastructure must be funded from non-TIF sources to preserve the full $48,000,000 cap for the Developer’s eligible costs. The City should confirm the funding source. The TIF memo also notes that the Developer’s on-site infrastructure is eligible only to the extent it serves a documented public purpose; the Developer should structure and document the on-site infrastructure to maximize eligibility.]

Section 6.4 Property Tax Abatement. The City shall provide a twelve (12)-year declining property tax abatement on Phase I improvements only, measured from the pre-development base equalized assessed value, as follows: Years 1–4, seventy-five percent (75%) abatement; Years 5–8, fifty percent (50%) abatement; Years 9–12, twenty-five percent (25%) abatement; and Year 13 and thereafter, full assessment with no abatement. No property tax abatement is provided for Phase II, Phase III, or Phase IV.

[Drafting Note — Cross-Document Conflict / Open Item: The TIF District Summary Memo (§IV.B, §VIII.4) identifies an internal tension: the Phase I abatement benefits the Developer by reducing its property tax burden, but simultaneously reduces the tax increment captured by the TIF District (because the abatement reduces the assessed value of Phase I improvements), thereby reducing the TIF Reimbursement available to the Developer. The Corporation Counsel recommends that the Development Agreement either (i) structure the abatement to apply only to the non-TIF-captured portion of the tax bill (if legally permissible) to minimize the impact on TIF increment, or (ii) include an express acknowledgment that the abatement reduces TIF reimbursement capacity and that the Developer accepts this trade-off. The Developer’s interest is to preserve the full economic value of both the abatement and the TIF Reimbursement; the Developer should seek to structure the abatement to minimize its impact on TIF-capturable increment if legally permissible. This is an open item. Separately, the Term Sheet (§18.4) provides that the Parties’ respective positions on incentives for later phases “shall be addressed during negotiation of the definitive Agreement”; the Developer may seek abatement or other incentives for Phases II–IV, which remain open.]

Section 6.5 Permit Fee Waiver. The City shall waive building permit fees for Phase I and Phase II of the Project, with an estimated combined value of One Million Four Hundred Thousand Dollars ($1,400,000) (Nine Hundred Twenty Thousand Dollars ($920,000) for Phase I and Four Hundred Eighty Thousand Dollars ($480,000) for Phase II). The permit fee waiver is a separate incentive and shall not be charged against the TIF Reimbursement cap. No permit fee waiver is contemplated for Phase III or Phase IV.

[Drafting Note — Open Item: Incentives for Phases III and IV (abatement, fee waivers, or other) are not provided under the Term Sheet and remain open for negotiation. The Developer’s interest is to preserve the ability to seek additional incentives for later phases, particularly given that the Project’s public amenities (plaza, community center, public parking) are concentrated in Phase IV.]

Section 6.6 Summary of Public Incentives. The public incentives are summarized in Exhibit F and consist of: the Land Write-Down ($9,200,000); TIF Reimbursement (up to $48,000,000); City off-site infrastructure funding ($12,500,000); the Phase I property tax abatement; and the permit fee waivers ($1,400,000).

## ARTICLE VII. ENVIRONMENTAL MATTERS

Section 7.1 Phase II ESA; Reliance. The Parties acknowledge the Phase II ESA prepared by Greenfield Environmental Consultants LLC, dated November 8, 2024, which identified: (a) Parcel 015—no contamination, no further action required; (b) Parcel 016—BTEX (benzene, toluene, ethylbenzene, and xylene) contamination in soil and groundwater over approximately 1.8 acres, plus localized TCE contamination, requiring remediation under the IEPA VSRP, at an estimated cost of Two Million Eight Hundred Thousand Dollars ($2,800,000) and an estimated timeline of fourteen (14) to eighteen (18) months, culminating in an NFR Letter; and (c) Parcel 017—low-level metals contamination in shallow fill, suitable for residential use with an engineered barrier (clean fill cap) and ELUC, at an estimated cost of Three Hundred Forty Thousand Dollars ($340,000). The total estimated environmental remediation cost is Three Million One Hundred Forty Thousand Dollars ($3,140,000).

[Drafting Note — Open Item: The Phase II ESA (§9, Reliance) was prepared for the exclusive use of the Developer and its counsel, and provides that any reliance by third parties (including the City and the Construction Lender) requires execution of a reliance letter from Greenfield on terms acceptable to Greenfield. The Developer should obtain reliance letters for the City and the Construction Lender, or the Agreement should address the City’s and the Construction Lender’s access to and reliance on the Phase II ESA.]

Section 7.2 City Indemnification for Pre-Existing Environmental Conditions. The City shall indemnify, defend, and hold harmless the Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to pre-existing environmental conditions on the Property (Parcels 015, 016, and 017), including but not limited to third-party claims, governmental enforcement actions, and contribution or cost-recovery actions under federal or state environmental laws. This indemnity applies to pre-existing conditions whether known or unknown, disclosed or undisclosed, and whether arising before or after conveyance, and shall include the cost of any remediation overruns attributable to pre-existing contamination. This indemnification obligation shall survive the expiration or termination of this Agreement and the conveyance of the Property.

[Drafting Note — Developer’s Position / Open Item: The Term Sheet (§16) provides that the City indemnifies the Developer for pre-existing environmental conditions. The Phase II ESA (§4.2.4, §5.3, §8.2) confirms that the contamination is pre-existing and attributable to the former Lakemont Ironworks operations (ceased 2009), that the City acquired the parcels with knowledge of the conditions (the City’s 2018 purchase records reference a prior Phase I ESA identifying the UST farm and metal finishing operations), and that the City, as current owner, bears primary responsible-party status under the Illinois Environmental Protection Act. The ESA further warns that actual remediation costs may exceed the base estimate by 25% to 35% (total cost exposure for Parcel 016 alone could reach $3.8 to $4.2 million). The Developer’s position is that the City, as the owner that created or acquired with knowledge of the pre-existing contamination, should bear all remediation costs and all cost overruns attributable to pre-existing contamination, with such costs reimbursable through TIF or direct City funding. The Lakeshore Side Letter (§4.3(d)) requires the Investor’s consent to any environmental remediation obligation exceeding $3,140,000 without a corresponding increase in TIF Reimbursement or direct City funding sufficient to offset the excess. The scope of the City’s indemnity (including whether it is capped, the survival period, and the treatment of overruns) is a critical open item and should be confirmed with the City and the Investor.]

Section 7.3 Remediation Performance and Cost Allocation.

- Performance. The Developer shall, at the City’s cost (reimbursable through TIF Reimbursement or direct City funding), perform or contract for the remediation of Parcel 016 under the IEPA VSRP and the installation of the engineered barrier on Parcel 017, using Greenfield Environmental Consultants LLC or another qualified environmental consultant. The Developer shall be the named applicant on the VSRP enrollment and NFR Letter application, unless the Parties agree otherwise.

[Drafting Note — Cross-Document Conflict / Open Item: Resolution R-2025-017, Condition (b), requires that the Developer submit, and the IEPA approve, a RAP for Parcel 016 prior to conveyance—indicating the Developer is responsible for the RAP. The Phase II ESA (§8.2(a)) notes that the City, as current owner, bears primary responsible-party status under the Illinois Environmental Protection Act, and that the allocation of remediation performance responsibility between the City and the Developer is a matter for the transactional documents. The Developer’s position is that, while the Developer may perform the remediation work (for efficiency and schedule control), the City should bear the cost of all remediation and overruns attributable to pre-existing contamination, either through TIF Reimbursement or direct City funding. Whether the City or the Developer is the VSRP applicant, and the precise cost-allocation mechanism (including overruns), should be finalized.]

- Cost Overruns. In the event that actual remediation costs exceed the estimated Three Million One Hundred Forty Thousand Dollars ($3,140,000), the City shall be responsible for funding the excess, either through additional TIF Reimbursement (to the extent eligible and within the cap) or direct City funding, and the Developer shall not bear the cost of overruns attributable to pre-existing contamination. The Developer shall promptly notify the City of any anticipated cost overrun and shall provide supporting documentation.

- TIF Eligibility. Environmental remediation costs are eligible TIF costs and are prioritized for early reimbursement pursuant to Section 6.2(c).

Section 7.4 NFR Letter and Conveyance Condition. IEPA approval of the RAP for Parcel 016 is a condition precedent to the conveyance of Parcel 016 to the Developer, as provided in Article IX. The Parties acknowledge that an NFR Letter is required prior to residential development on Parcel 016 and for insurable title and Construction Loan financing of improvements on Parcel 016. The Developer shall use commercially reasonable efforts to obtain the NFR Letter as promptly as practicable following RAP approval.

[Drafting Note — Cross-Document Conflict / Open Item: Resolution R-2025-017, Condition (b), and the Term Sheet (§4) require IEPA approval of the RAP (not the NFR Letter) as a condition precedent to conveyance. The Construction Lender (Loan Term Sheet §7.1(7)) requires, for Parcel 016, either (a) an NFR Letter, or (b) evidence of VSRP enrollment with an approved RAP plus an environmental escrow or insurance product satisfactory to the Lender sufficient to cover estimated remediation costs of $2,800,000 plus a 25% contingency ($3,500,000 total). The Phase II ESA (§5.2, §6.1) states that the NFR Letter is a prerequisite for residential development on Parcel 016 and for insurable title and lender financing. The Developer’s position is that the conveyance condition should be RAP approval (consistent with the Resolution and Term Sheet), with the NFR Letter to be obtained thereafter, and that a phased conveyance (Section 2.1) should be available so that Phase I construction can commence on the clean portions of the Property while Parcel 016 remediation proceeds. The Construction Lender’s alternative (VSRP enrollment + approved RAP + environmental escrow/insurance of $3.5 million) should be explored to allow earlier conveyance and financing of Parcel 016. The interplay among the conveyance condition, the NFR Letter timeline, the Construction Lender’s requirements, and the Phase I groundbreaking deadline is a critical open item.]

Section 7.5 Environmental Insurance. The Developer shall obtain pollution legal liability insurance in an amount not less than Ten Million Dollars ($10,000,000), naming the City and the Construction Lender as additional insureds, with a policy term covering the full construction period and a three-year extended reporting period, as required by the Construction Lender.

Section 7.6 Vapor Intrusion. The RAP for Parcel 016 shall include a vapor intrusion evaluation, including soil gas sampling within proposed building footprint areas on or near the BTEX/TCE plume. If the evaluation indicates a health risk, vapor mitigation measures (sub-slab depressurization, vapor barriers, or passive venting) shall be incorporated into the building design for structures on or adjacent to the contaminated area on Parcel 016. The cost of such evaluation and mitigation shall be a remediation cost borne by the City pursuant to Section 7.3.

Section 7.7 Remediation Delays as Force Majeure. Delays in IEPA review or approval of the VSRP application, the RAP, or the NFR Letter application, and delays in remediation attributable to the discovery of additional pre-existing contamination or to regulatory requirements beyond the Developer’s reasonable control, shall constitute Force Majeure events under Article XIV to the extent they delay the Project schedule.

[Drafting Note — Developer’s Position / Open Item: The Phase II ESA (§5.2, §8.2(d)) recommends that the transactional documents address whether delay in NFR Letter issuance constitutes a Force Majeure event, a basis for deadline extension, or a potential default. The Term Sheet’s Force Majeure definition (§14) includes “actions or inactions of governmental authorities (other than the City)”—which would encompass IEPA delays. The Developer’s position is that IEPA/regulatory delays in RAP approval and NFR issuance, and delays from discovery of additional pre-existing contamination, should be Force Majeure events (or at minimum deadline extensions) and not Developer defaults, since the contamination is pre-existing and the regulatory process is outside the Developer’s control. The City should confirm.]

## ARTICLE VIII. AFFORDABLE HOUSING

Section 8.1 Affordable Units. The Developer shall construct one hundred six (106) Affordable Units across the Project, representing twenty percent (20%) of the five hundred thirty (530) total residential units, distributed as follows: sixty-four (64) Affordable Units in Phase I (out of 320 total units) and forty-two (42) Affordable Units in Phase III (out of 210 total units). Affordable Units shall be restricted to households earning at or below sixty percent (60%) of AMI.

Section 8.2 Integration. Affordable Units shall be distributed proportionally across unit types (studio, one-bedroom, and two-bedroom) and shall not be segregated or concentrated on particular floors or in separate wings. Affordable Units shall be comparable in design, finishes, and amenity access to market-rate units within the same building, subject to reasonable variations consistent with industry practice.

Section 8.3 Affordability Restriction. The affordability restrictions shall remain in effect for a minimum period of thirty (30) years from the date of issuance of the certificate of occupancy for the applicable phase. The restrictions shall be memorialized by a restrictive covenant recorded against the applicable parcel and running with the land, in the form attached as Exhibit G.

Section 8.4 Compliance. The Developer shall comply with the City’s Affordable Housing Compliance Program and shall provide annual income certification documentation to the City’s Community Development Department for all Affordable Units throughout the affordability restriction period.

[Drafting Note — Cross-Document Conflict: As flagged in Section 4.2, the Term Sheet (§12) refers to “at least 100 affordable units,” while the Resolution (Condition (g)), the RFP Response Narrative, and the Term Sheet’s own breakdown specify 106 Affordable Units (20% of 530). The Developer’s position is to fix the number at 106, which satisfies the 20% minimum. The “at least 100” language should be removed to avoid ambiguity. The 30-year restriction period is consistent across the Term Sheet (§12) and the RFP Response Narrative (§6.1).]

## ARTICLE IX. CONDITIONS PRECEDENT

Section 9.1 Conditions Precedent to Execution of this Agreement. The execution of this Agreement is subject to the satisfaction (or waiver by the Party entitled to the benefit) of the following conditions precedent:

- Rezoning. Completion of the rezoning of the Property from M-2 to PD-TOD, approved by the City Council and effective, with any applicable appeal period expired;

- Parcel Consolidation. Completion or authorization of the consolidation of the three parcels into a single parcel of record;

- IEPA RAP Approval. IEPA approval of the RAP for Parcel 016 under the VSRP;

- Equity Demonstration. The Developer’s demonstration of committed equity of at least Eighty-Five Million Dollars ($85,000,000), in form and substance reasonably acceptable to the City;

- City Council Approval. Approval of this Agreement by the Lakemont City Council;

- Construction Lender Confirmation. Confirmation from the Construction Lender that this Agreement is in a form acceptable to the Construction Lender as a condition of the construction loan commitment; and

- Investor Review. Review of this Agreement by Lakeshore Capital Partners Fund III LP in accordance with the Lakeshore Side Letter.

[Drafting Note — Cross-Document Conflict / Open Item: The Resolution (Condition (a)) requires the Developer to demonstrate committed equity of at least $85,000,000 within sixty (60) days of the adoption of the Resolution (i.e., on or before April 19, 2025), verified by Clearmont Accounting Group LLP. The Term Sheet (§7) requires equity demonstration within sixty (60) days of City Council approval of the definitive Agreement. These are different triggers and deadlines. The Developer’s committed equity ($51,000,000 from Lakeshore Capital Partners Fund III LP and $34,000,000 from the Pellegrini Family Trust) is in place, so the demonstration should be satisfiable under either trigger; however, the Agreement should state a single, consistent equity-demonstration deadline and form of evidence. The Developer’s interest is to align the deadline with the execution of this Agreement and to use the evidence already assembled (executed subscription/commitment letters and audited financials). The Construction Lender (Loan Term Sheet §3, §7.1(8)) separately requires evidence of the $85,000,000 equity commitment (executed subscription agreements, fund commitment letters, and bank statements) as a condition to loan closing, on an “equity in first” basis. The timing and form of equity demonstration should be reconciled across the Resolution, the Term Sheet, and the Construction Lender’s requirements.]

[Drafting Note — Open Item: The Construction Lender (Loan Term Sheet §7.1) imposes additional conditions precedent to loan closing that are not conditions to execution of this Agreement but that the Developer must satisfy before the Construction Loan funds, including: an updated MAI appraisal demonstrating compliance with loan-to-value (65% max) and loan-to-cost (75% max) requirements; an ALTA lender’s title policy; an ALTA/NSPS survey; environmental clearance (NFR Letter or VSRP enrollment + RAP + $3.5 million escrow/insurance for Parcel 016); the $15,000,000 performance bond/LC; all insurance policies; Phase I building permits; an executed GMP or stipulated-sum construction contract with a Lender-approved general contractor; an architect’s certificate; legal opinions; organizational documents; guaranties; and a subordination/intercreditor agreement if the City holds any lien or security interest. The Developer should ensure that this Agreement’s conditions precedent and the Construction Lender’s conditions are harmonized and that the Developer is not required to satisfy the Construction Lender’s closing conditions as conditions to executing this Agreement.]

Section 9.2 Conditions Precedent to Closing (Conveyance). The obligations of the Parties to close the conveyance of the Property are subject to the satisfaction (or waiver) of the conditions in Section 9.1, together with: (a) execution of this Agreement by both Parties and approval by the City Council; (b) the Developer’s posting of the Performance Security required by Article XI; and (c) delivery of the title insurance policy and survey described in Section 2.2.

Section 9.3 Conditions Precedent to Later Phases. The Developer’s obligations to commence Phase II, Phase III, and Phase IV are subject to the Developer’s satisfaction of phase-specific conditions precedent, including the availability of construction financing for the applicable phase. The Construction Lender’s facility currently contemplates funding for Phase I and Phase II only; availability for Phases III and IV is subject to a separate supplemental commitment or amendment to be negotiated at the appropriate time. The Developer’s failure to secure financing for a later phase shall not, in itself, constitute a default under this Agreement, provided that the Developer is pursuing financing in good faith and the applicable commencement deadline has not expired (as may be extended by Force Majeure).

[Drafting Note — Open Item: Approximately $58,400,000 in additional debt and/or mezzanine financing is required for Phases III and IV (Term Sheet §7; Loan Term Sheet §3; Lakeshore Side Letter §1(E), §5.3, §7(a)). This financing has not yet been secured. The Construction Lender’s facility covers Phase I and Phase II only (Loan Term Sheet §2.1). The Developer’s interest is to ensure that the Agreement does not require later-phase financing to be in place at execution and that the Developer is not in default for failing to secure later-phase financing before the applicable commencement deadline (as extended). The Lakeshore Side Letter (§7(a)) restricts the Developer from incurring Project-level indebtedness in excess of $268,400,000 ($210,000,000 + $58,400,000) without the Investor’s consent. The structure and terms of later-phase financing, and the conditions to each later phase, should be finalized.]

## ARTICLE X. CONSTRUCTION STANDARDS AND REQUIREMENTS

Section 10.1 Prevailing Wage. All construction work performed on the Project that constitutes “public works” within the meaning of the Illinois Prevailing Wage Act, 820 ILCS 130/0.01 et seq. (the “Prevailing Wage Act”), including all work paid for in whole or in part out of public funds (including TIF Reimbursement, the Land Write-Down, the property tax abatement, and permit fee waivers), shall comply with the Prevailing Wage Act. The Developer shall include prevailing wage requirements in all contracts and subcontracts for such work, shall maintain certified payroll records and make them available to the City and the Illinois Department of Labor upon request, and shall post prevailing wage rate schedules at the construction site.

[Drafting Note — Cross-Document Conflict / Open Item: The Term Sheet (§11.1) states that “all construction performed on the Project shall comply with the Illinois Prevailing Wage Act,” which the TIF District Summary Memo (§V) notes converts a potentially debatable statutory question into an unambiguous contractual obligation covering the entire Project, including purely private components (market-rate residential, office, hotel) that might otherwise be argued to fall outside the statutory mandate. The Corporation Counsel’s recommendation is that the City insist on prevailing wage coverage for “all construction” to eliminate ambiguity. The Developer’s position, reflected above, is to comply with the Prevailing Wage Act to the extent it applies by operation of statute (which, given the substantial public financial assistance, the Corporation Counsel acknowledges likely extends to all construction activity on the Project site) and to the extent contractually required for TIF-reimbursed and public components, while preserving the Developer’s ability to argue that purely private components not paid for with public funds are not statutorily subject to prevailing wage. The scope of prevailing wage coverage—statutory versus contractual “all construction”—is an open item that the Developer’s counsel should negotiate with the City. The Developer should understand that broad prevailing wage coverage may increase construction costs for purely private components.]

Section 10.2 LEED Certification. As provided in Section 4.5, all buildings shall achieve LEED Gold certification or an equivalent green building certification approved by the Director of the Community Development Department.

Section 10.3 Construction Contracts. The Developer shall enter into construction contracts with qualified general contractors and shall construct the Project in accordance with plans and specifications approved by the City under Section 4.4 and the Construction Lender’s construction consultant. The Developer shall maintain a construction budget that includes a minimum five percent (5%) hard cost contingency for each phase.

Section 10.4 Construction Monitoring. The City shall have the right, upon reasonable notice, to inspect the Project site during construction to confirm compliance with this Agreement. The Construction Lender shall employ an independent construction monitor at the Developer’s expense to verify work in place and compliance with the approved budget and schedule; the City may rely on the Construction Lender’s construction monitoring reports to the extent made available to the City.

Section 10.5 Compliance with Laws. The Developer shall comply with all applicable laws, codes, and ordinances in the construction and operation of the Project, including the Prevailing Wage Act to the extent applicable, the requirements of this Agreement, and the PD-TOD zoning ordinance.

## ARTICLE XI. PERFORMANCE SECURITY

Section 11.1 Phase I Performance Security. Prior to the conveyance of the Property to the Developer, the Developer shall post a performance bond issued by Ridgepoint Surety Corporation (or another surety company reasonably acceptable to the City and the Construction Lender) or an irrevocable standby letter of credit issued by a nationally recognized financial institution acceptable to the City and the Construction Lender, in the amount of Fifteen Million Dollars ($15,000,000) (the “Phase I Performance Security”). The Phase I Performance Security shall secure the Developer’s obligation to commence and substantially complete Phase I in accordance with this Agreement.

Section 11.2 Release. The Phase I Performance Security shall be maintained continuously from the date of conveyance until Phase I Substantial Completion, as evidenced by the issuance of a temporary or final certificate of occupancy by the City. Upon Phase I Substantial Completion, the Phase I Performance Security shall be released and returned to the Developer within thirty (30) days following written request and verification of Substantial Completion by the City.

Section 11.3 Later-Phase Performance Security. The amount, form, and conditions of performance security for Phase II, Phase III, and Phase IV shall be established by agreement of the Parties prior to the commencement of each such phase, in amounts reasonably related to the scope of the applicable phase and acceptable to the City, the Construction Lender, and the Investor.

[Drafting Note — Open Item: The Term Sheet (§8) and the Lakeshore Side Letter (§4.3(e)) provide that performance security amounts for later phases are “to be established in the Development Agreement.” The Developer’s interest is to set later-phase security at reasonable amounts tied to phase scope, to be agreed before each phase commences, and to ensure release upon Substantial Completion of each phase. The Construction Lender (Loan Term Sheet §4.1) requires an assignment of any performance bonds or letters of credit posted in connection with this Agreement, including the Phase I $15,000,000 performance bond. The form, draw mechanics, and assignment of the Performance Security should be finalized and attached as an exhibit.]

## ARTICLE XII. ASSIGNMENT, CHANGE OF CONTROL, AND LENDER PROTECTIONS

Section 12.1 Assignment by Developer. The Developer may not assign this Agreement or any interest therein, in whole or in part, without the prior written consent of the City, which consent may be withheld in the City’s reasonable discretion; provided, however, that the following transfers shall not require the City’s prior written consent (each, a “Permitted Transfer”):

- Internal Transfers. Transfers of membership interests among the existing members of the Developer (the Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, and TransitWorks Equity Group LLC);

- Estate Planning. Transfers by Marcus J. Pellegrini for estate-planning purposes to family trusts or entities controlled by Pellegrini, provided Pellegrini retains management control;

- Capital Raises. Transfers or issuances of membership interests in connection with capital raises (including the approximately $58,400,000 in additional debt, mezzanine, or equity financing anticipated for later phases) that have been approved by Lakeshore Capital Partners Fund III LP (pursuant to the Lakeshore Side Letter) and the City;

- Controlling-Interest Affiliate. Assignment to an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds a controlling interest and which expressly assumes in writing all of the Developer’s obligations under this Agreement; and

- Lender Transfers. Assignment or transfer to the Construction Lender or a Construction Lender-designee, or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, as provided in Section 12.5.

The Developer shall provide the City with written notice of any Permitted Transfer, together with a copy of the assignment and assumption agreement, within fifteen (15) days of the effective date. Any purported assignment in violation of this Section 12.1 shall be void and of no force and effect.

[Drafting Note — Cross-Document Conflict / Open Item: The Term Sheet (§10) permits assignment without City consent only to an entity in which Pellegrini (or the Pellegrini Family Trust) holds “at least a 50% controlling interest,” and provides that City consent for other assignments “may be withheld in the City’s reasonable discretion.” The Construction Lender (Loan Term Sheet §12(e)) requires that the Agreement permit assignment to a Lender-designee or foreclosure purchaser without the City’s consent (or, if consent is required, consent not unreasonably withheld and the City responding within 30 days). The Lakeshore Side Letter (§8.3) requires the Developer to negotiate assignment and change-of-control provisions that include (i) carve-outs for internal transfers among existing members, (ii) carve-outs for capital raises approved by both the Investor and the City, (iii) a “Key Person” provision as an alternative or supplement to rigid percentage thresholds, and (iv) a reasonable cure period (not less than 60 days) before any assignment default is triggered. The Developer’s position, reflected above, is to broaden the Permitted Transfers to accommodate internal transfers, estate planning, approved capital raises, and Lender transfers, and to add a Key Person provision (Section 12.3) as an alternative to rigid percentage thresholds. The City’s consent standard for non-permitted assignments (“reasonable discretion” per the Term Sheet) must be reconciled with the Construction Lender’s requirement that foreclosure transfers not be subject to City consent. This is a significant open item requiring coordination among the Developer, the City, the Construction Lender, and the Investor.]

Section 12.2 Change of Control. A “Change of Control” shall be deemed to occur upon any of the following: (a) the Pellegrini Interest falls below fifty percent (50%) of the total membership interests in the Developer; (b) Marcus J. Pellegrini ceases to serve as Manager and Chief Executive Officer of the Developer and is not replaced by a person reasonably approved by the City (and, where required, the Investor and the Construction Lender) within sixty (60) days; (c) any single person or entity (other than the Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, or TransitWorks Equity Group LLC) acquires twenty-five percent (25%) or more of the membership interests in the Developer; or (d) the Developer merges with, consolidates into, or is acquired by another entity. A Change of Control without the City’s prior written consent (and, where required, the Construction Lender’s and the Investor’s consent) shall constitute a material default under this Agreement, subject to the cure provisions in Article XIII.

[Drafting Note — Cross-Document Conflict / Open Item: The Term Sheet (§10) and the Construction Lender (Loan Term Sheet §8.1) use a 50% Pellegrini Interest threshold for change-of-control/assignment restrictions (the Construction Lender’s [50]% threshold is expressly “subject to further discussion and negotiation”). The Lakeshore Side Letter (§5.2) defines a Change of Control at a 51% Pellegrini Interest threshold, intended to provide the Investor with enhanced governance protections above the Term Sheet’s 50% threshold. The Side Letter (§5.3) acknowledges that the approximately $58,400,000 in additional financing for later phases may require equity contributions or conversion features that could dilute the Pellegrini Interest below both the 51% and 50% thresholds, and commits the parties to work together to structure the Agreement’s assignment and change-of-control provisions to accommodate internal transfers and approved capital raises. The Developer’s position is to (i) use a single, consistent threshold (the Developer prefers 50% to align with the Term Sheet and the Construction Lender, while acknowledging the Investor’s 51% governance threshold under the Side Letter operates at the entity level), (ii) add a Key Person provision (Section 12.3) as an alternative or supplement to the percentage threshold, and (iii) include broad Permitted Transfer carve-outs (Section 12.1) and a 60-day cure period (Section 13.3) so that dilution from approved capital raises does not automatically trigger a default. The reconciliation of the 50% and 51% thresholds, and the interaction with future capital raises, is a critical open item.]

Section 12.3 Key Person Provision. The Parties acknowledge that the City’s selection of the Developer was based, in substantial part, on the qualifications, experience, and financial capacity of Marcus J. Pellegrini and his affiliated entities. Accordingly, Marcus J. Pellegrini shall serve as Manager and Chief Executive Officer of the Developer and shall exercise day-to-day management authority over the Project. This Key Person provision is intended as an alternative and supplement to the percentage-of-interest thresholds in Section 12.2, such that the Developer’s compliance with this Agreement is measured by Pellegrini’s active and material involvement in the management of the Project, in addition to the ownership thresholds.

Section 12.4 Construction Lender Cure Rights. This Agreement shall provide the Construction Lender with the following protections, which the City acknowledges and agrees are necessary to enable the Construction Loan to close:

- Notice of Default. The City shall provide the Construction Lender with prompt written notice of any default by the Developer under this Agreement, concurrently with notice to the Developer.

- Cure Periods. The Construction Lender shall have the right (but not the obligation) to cure any default by the Developer under this Agreement. The Construction Lender’s cure period shall be not less than thirty (30) days beyond the Developer’s cure period for monetary defaults and not less than sixty (60) days beyond the Developer’s cure period for non-monetary defaults, with such periods extended as necessary if the Construction Lender is diligently pursuing a cure that requires additional time (including time necessary to obtain possession of the Property through foreclosure or appointment of a receiver).

- No Termination During Lender Cure. The City shall not terminate this Agreement while the Construction Lender is diligently pursuing a cure of a Developer default within the Construction Lender’s extended cure periods.

- Lender Cure Costs. The Construction Lender shall have the right to cure any default by the Developer under this Agreement on behalf of the Developer, and all cure costs (including reasonable attorneys’ fees and expenses) may be added to the outstanding Construction Loan balance.

[Drafting Note — Developer’s Position / Lender Requirement: The Construction Lender (Loan Term Sheet §12(b)) requires these cure rights as a condition to closing. The Term Sheet (§15) provides the Developer with 60-day monetary and 90-day non-monetary cure periods; the Construction Lender’s extended cure periods would therefore be 90 days (monetary) and 150 days (non-monetary) beyond the Developer’s cure periods. The Developer’s interest is to incorporate these Lender cure rights into this Agreement so that the City cannot terminate the Agreement or exercise remedies while the Construction Lender is curing, preserving the Developer’s (and the Construction Lender’s) ability to protect the Project and the Construction Loan. The City should confirm its agreement to these Lender protections.]

Section 12.5 Foreclosure and Deed-in-Lieu Transfers. This Agreement shall be freely assignable to the Construction Lender or a Construction Lender-designee, or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, without the City’s prior consent; provided, that if City consent is required for any such transfer, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within thirty (30) days of request. The assignee shall assume in writing all of the Developer’s obligations under this Agreement.

Section 12.6 Lender Consent to Amendments. No material amendment, modification, supplement, or termination of this Agreement shall be effective without the Construction Lender’s prior written consent, which shall not be unreasonably withheld, conditioned, or delayed. The Developer shall also obtain the consent of Lakeshore Capital Partners Fund III LP for any Material Amendment (as defined in the Lakeshore Side Letter) in accordance with the Side Letter.

[Drafting Note — Open Item: The Construction Lender (Loan Term Sheet §12(c)) requires Lender consent to material amendments. The Lakeshore Side Letter (§4.2) requires the Investor’s consent for any “Material Amendment” (defined in Side Letter §2 to include changes to the TIF cap, abatement schedule, phasing timelines, financial obligations, affordable housing requirements, assignment/change-of-control provisions, or clawback mechanisms). The Developer’s interest is to ensure that the Agreement’s amendment provisions accommodate both the Construction Lender’s and the Investor’s consent rights, while the City may resist third-party veto rights over a municipal agreement. The Developer covenants to obtain the Investor’s consent for Material Amendments as a matter of entity-level obligation; the Agreement should provide that material amendments require Construction Lender consent (a Lender requirement the City must accept to enable the Construction Loan). The City’s willingness to accept these third-party consent rights is an open item.]

Section 12.7 Subordination of City Interests. Any lien, encumbrance, or security interest that the City may hold or acquire in the Property (other than the Permitted Exceptions, and expressly excluding any reversionary or re-entry right, which is prohibited by Section 5.5) shall be subordinated to the Construction Lender’s first-priority mortgage pursuant to a subordination and intercreditor agreement in form and substance acceptable to the Construction Lender.

Section 12.8 Collateral Assignment. The Developer may grant to the Construction Lender a collateral assignment of this Agreement, the Developer’s rights to receive TIF Reimbursement (up to $48,000,000), all governmental permits, approvals, entitlements, and development rights associated with the Project, and a pledge of the membership interests in the Developer, in each case as security for the Construction Loan. The City acknowledges and consents to such collateral assignments and pledges.

[Drafting Note — Lender Requirement: The Construction Lender (Loan Term Sheet §4.1) requires, as collateral, a first-priority mortgage, an assignment of leases and rents, a collateral assignment of construction contracts and development agreements (including this Agreement), a collateral assignment of TIF reimbursement rights, a collateral assignment of permits and entitlements, a pledge of 100% of the membership interests in the Developer, and an assignment of the performance bond/LC. The Developer’s interest is to ensure that this Agreement expressly permits these collateral assignments to the Construction Lender, since they are conditions to the Construction Loan. The City’s consent to the collateral assignment of this Agreement and the TIF reimbursement rights should be confirmed.]

Section 12.9 Estoppel Certificates. The City shall deliver estoppel certificates to the Construction Lender upon reasonable request (not more than twice per calendar year), certifying the status of this Agreement, the existence or absence of any outstanding defaults by the Developer, and such other customary matters as the Construction Lender may reasonably request.

Section 12.10 Lender Review of this Agreement. This Agreement was delivered to the Construction Lender in draft form not less than fifteen (15) business days prior to its proposed execution date, and the Construction Lender has confirmed in writing that this Agreement is in a form acceptable to the Construction Lender.

## ARTICLE XIII. DEFAULT, CURE, AND TERMINATION

Section 13.1 Monetary Defaults. In the event of a monetary default by either Party (including the Developer’s failure to pay the Purchase Price or the City’s failure to fund its committed infrastructure obligations), the non-defaulting Party shall provide written notice specifying the nature and amount of the default. The defaulting Party shall have sixty (60) days from receipt of such notice to cure the default.

Section 13.2 Non-Monetary Defaults. In the event of a non-monetary default by either Party (including failure to commence construction within applicable deadlines, failure to comply with affordable housing requirements, or failure to maintain required insurance), the non-defaulting Party shall provide written notice specifying the nature of the default in reasonable detail. The defaulting Party shall have ninety (90) days from receipt of such notice to cure the default; provided, that if the nature of the default is such that it cannot reasonably be cured within ninety (90) days, the defaulting Party shall have such additional time as is reasonably necessary to effect a cure, so long as the defaulting Party has commenced cure efforts within the initial ninety (90)-day period and is diligently and continuously pursuing cure to completion. The Construction Lender’s extended cure periods under Section 12.4 shall apply in addition to the foregoing.

Section 13.3 Termination by City. The City shall have the right to terminate this Agreement upon: (a) a material breach by the Developer that remains uncured after the expiration of the applicable cure period (including the Construction Lender’s extended cure periods under Section 12.4); (b) the Developer’s abandonment of the Project, evidenced by cessation of all construction activity for a period of one hundred eighty (180) consecutive days (other than cessation caused by Force Majeure events); and (c) such other events of default as may be specified in this Agreement. The City’s right to terminate is expressly subject to the Construction Lender’s cure rights in Section 12.4, and the City shall not terminate this Agreement while the Construction Lender is diligently pursuing a cure.

[Drafting Note — Cross-Document Conflict (CRITICAL): The Term Sheet (§15) provides that the City may terminate if the Developer “fails to commence Phase I construction within 6 months following land conveyance.” If Closing occurs in mid-2025 (as targeted), six months from conveyance would be late 2025 or early 2026—before the Phase I groundbreaking deadline of March 1, 2026. The six-month-from-conveyance commencement trigger is therefore internally inconsistent with the March 1, 2026 groundbreaking deadline and could cause the City to have a termination right before the Developer’s actual commencement deadline has arrived. The Developer’s position, reflected above, is to remove the “six months following land conveyance” trigger and to tie the commencement obligation to the March 1, 2026 groundbreaking deadline (as extended by Force Majeure and cure periods). The City should confirm. The Construction Lender (Loan Term Sheet §12) also requires that termination of this Agreement by the City be an event of default under the Construction Loan only after the Construction Lender’s cure rights have been exhausted; the Developer’s position is reflected in Section 12.4(c).]

Section 13.4 Termination by Developer. The Developer shall have the right to terminate this Agreement upon: (a) the City’s failure to deliver clean, marketable, and insurable fee simple absolute title to the Property at Closing in accordance with Article V; (b) the City’s failure to fund its committed off-site infrastructure obligations ($12,500,000) within the timelines specified in this Agreement; (c) the City’s failure to complete the rezoning or parcel consolidation in accordance with Article III; (d) a condemnation or taking by eminent domain of more than fifteen percent (15%) of the Property by any entity, including the City; and (e) such other events of default as may be specified in this Agreement.

[Drafting Note — Developer’s Position / Open Item: The Term Sheet (§15) limits the Developer’s termination right for condemnation to a taking “by any entity other than the City.” The Developer’s position is that any condemnation or taking of more than 15% of the Property—whether by the City or any other entity—should give the Developer a termination right, since a material taking would impair the Project regardless of the condemning authority. The Construction Lender (Loan Term Sheet §6.1, default #8) treats condemnation of more than 15% of the Project site by area or value as a Loan event of default. The Developer has also added a termination right for the City’s failure to complete the rezoning or parcel consolidation, since those are City obligations under Article III. The City should confirm the expanded condemnation and rezoning termination rights.]

Section 13.5 Remedies. Upon termination of this Agreement by a non-defaulting Party, the non-defaulting Party shall have all remedies available at law or in equity, including damages, specific performance, and injunctive relief, subject in all cases to the dispute resolution provisions of Article XVI. The Developer’s Performance Security shall be the City’s sole and exclusive monetary remedy for the Developer’s failure to substantially complete Phase I, except for willful misconduct or fraud, and except as otherwise provided in Section 5.5.

[Drafting Note — Developer’s Position: The Developer’s interest is to limit the City’s monetary remedies for a Phase I completion failure to the Performance Security (and the alternative completion-assurance mechanisms in Section 5.5), consistent with the substitution of the reversionary interest with a liquidated-damages/repurchase-option mechanism. The City may seek broader remedies; the scope of remedies upon termination is an open item.]

## ARTICLE XIV. FORCE MAJEURE

Section 14.1 Definition. “Force Majeure” means any event beyond the reasonable control of the affected Party that prevents or materially delays the performance of its obligations, including, without limitation: acts of God, fire, flood, earthquake, hurricane, tornado, severe weather events, pandemic, epidemic, quarantine, governmental health orders, war, terrorism, civil unrest, insurrection, strikes or labor disputes (other than those caused by the affected Party’s labor practices or failure to comply with applicable labor laws), industry-wide supply chain disruptions beyond the affected Party’s reasonable control, governmental moratoria on construction, actions or inactions of governmental authorities (including the IEPA, but excluding the City of Lakemont), and delays in the issuance of the NFR Letter or other regulatory approvals attributable to pre-existing environmental conditions or to regulatory review beyond the Developer’s reasonable control.

Section 14.2 Effect. Force Majeure events shall extend the applicable deadlines for commencement and Substantial Completion on a day-for-day basis for the duration of the Force Majeure event.

Section 14.3 Aggregate Cap. The maximum extension of time available under this Article XIV shall not exceed eighteen (18) months in the aggregate across the Project.

[Drafting Note — Cross-Document Conflict: The Term Sheet (§14) provides an 18-month aggregate Force Majeure cap across the Project. The Construction Lender (Loan Term Sheet §6.1, default #9) provides Force Majeure extensions of “up to 180 days” (six months) for a Phase I Substantial Completion default. The Construction Lender’s 180-day cap is more restrictive than the Term Sheet’s 18-month aggregate cap: if Phase I Substantial Completion is delayed by Force Majeure for more than 180 days, the Construction Loan would be in default even though this Agreement might permit the extension. The Developer’s interest is to align the Construction Lender’s Force Majeure cap with this Agreement’s 18-month aggregate cap (or at least to ensure consistency), and to confirm that the Construction Lender will grant extensions consistent with this Agreement. This is an open item to be resolved with the Construction Lender.]

Section 14.4 Notice. The affected Party shall provide written notice to the other Party within fifteen (15) business days of the occurrence of a Force Majeure event, describing in reasonable detail the nature of the event, its anticipated duration, and its expected impact on the Project timeline, with updated notices as circumstances change.

Section 14.5 Mitigation. The affected Party shall use commercially reasonable efforts to mitigate the effects of any Force Majeure event, including pursuing alternative suppliers, adjusting construction sequencing, and engaging additional contractors as reasonably available.

Section 14.6 Exclusions. Force Majeure shall not include: financial inability to perform, changes in market conditions, increases in the cost of labor or materials (unless attributable to an industry-wide supply chain disruption), the Developer’s failure to obtain financing, or any event caused by the affected Party’s negligence or willful misconduct.

## ARTICLE XV. INDEMNIFICATION AND INSURANCE

Section 15.1 Mutual Indemnification. Each Party shall indemnify, defend, and hold harmless the other Party, and its officers, employees, agents, and representatives, from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to the indemnifying Party’s negligent acts or omissions, reckless conduct, or willful misconduct in connection with the performance of its obligations under this Agreement.

Section 15.2 Developer Indemnification of City. The Developer shall indemnify, defend, and hold harmless the City from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to construction activities on the Property, including without limitation claims for personal injury, death, property damage, and workers’ compensation, regardless of whether such claims are brought by the Developer’s employees, contractors, subcontractors, or third parties.

Section 15.3 City Indemnification of Developer. As provided in Section 7.2, the City shall indemnify, defend, and hold harmless the Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to pre-existing environmental conditions on the Property, including third-party claims, governmental enforcement actions, and contribution or cost-recovery actions under federal or state environmental laws, including the cost of remediation overruns attributable to pre-existing contamination.

Section 15.4 Survival. The indemnification obligations in this Article XV and in Section 7.2 shall survive the expiration or termination of this Agreement and the conveyance of the Property.

Section 15.5 Insurance. The Developer shall maintain, or cause its general contractor to maintain, throughout the construction period for each phase, the following minimum insurance coverages:

- Commercial General Liability (CGL): Ten Million Dollars ($10,000,000) per occurrence and Twenty-Five Million Dollars ($25,000,000) in the aggregate, including coverage for premises/operations, products/completed operations, contractual liability, and broad-form property damage;

- Umbrella/Excess Liability: Twenty-Five Million Dollars ($25,000,000) per occurrence and in the aggregate, in excess of the CGL policy;

- Builder’s Risk: Full replacement value of each phase under construction (Phase I: $105,000,000; Phase II: $76,000,000; and subsequent phases at their respective hard construction costs), written on an all-risk basis including coverage for fire, windstorm, vandalism, theft, flood, and earthquake (with sub-limits as appropriate);

- Workers’ Compensation: Statutory limits as required by Illinois law;

- Automobile Liability: Five Million Dollars ($5,000,000) combined single limit;

- Professional Liability: Five Million Dollars ($5,000,000) per claim and in the aggregate; and

- Pollution Legal Liability: Ten Million Dollars ($10,000,000), as provided in Section 7.5.

The City of Lakemont shall be named as an additional insured on the CGL and umbrella/excess liability policies, and the Construction Lender shall be named as an additional insured and loss payee as required by the Construction Loan Documents. All policies shall be issued by carriers rated A- VII or better by A.M. Best. Certificates of insurance shall be provided to the City prior to conveyance and updated annually and upon renewal. All policies shall provide for at least thirty (30) days’ prior written notice to the City and the Construction Lender of cancellation, non-renewal, or material modification.

[Drafting Note — Cross-Document Conflict: The Term Sheet (§11.3) requires CGL coverage of $10,000,000 per occurrence and $20,000,000 in the aggregate, and does not require Professional Liability or Pollution Legal Liability. The Construction Lender (Loan Term Sheet §5) requires CGL of $10,000,000 per occurrence and $25,000,000 in the aggregate, Professional Liability of $5,000,000, and Pollution Legal Liability of $10,000,000, with carriers rated A- VII or better and the Lender as additional insured/loss payee. The Developer’s position, reflected above, is to adopt the Construction Lender’s more comprehensive requirements (CGL aggregate of $25,000,000, plus Professional Liability and Pollution Legal Liability) so that a single insurance program satisfies both the City’s and the Construction Lender’s requirements. The City should confirm its acceptance of the higher CGL aggregate and the additional coverages.]

## ARTICLE XVI. DISPUTE RESOLUTION

Section 16.1 Negotiation. The Parties shall first attempt to resolve any dispute arising under or related to this Agreement through good-faith negotiation between the City Manager (or designee) and the Developer’s CEO (or designee) for a period of thirty (30) days following written notice of the dispute by either Party.

Section 16.2 Mediation. If the dispute is not resolved through negotiation within the thirty (30)-day period, the dispute shall be submitted to non-binding mediation before the Lakemont Mediation Center, or such other neutral mediator as the Parties may agree upon. The costs of mediation, including mediator fees, shall be shared equally by the Parties, and each Party shall bear its own attorneys’ fees.

Section 16.3 Binding Arbitration. If the dispute is not resolved through mediation within sixty (60) days following submission to the mediator, the dispute shall be submitted to final and binding arbitration administered under the Commercial Arbitration Rules of the American Arbitration Association, conducted by a single arbitrator with experience in real estate development matters.

Section 16.4 Venue and Governing Law. All mediation and arbitration proceedings shall be conducted in Cook County or Lake County, Illinois. This Agreement shall be governed by and construed in accordance with the laws of the State of Illinois, without regard to conflict-of-law principles.

Section 16.5 Provisional Remedies. Nothing in this Article XVI shall prevent either Party from seeking temporary restraining orders, preliminary injunctions, or other provisional judicial relief where necessary to prevent irreparable harm, pending resolution of the dispute through the procedures set forth above.

## ARTICLE XVII. REPRESENTATIONS AND WARRANTIES

Section 17.1 Mutual Representations. Each Party represents and warrants that: (a) it has full power and authority to enter into this Agreement and to perform its obligations hereunder; (b) the execution and delivery of this Agreement has been duly authorized by all necessary action; and (c) this Agreement constitutes its legal, valid, and binding obligation, enforceable in accordance with its terms.

Section 17.2 Developer Representations. The Developer represents and warrants that: (a) it has the financial capacity, development experience, and organizational resources necessary to complete the Project in accordance with the terms of this Agreement; (b) it has committed equity of at least $85,000,000 available for the Project; and (c) it has obtained a preliminary construction loan commitment from the Construction Lender.

Section 17.3 City Representations. The City represents and warrants that: (a) it has good and marketable fee simple absolute title to the Property, free and clear of all liens, encumbrances, and adverse claims (except the Permitted Exceptions), and has the legal authority to convey the Property to the Developer; (b) the Property is located within the TIF District and TIF funds are legally available for the purposes described in this Agreement, subject to annual appropriation and the availability of increment; (c) the rezoning and parcel consolidation are within the City’s authority to accomplish; and (d) the City has disclosed to the Developer all known environmental conditions on the Property, as reflected in the Phase II ESA and the City’s records.

[Drafting Note — Developer’s Position: The Developer’s interest is to obtain robust City representations regarding title, TIF availability, the City’s authority to accomplish the rezoning and consolidation, and disclosure of environmental conditions. The Term Sheet (§18.1) provides for customary representations, including the City’s representation that it has good and marketable title and that TIF funds are legally available. The Developer should seek an express City representation regarding disclosure of known environmental conditions, given the pre-existing contamination and the City’s knowledge of those conditions at the time of acquisition (Phase II ESA §4.2.4).]

## ARTICLE XVIII. MISCELLANEOUS

Section 18.1 Notices. All notices, demands, requests, consents, approvals, and other communications required or permitted under this Agreement shall be in writing and shall be deemed delivered upon personal delivery, upon the date of delivery by nationally recognized overnight courier, or three (3) business days following deposit in the United States mail, registered or certified, return receipt requested, postage prepaid, addressed as follows:

If to the Developer: Granite City Development LLC 900 West Monroe Street, Suite 2200 Chicago, IL 60607 Attn: Marcus J. Pellegrini, Manager and CEO With a copy to: Thornfield & Pratt LLP 311 South Wacker Drive, Suite 5400 Chicago, IL 60606 Attn: Catherine M. Albrecht

If to the City: City of Lakemont Office of the City Manager 200 Civic Center Drive Lakemont, IL 60048 Attn: Gerald T. Fong, City Manager With a copy to: Office of Corporation Counsel, City of Lakemont 200 Civic Center Drive Lakemont, IL 60048 Attn: Rebecca A. Sinclair, Esq. And to: Ashford, Keene & Mulvaney LLP 150 North Michigan Avenue, Suite 3200 Chicago, IL 60601 Attn: Jonathan Ashford

Either Party may change its notice address by providing written notice to the other Party in accordance with this Section 18.1.

Section 18.2 Entire Agreement. This Agreement, together with the Exhibits hereto, constitutes the entire agreement between the Parties with respect to the subject matter hereof and supersedes the Negotiated Term Sheet and all prior negotiations, representations, and understandings, whether written or oral. In the event of any conflict between this Agreement and the Negotiated Term Sheet, this Agreement shall control.

[Drafting Note — Open Item: The Lakeshore Side Letter (§10.5) provides that, in the event of any conflict between the Side Letter and the Operating Agreement with respect to Project-related matters, the Side Letter controls. The Side Letter is an agreement between the Developer and the Investor (Lakeshore Capital Partners Fund III LP) and is not a Party to this Agreement. The Developer should ensure that this Agreement is consistent with the Developer’s obligations under the Side Letter (including the Minimum IRR commitment, consent rights, anti-dilution protections, and the restrictions on agreeing to clawback/reversionary mechanisms without Investor consent), since the Developer has covenanted in the Side Letter not to agree to terms in this Agreement that would materially and adversely affect the Investor’s ability to achieve the Minimum IRR (Side Letter §3.5) or to agree to clawback mechanisms without Investor consent (Side Letter §7(d)). The Developer’s counsel should confirm consistency between this Agreement and the Side Letter.]

Section 18.3 Amendments. This Agreement may be amended, modified, or supplemented only by a written instrument executed by both Parties, subject to the Construction Lender’s and the Investor’s consent rights as provided in Section 12.6.

Section 18.4 Severability. If any provision of this Agreement is held to be invalid or unenforceable, the remaining provisions shall remain in full force and effect, and the Parties shall negotiate in good faith a substitute provision that most nearly reflects the Parties’ original intent.

Section 18.5 No Waiver. No waiver of any provision of this Agreement shall be effective unless in writing and signed by the Party against whom the waiver is asserted. No failure or delay in exercising any right shall operate as a waiver.

Section 18.6 Assignment. This Agreement shall be binding upon and inure to the benefit of the Parties and their respective successors and permitted assigns, subject to Article XII.

Section 18.7 Counterparts. This Agreement may be executed in any number of counterparts, each of which shall be deemed an original and all of which together shall constitute one and the same instrument. Signatures transmitted by electronic means shall be deemed original signatures.

Section 18.8 Costs. Each Party shall bear its own costs and expenses incurred in connection with the negotiation and preparation of this Agreement, including legal fees, consultant fees, and other professional expenses.

Section 18.9 Confidentiality. The terms and contents of this Agreement are confidential and shall not be disclosed by either Party to any third party, except: (a) to each Party’s legal counsel, financial advisors, accountants, lenders, and equity investors, as reasonably necessary; (b) as required by applicable law or governmental regulation, including the Illinois Freedom of Information Act (5 ILCS 140/) as applicable to the City; and (c) to the extent necessary for City Council proceedings and other governmental approvals related to the Project.

Section 18.10 Further Assurances. Each Party shall execute and deliver such further documents and instruments and take such further actions as may be reasonably necessary to carry out the purposes of this Agreement.

## SIGNATURE PAGE

IN WITNESS WHEREOF, the Parties have executed this Development Agreement as of the date first written above.

GRANITE CITY DEVELOPMENT LLC

By: _______________________ Name: Marcus J. Pellegrini Title: Manager and Chief Executive Officer Date: [•], 2025

CITY OF LAKEMONT, ILLINOIS

By: _______________________ Name: Gerald T. Fong Title: City Manager Date: [•], 2025

Approved as to form:

Rebecca A. Sinclair, Esq. Corporation Counsel, City of Lakemont

## EXHIBITS

The following exhibits are attached to and incorporated into this Agreement. Several exhibits are identified as “[to be prepared]” pending negotiation of the open items flagged throughout this Agreement.

Exhibit A — Legal Description of the Property (to be prepared; per-parcel legal descriptions to be confirmed by survey, with consolidation plat referencing the ELUC area on Parcel 017)

[Drafting Note — Open Item: The legal descriptions should be confirmed by an ALTA/NSPS survey, and the consolidation plat should expressly reference the institutional control (ELUC) area on Parcel 017 by legal description, as recommended by the Phase II ESA (§4.3.3). The per-parcel acreage discrepancy between the Phase II ESA and the RFP Response Narrative (see Recital A drafting note) should be resolved by survey.]

Exhibit B — Permitted Exceptions (to be prepared; subject to Construction Lender approval)

Exhibit C — Project Budget (to be prepared; total Project cost approximately $412,000,000, with hard construction costs of $340,000,000 across four phases, land acquisition $9,200,000, environmental remediation $3,140,000, on-site infrastructure $8,300,000, and soft costs/financing/contingency approximately $51,360,000)

Exhibit D — Liquidated Damages Amount and Repurchase Option Mechanics (to be prepared; pending negotiation of the alternative completion-assurance mechanism in lieu of the reversionary interest, as flagged in Section 5.5)

Exhibit E — TIF Increment Projections (to be prepared; reflecting the base-case and abatement-adjusted projections from the TIF District Summary Memo, including the benchmark date and “materially below projections” standard for the City’s good-faith extension effort under Section 6.2(d))

Exhibit F — Summary of Public Incentives (to be prepared)

Exhibit G — Form of Affordable Housing Restrictive Covenant (to be prepared; 30-year restriction running with the land)

Exhibit H — Form of Performance Security / Letter of Credit (to be prepared; subject to Construction Lender assignment requirements)

Exhibit I — Form of Subordination and Intercreditor Agreement (to be prepared; subordinating any City security interest to the Construction Lender’s mortgage)

Exhibit J — Form of Access Agreement / Deed Restrictions for Public Parking (to be prepared; to establish TIF eligibility of Phase I and Phase II parking structures)

Exhibit K — Environmental Remediation Plan Summary and Cost Allocation (to be prepared; incorporating the Phase II ESA recommendations, the cost-overrun allocation in Section 7.3, and the vapor intrusion evaluation in Section 7.6)

*[Drafting Note — Consolidated Summary of Cross-Document Conflicts and Open Items: The following is a consolidated index of the principal conflicts and open items flagged throughout this draft, for ease of reference in negotiation:

- Reversionary interest vs. Lender prohibition vs. Investor consent (Section 5.5) — CRITICAL.

- 36-month reversion clock vs. September 30, 2028 Substantial Completion deadline (Section 5.5).

- “Six months following land conveyance” commencement trigger vs. March 1, 2026 groundbreaking (Section 13.3).

- Force Majeure aggregate cap: 18 months (Term Sheet) vs. 180 days (Construction Lender) (Section 14.3).

- Change-of-control threshold: 50% (Term Sheet/Construction Lender) vs. 51% (Lakeshore Side Letter); future capital-raise dilution (Section 12.2).

- NFR Letter vs. RAP approval as conveyance condition; phased conveyance feasibility (Sections 2.1, 7.4, 9.1).

- Environmental remediation cost-overrun allocation; City indemnity scope (Sections 7.2, 7.3).

- Remediation performance responsibility and VSRP applicant (Section 7.3).

- Remediation timeline (14–18 months) vs. March 1, 2026 groundbreaking (Sections 2.1, 7.4).

- Parcel 016 acquisition history: tax forfeiture 2016 vs. direct purchase 2018 (Recital A).

- TIF shortfall risk; pay-as-you-go; City good-faith extension effort (Section 6.2(d)).

- Land write-down charged against TIF cap? (Section 6.1).

- City off-site infrastructure funding source (TIF vs. general funds) (Section 6.3).

- Abatement–TIF interaction (Section 6.4).

- Abatement and permit fee waivers limited to Phases I–II; later-phase incentives open (Sections 6.4, 6.5).

- Local hiring: 35% mandate (Resolution) vs. goal/good-faith (Term Sheet) (Article X, Section 10.1).

- Living wage $17.50/hour for retail/hotel employees (Resolution) not in Term Sheet (Article X).

- First-source hiring (Resolution) not in Term Sheet (Article X).

- Affordable unit count: “at least 100” (Term Sheet) vs. 106 (Resolution/RFP) (Sections 4.2, 8.1).

- City consent standard for assignment vs. Construction Lender foreclosure transfer right (Sections 12.1, 12.5).

- Construction Lender cure rights integration (Section 12.4).

- Construction Lender and Investor consent to amendments (Section 12.6).

- Subordination of City interests to Construction Lender mortgage (Section 12.7).

- Collateral assignment of Agreement, TIF rights, permits, and membership interests (Section 12.8).

- Estoppel certificates from City (Section 12.9).

- Construction Lender and Investor review of this Agreement before execution (Sections 9.1, 12.10).

- Insurance: CGL aggregate $20M (Term Sheet) vs. $25M (Construction Lender); Professional Liability and Pollution Legal Liability (Section 15.5).

- Prevailing wage scope: “all construction” (Term Sheet) vs. statutory/TIF-reimbursed only (Section 10.1).

- Equity demonstration timing: 60 days from Resolution adoption vs. 60 days from City Council approval of definitive Agreement (Section 9.1).

- Parcel acreage discrepancy: Phase II ESA vs. RFP Response Narrative (Recital A).

- RFP number: 2024-CD-07 (RFP Response) vs. 2024-CD-018 (Term Sheet) (Recital B).

- Hotel brand and architect/general contractor not yet selected (open).

- Later-phase financing ($58,400,000) not secured; Construction Loan covers Phases I–II only (Section 9.3).

- Performance security amounts for Phases II–IV not set (Section 11.3).

- Condemnation >15%: Term Sheet limits Developer termination to “entity other than City” (Section 13.4).

- Community center conveyance terms, TIF eligibility, and parking TIF eligibility (Sections 4.6, 4.7).

- Consistency with the Lakeshore Side Letter (Minimum IRR, consent rights, anti-dilution, clawback consent) (Section 18.2).]*

[Drafting Note — General: This draft is prepared from the perspective of the Developer (Granite City Development LLC) and reflects the Developer’s preferred positions on the principal open items, consistent with the Developer’s obligations to the Construction Lender (First Prairie National Bank) and the Investor (Lakeshore Capital Partners Fund III LP) under the Construction Loan Term Sheet and the Lakeshore Side Letter, respectively. Numerous provisions flagged as open items or cross-document conflicts will require negotiation with the City and confirmation with the Construction Lender and the Investor before this Agreement is finalized and executed. The bracketed drafting notes are intended to identify, for the benefit of the Developer’s counsel and principals, the specific points of conflict among the source documents and the matters that remain to be resolved.]

END OF DRAFT