# DEVELOPMENT AGREEMENT

# LAKEMONT STATION COMMONS MIXED-USE TRANSIT-ORIENTED DEVELOPMENT

[DRAFT — PREPARED ON BEHALF OF GRANITE CITY DEVELOPMENT LLC — FOR NEGOTIATION]

[Drafting Note — Purpose and Scope of Draft: This Development Agreement (this “Agreement”) is drafted on behalf of Granite City Development LLC (“Developer”) and reflects the Developer’s negotiating positions. Bracketed provisions and bracketed drafting notes throughout flag (i) cross-document conflicts among the source materials (the City Council Resolution R-2025-017, the Negotiated Term Sheet dated January 22, 2025, the Construction Loan Term Sheet from First Prairie National Bank, the Lakeshore Capital Partners Fund III LP Side Letter dated February 10, 2025, the Phase II Environmental Site Assessment by Greenfield Environmental Consultants LLC dated November 8, 2024, the TIF District Summary Memorandum from Corporation Counsel dated March 5, 2025, and the Developer’s RFP Response Narrative dated December 16, 2024) and (ii) open items requiring resolution before execution. Bracketed notes are not operative contract text and are intended to guide negotiation. Defined terms are capitalized.]

This DEVELOPMENT AGREEMENT (this “Agreement”) is made and entered into as of [●], 2025 (the “Effective Date”), by and between GRANITE CITY DEVELOPMENT LLC, an Illinois limited liability company (“Developer”), and the CITY OF LAKEMONT, ILLINOIS, an Illinois home rule municipality (“City”). Developer and City are referred to herein each as a “Party” and collectively as the “Parties.”

## RECITALS

A. The City is the owner of certain real property commonly known as 1400–1550 Lakemont Station Boulevard, Lakemont, Illinois 60048, consisting of three (3) parcels of record identified by Parcel Identification Numbers 12-24-300-015, 12-24-300-016, and 12-24-300-017, totaling approximately 12.7 acres (553,212 square feet) (collectively, the “Property”).

[Drafting Note — Conflict on Parcel Acquisition History: The City Council Resolution R-2025-017, the Negotiated Term Sheet, the TIF District Summary Memorandum, and the Developer’s RFP Response Narrative each state that the City acquired Parcels 12-24-300-015 and 12-24-300-016 through tax forfeiture proceedings in 2016 and acquired Parcel 12-24-300-017 by direct purchase in 2018. The Phase II Environmental Site Assessment (Greenfield Environmental Consultants LLC, dated November 8, 2024) states, to the contrary, that Parcel 12-24-300-016 was acquired by the City through direct purchase in 2018 (together with Parcel 017), and that only Parcel 015 was acquired through tax forfeiture in 2016. This discrepancy affects the chain of title and the title encumbrances that may burden each parcel (tax-forfeiture parcels may carry different title characteristics than direct-purchase parcels). The City’s title representations in Article 15 and the Permitted Exceptions schedule must be reconciled to the actual recorded chain of title for each parcel. OPEN ITEM — confirm acquisition mechanism for each parcel against recorded deeds and the City’s 2018 purchase records referenced in the Phase II ESA.]

[Drafting Note — Conflict on Individual Parcel Acreages: The Developer’s RFP Response Narrative (Section 3.1) states the parcel sizes as approximately 3.8 acres (015), 4.1 acres (016), and 4.8 acres (017). The Phase II ESA states approximately 4.2 acres (015), 4.1 acres (016), and 4.4 acres (017). The total of 12.7 acres (553,212 square feet) is consistent across all documents. The individual parcel sizes should be confirmed by the ALTA/NSPS survey required as a condition precedent and stated by legal description rather than approximate acreage. OPEN ITEM.]

B. The Property constitutes the former site of the Lakemont Ironworks manufacturing campus, which ceased industrial operations in 2009 and has remained substantially vacant and underutilized. The Property is situated immediately adjacent to the Lakemont Central Metra commuter rail station, providing direct access to commuter rail service on the Metra Milwaukee District/North Line.

C. The Property is currently zoned M-2 (General Manufacturing) under the City of Lakemont Zoning Ordinance, as amended. The proposed mixed-use transit-oriented development requires rezoning of the Property from M-2 to PD-TOD (Planned Development — Transit Oriented District).

D. The City, through its Community Development Department, conducted a competitive Request for Proposals process (RFP No. 2024-CD-018 [Drafting Note — RFP Number Conflict: The Negotiated Term Sheet references “RFP No. 2024-CD-018,” while the Developer’s RFP Response Narrative references “RFP No. 2024-CD-07.” Confirm the correct RFP number.]) for the redevelopment of the Property. Developer was selected as the preferred developer based upon its qualifications, experience, project proposal, and demonstrated financial capacity.

E. On January 22, 2025, the City Manager, Gerald T. Fong, acting on behalf of the City, and Developer, by its Manager, Marcus J. Pellegrini, executed a non-binding Negotiated Term Sheet setting forth the principal economic and legal terms proposed to govern this Agreement (the “Term Sheet”).

F. On February 18, 2025, the City Council of the City of Lakemont adopted Resolution No. R-2025-017 (the “Resolution”), by a vote of 7–2, granting conditional approval for the Project and authorizing the City Manager to negotiate and execute this Agreement, subject to the conditions set forth in Section 3 of the Resolution.

[Drafting Note — Political Risk / Non-Unanimous Vote: The Resolution was adopted by a 7–2 vote, not unanimously. Developer should consider whether the Agreement should include a City representation that the Resolution remains in full force and effect and has not been repealed or modified, and whether any conditions of the Resolution that are not expressly incorporated into this Agreement are deemed satisfied or waived upon execution. OPEN ITEM.]

G. Developer proposes a four-phase mixed-use transit-oriented development to be known as “Lakemont Station Commons” (the “Project”), with a total gross building area of approximately 1,620,000 square feet and a total estimated Project cost of approximately Four Hundred Twelve Million Dollars ($412,000,000).

H. The Property is located within the Lakemont Central Tax Increment Financing District, established pursuant to Ordinance No. 2019-42, which expires on December 31, 2042.

I. Developer has obtained a preliminary (non-binding) commitment letter from First Prairie National Bank for a construction loan facility in an amount of up to Two Hundred Ten Million Dollars ($210,000,000) (the “Construction Loan”), subject to the execution of this Agreement in form and substance acceptable to such lender.

[Drafting Note — Financing Commitment Risk: Both the Term Sheet and the Construction Loan Term Sheet are expressly non-binding. The Construction Loan Term Sheet expires unless accepted by a date to be inserted (May [●], 2025) and is subject to credit committee approval and due diligence. The Agreement should condition Developer’s obligations on the closing of the Construction Loan (or substitute financing) and should not require groundbreaking until financing is in place. See Article 6 and Article 17. OPEN ITEM.]

NOW, THEREFORE, in consideration of the mutual covenants and agreements set forth herein, and for other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the Parties agree as follows:

## ARTICLE 1. DEFINITIONS

Section 1.1 Defined Terms. As used in this Agreement, the following capitalized terms shall have the meanings set forth below. Additional defined terms are defined elsewhere in this Agreement.

“Affordable Unit” means a residential dwelling unit restricted to occupancy by households earning at or below sixty percent (60%) of Area Median Income, as more particularly described in Article 9.

“Affordable Housing Covenant” means the restrictive covenant recorded against the applicable parcel pursuant to Section 9.4, running with the land and restricting the Affordable Units for the Affordability Restriction Period.

“Agreement” means this Development Agreement, including all Recitals, Articles, Sections, Exhibits, and Schedules, as the same may be amended in accordance with Section 20.6.

“AMI” means Area Median Income as published annually by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area, or any successor designation.

“Appraised Value” means the as-is fair market value of the Property of Eighteen Million Four Hundred Thousand Dollars ($18,400,000) as established in the appraisal report dated January 15, 2025, prepared by Crossland Appraisal Services.

“City” means the City of Lakemont, Illinois.

“Closing” means the closing of the conveyance of the Property from City to Developer pursuant to Article 3.

“Construction Lender” means First Prairie National Bank, or any successor construction lender approved by City pursuant to Section 6.4.

“Construction Loan Documents” means the definitive loan agreements, mortgage, security instruments, guaranties, and other documents evidencing and securing the Construction Loan.

“ELUC” means an environmental land use control, in the form of a restrictive covenant, recorded against the Property in connection with the IEPA Voluntary Site Remediation Program, as described in the Phase II ESA.

“Force Majeure” has the meaning set forth in Section 11.3.

“IEPA” means the Illinois Environmental Protection Agency.

“NFR Letter” means a No Further Remediation letter issued by IEPA under the Voluntary Site Remediation Program.

“Permitted Exceptions” means the title exceptions permitted under Section 3.3 and set forth on Schedule 3.3.

“Phase” or “Phases” means each of Phase I, Phase II, Phase III, and Phase IV of the Project, as described in Article 2.

“Phase I Substantial Completion” means Substantial Completion of Phase I.

“Project” means the Lakemont Station Commons mixed-use transit-oriented development described in Article 2.

“Property” means the real property described in Recital A and in the legal description attached as Schedule 3.1.

“Purchase Price” means Nine Million Two Hundred Thousand Dollars ($9,200,000).

“RAP” means a Remedial Action Plan for the environmental remediation of Parcel 12-24-300-016, submitted to and approved by IEPA under the Voluntary Site Remediation Program.

“Substantial Completion” has the meaning set forth in Section 11.2.

“TIF Act” means the Illinois Tax Increment Allocation Redevelopment Act, 65 ILCS 5/11-74.4-1 et seq., as amended.

“TIF District” means the Lakemont Central Tax Increment Financing District established by City Ordinance No. 2019-42, expiring December 31, 2042.

“TIF Reimbursement” means the reimbursement to Developer of eligible redevelopment project costs from tax increment revenues generated within the TIF District, as provided in Article 4.

“VSRP” means the IEPA Voluntary Site Remediation Program.”

## ARTICLE 2. THE PROJECT AND DEVELOPMENT PLAN

Section 2.1 The Project. Developer shall design, entitle, construct, and deliver the Project, a mixed-use transit-oriented development known as “Lakemont Station Commons,” consisting of approximately 1,620,000 gross square feet of building area across four (4) phases, with a total estimated hard construction cost of approximately Three Hundred Forty Million Dollars ($340,000,000) and a total estimated Project cost of approximately Four Hundred Twelve Million Dollars ($412,000,000). The Project shall include, in the aggregate: five hundred thirty (530) residential dwelling units; sixty-three thousand (63,000) square feet of retail space; two hundred eighty thousand (280,000) square feet of Class A office space; one hundred fifty (150) hotel rooms; one thousand four hundred thirty (1,430) structured parking spaces; a 2.5-acre public plaza; and a 28,000-square-foot community center.

Section 2.2 Phase I — Residential Tower A and Retail Podium. Phase I shall consist of: (a) three hundred twenty (320) residential dwelling units, comprising two hundred fifty-six (256) market-rate units and sixty-four (64) Affordable Units; (b) forty-five thousand (45,000) square feet of ground-floor retail space; and (c) a four hundred eighty (480)-space structured parking facility. Phase I shall comprise approximately four hundred twenty thousand (420,000) square feet of gross building area, with an estimated hard construction cost of One Hundred Five Million Dollars ($105,000,000).

Section 2.3 Phase II — Office Building and Retail. Phase II shall consist of: (a) two hundred eighty thousand (280,000) square feet of Class A office space; (b) eighteen thousand (18,000) square feet of retail space; and (c) a three hundred fifty (350)-space structured parking facility. Phase II shall comprise approximately three hundred eighty thousand (380,000) square feet of gross building area, with an estimated hard construction cost of Seventy-Six Million Dollars ($76,000,000).

Section 2.4 Phase III — Residential Tower B and Hotel. Phase III shall consist of: (a) two hundred ten (210) residential dwelling units, comprising one hundred sixty-eight (168) market-rate units and forty-two (42) Affordable Units; and (b) a one hundred fifty (150)-room select-service hotel. Phase III shall comprise approximately four hundred forty thousand (440,000) square feet of gross building area, with an estimated hard construction cost of Eighty-Eight Million Dollars ($88,000,000).

[Drafting Note — Open Item — Hotel Brand: The hotel brand/flag is “to be determined,” with Developer in discussions with two national hospitality flags (Term Sheet §3.3). The Agreement should permit Developer to select the hotel operator/brand in its reasonable discretion, subject to compliance with the PD-TOD zoning and the living wage requirements of Article 10. OPEN ITEM.]

Section 2.5 Phase IV — Public Plaza, Community Center, and Parking Structure. Phase IV shall consist of: (a) a 2.5-acre public plaza incorporating landscaping and public art installations; (b) a twenty-eight thousand (28,000) square foot community center facility (to be conveyed to the City upon completion as provided in Section 2.6); and (c) a six hundred (600)-space public parking structure. Phase IV shall comprise approximately three hundred eighty thousand (380,000) square feet of gross building area, with an estimated hard construction cost of Seventy-One Million Dollars ($71,000,000).

Section 2.6 Community Center Conveyance. Upon Substantial Completion of Phase IV, Developer shall convey the community center facility to the City in fee simple, by special warranty deed, at no additional cost to the City.

[Drafting Note — Open Item — Community Center Specifications: The Developer’s RFP Response Narrative states the community center will be conveyed “fully furnished and equipped per the agreed-upon specifications,” while the Term Sheet states it will be conveyed “at no additional cost.” The scope of finish, furnishings, equipment, programming, design consultation with the City’s Parks and Recreation Department, and the timing of design-specification agreement must be defined in a Schedule. Developer’s position: conveyance should be of the building shell and core plus agreed FF&E, with the specification schedule agreed before Phase IV construction commences, and the conveyance cost (including transfer costs) borne by Developer but the City responsible for its own operational fit-out beyond the agreed specifications. OPEN ITEM.]

Section 2.7 Development Plan. The detailed site plan, phasing plan, building program, design standards, and Project budget are set forth in the exhibits and schedules to this Agreement, including the Site Plan (Schedule 2.7-1), the Phasing Plan (Schedule 2.7-2), and the Project Budget (Schedule 2.7-3).

[Drafting Note — Open Item — Architect and General Contractor: The Developer’s RFP Response Narrative states that the architect and general contractor selections are “to be finalized and submitted to the City upon selection of the Developer as the preferred development partner.” The Construction Loan Term Sheet requires an executed GMP or stipulated-sum contract with a Lender-approved general contractor and a Lender-approved construction budget as conditions precedent to closing. The Agreement should permit Developer to select the architect and general contractor in its reasonable discretion, subject to City and Construction Lender approval (not to be unreasonably withheld), and should not require City pre-approval of subcontracts. OPEN ITEM.]

Section 2.8 Design Review. Developer shall submit design drawings for each Phase to the City’s Community Development Department for review. The City shall approve or provide written comments within thirty (30) business days of submission. The City’s approval shall not be unreasonably withheld, conditioned, or delayed, and shall be deemed given if the City does not respond within such thirty (30) business day period. The City’s review shall be limited to consistency with the PD-TOD zoning standards, this Agreement, and applicable codes.

[Drafting Note — Developer Position: A deemed-approval mechanism and a limited scope of City review protect Developer against design-review delay being used as a basis for default or delay claims. The Term Sheet (§19) contemplates “design review and approval procedures” in the definitive Agreement but does not specify timelines. OPEN ITEM — confirm City acceptance of deemed-approval and 30-business-day timeline.] ## ARTICLE 3. THE PROPERTY; LAND CONVEYANCE

Section 3.1 Conveyance. Following the execution of this Agreement and the satisfaction or waiver of all conditions precedent to Closing set forth in Article 17, the City shall convey the Property (as consolidated into a single parcel) to Developer by special warranty deed, free and clear of all liens, encumbrances, and exceptions, except for the Permitted Exceptions.

Section 3.2 Purchase Price; Payment. The Purchase Price for the Property shall be Nine Million Two Hundred Thousand Dollars ($9,200,000), representing fifty percent (50%) of the Appraised Value, consistent with the City’s economic development incentive policy for transit-oriented development. The Purchase Price shall be due and payable at Closing. Developer may fund the Purchase Price from equity, Construction Loan proceeds, or a combination thereof. The difference between the Appraised Value and the Purchase Price (Nine Million Two Hundred Thousand Dollars ($9,200,000)) constitutes a land write-down incentive (the “Land Write-Down”).

Section 3.3 Title; Permitted Exceptions. The City shall deliver marketable and insurable fee simple absolute title to the Property. The City shall provide, at the City’s expense, an owner’s policy of title insurance in the amount of the Purchase Price issued by a nationally recognized title insurance company. The Permitted Exceptions shall be limited to: (a) real estate taxes not yet due and payable; (b) standard utility and access easements that do not materially interfere with the development, use, or value of the Project; (c) covenants and restrictions of the PD-TOD zoning ordinance; (d) environmental use controls or institutional controls recorded in connection with the IEPA VSRP NFR Letter for Parcel 12-24-300-016 and the engineered barrier/ELUC requirements for Parcel 12-24-300-017, in each case as reviewed and approved by Developer’s counsel and the Construction Lender’s counsel; and (e) such other exceptions as Developer and the Construction Lender may approve in writing.

[Drafting Note — Critical Conflict — Reversionary Interest Prohibited: The Construction Loan Term Sheet (Sections 4.2 and 12) expressly prohibits the mortgaged property from being subject to any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other form of defeasible fee estate in favor of the City or any other party. The Lender states that any such interest would render Developer’s title uninsurable, subordinate the Lender’s first-priority mortgage to the City’s right to reclaim the property, prevent foreclosure, and render the Construction Loan “impossible to close.” Accordingly, no reversionary interest, defeasible fee, right of re-entry, or possibility of reverter in favor of the City may be included among the Permitted Exceptions or elsewhere in this Agreement. The completion-assurance mechanism in Article 12 is drafted as an alternative to the reversionary interest contemplated by Resolution R-2025-017, Condition No. 8. This is the single most significant cross-document conflict and must be resolved with the City before execution. See Article 12 and the drafting note thereto.]

[Drafting Note — Developer Position on Title: Developer requires fee simple absolute, indefeasible title. The City’s title representations in Article 15 must cover each parcel individually given the differing acquisition histories (see Recital A drafting note). The Phase II ESA recommends a comprehensive review of title for each individual parcel prior to consolidation to identify any environmental liens, utility easements, unresolved tax claims, or mechanic’s liens arising from the City’s prior demolition or site-clearing work. OPEN ITEM — require City to deliver, as a condition precedent, an ALTA/NSPS survey and title commitment for each parcel and the consolidated parcel.]

Section 3.4 Parcel Consolidation. The three (3) parcels comprising the Property shall be consolidated into a single parcel of record prior to or concurrent with Closing. The City shall be responsible, at its expense, for effectuating the parcel consolidation, including the preparation and recording of any consolidation plat, and shall obtain all required county approvals.

[Drafting Note — Open Item — Phased Conveyance: The Phase II ESA (Section 8.2) recommends that the parties consider a phased conveyance approach — conveying clean Parcel 015 (and Parcel 017, before or after the engineered barrier) to Developer first, while Parcel 016 remediation proceeds, so that Phase I construction can commence on the clean portions of the Property while Parcel 016 remediation proceeds concurrently. However, Resolution R-2025-017, Condition No. 2(b), requires that, prior to any conveyance of the Property or any portion thereof to Developer, Developer shall have submitted and IEPA shall have approved a RAP for Parcel 016. This creates a tension: the Resolution conditions any conveyance (even of clean Parcel 015) on IEPA RAP approval for Parcel 016, while the Phase II ESA recommends conveying clean parcels first. Developer’s position: pursue a phased conveyance that conveys Parcel 015 (and, subject to the engineered barrier, Parcel 017) upon satisfaction of the conditions precedent applicable to those parcels, with Parcel 016 conveyed upon issuance of the NFR Letter, provided the City agrees to seek any necessary amendment to or clarification of the Resolution’s sequencing. This would protect the Phase I groundbreaking deadline (March 1, 2026) against Parcel 016 remediation delay. OPEN ITEM — confirm legal feasibility of phased conveyance under the Resolution and the PD-TOD rezoning/consolidation process.]

Section 3.5 Closing. Closing shall occur within thirty (30) days following the satisfaction or waiver of all conditions precedent to Closing. The Parties’ target Closing date is [mid-2025], subject to the timing of rezoning, IEPA approvals, and the satisfaction of other conditions.

Section 3.6 Risk of Loss. Between the Effective Date and Closing, the risk of loss or damage to the Property by fire, casualty, or other cause shall remain with the City. The City shall maintain the Property in its current condition and shall not grant any new easements, liens, or encumbrances affecting the Property without Developer’s prior written consent.

## ARTICLE 4. PUBLIC INCENTIVES

Section 4.1 Land Write-Down. The City shall convey the Property to Developer at the Purchase Price representing the Land Write-Down of Nine Million Two Hundred Thousand Dollars ($9,200,000), as provided in Section 3.2.

[Drafting Note — Open Item — Land Write-Down and TIF Cap Interaction: The TIF District Summary Memorandum (Corporation Counsel, March 5, 2025) recommends that the Agreement specify whether the Land Write-Down is charged against the $48,000,000 TIF Reimbursement cap or constitutes a separate incentive funded from another source. Developer’s position: the Land Write-Down is a separate incentive distinct from, and not charged against, the TIF Reimbursement cap, consistent with the Term Sheet (§5.6), which lists the Land Write-Down and TIF Reimbursement as separate line items. OPEN ITEM — confirm City agreement that the Land Write-Down does not reduce the TIF Reimbursement cap.]

Section 4.2 Tax Increment Financing Reimbursement.

- Pledge. The City shall pledge up to Forty-Eight Million Dollars ($48,000,000) in tax increment revenues over the remaining life of the TIF District to reimburse Developer for eligible redevelopment project costs incurred in connection with the Project (the “TIF Reimbursement Cap”). Eligible costs shall include, without limitation: public infrastructure improvements; environmental remediation costs; parking structure construction costs; the Land Write-Down (to the extent, if any, the Parties agree it is TIF-eligible); and other eligible project costs under the TIF Act and the Lakemont Central TIF District Redevelopment Plan adopted by Ordinance No. 2019-42.

- Pay-As-You-Go. TIF Reimbursement shall be on a pay-as-you-go basis. Developer shall front all eligible costs and shall be reimbursed annually from available tax increment as generated by the Project and other developments within the TIF District. The City shall not issue TIF bonds or notes for the Project.

- Reimbursement Priority. TIF Reimbursement shall be made in the following priority order: (i) first, environmental remediation costs for Parcels 12-24-300-016 and 12-24-300-017; (ii) second, public infrastructure costs, including the City’s off-site infrastructure commitment and Developer’s eligible on-site infrastructure expenditures; (iii) third, the public parking structure, public plaza, and community center costs associated with Phase IV; and (iv) fourth, all other eligible costs.

- Annual Increment. The estimated annual tax increment at full Project buildout is approximately Four Million Two Hundred Thousand Dollars ($4,200,000) per year.

- Certified Cost Documentation. Developer shall submit periodic reimbursement requests accompanied by certified cost documentation prepared by Developer’s auditing firm, Clearmont Accounting Group LLP, or another nationally recognized accounting firm acceptable to the City. The City shall have audit rights with respect to such documentation, exercisable within ninety (90) days of receipt of each reimbursement request; absent written objection within such period, the request shall be deemed approved.

[Drafting Note — Major Conflict / Open Item — TIF Cap Reachability: The TIF District Summary Memorandum (a privileged City internal communication) reveals that the $48,000,000 TIF Reimbursement Cap may not be fully reachable over the remaining life of the TIF District (which expires December 31, 2042). Under a base-case projection without accounting for the Phase I property tax abatement, cumulative increment reaches approximately $54.2 million by 2042, exceeding the cap. However, under an adjusted scenario incorporating the Phase I abatement (which reduces the assessed value of Phase I improvements and therefore the increment the TIF District captures from Phase I), cumulative increment through 2042 is estimated at approximately $38 million to $42 million — potentially $6 million to $10 million short of the cap. Under a worst-case timing scenario (with maximum permitted timeline extensions), full-buildout increment collection could be reduced to as few as five to six years, generating only $21 million to $25 million from the full-buildout period. The Corporation Counsel recommends that the Agreement: (a) make TIF Reimbursement expressly contingent on actual increment collected and not a guaranteed City obligation; (b) establish the reimbursement priority in Section 4.2(c); (c) include a City covenant to use good-faith efforts to seek a TIF District extension if reimbursement is tracking materially below projections as of a benchmark date (e.g., 2038); and (d) expressly state that a TIF shortfall does not constitute a default by the City. Developer’s position: Developer accepts that TIF Reimbursement is payable solely from available increment (consistent with the Term Sheet §5.2, which states the City does not guarantee the full cap will be reached), but Developer should resist the City’s proposed one-sided “shortfall is not a default” provision unless it is made mutual (i.e., a TIF shortfall likewise does not constitute a default by Developer or a basis for City termination), and Developer should insist on the City’s good-faith covenant to seek a TIF District extension and on the reimbursement priority in Section 4.2(c) to protect early reimbursement of environmental and infrastructure costs. This is a material economic risk to Developer and a primary open item. OPEN ITEM.]

[Drafting Note — Open Item — Abatement/TIF Interaction: The Phase I property tax abatement (Section 4.4) reduces the assessed value of Phase I improvements, which in turn reduces the tax increment generated by Phase I and available for TIF Reimbursement. The TIF District Summary Memorandum recommends the Agreement acknowledge this interaction. Developer’s position: the Agreement should acknowledge the interaction but should not require Developer to elect between the abatement and TIF Reimbursement; Developer is entitled to both the abatement (as a separate incentive) and TIF Reimbursement of eligible costs to the extent increment is available. OPEN ITEM.]

Section 4.3 Infrastructure Cost-Sharing.

- City Off-Site Infrastructure. The City shall fund Twelve Million Five Hundred Thousand Dollars ($12,500,000) for off-site infrastructure improvements, including: (i) widening of Lakemont Station Boulevard between Oak Street and Maple Avenue; (ii) installation of a new traffic signal at the Oak Street/Lakemont Station Boulevard intersection; (iii) extension of the water main along Lakemont Station Boulevard; and (iv) sanitary sewer upgrade and capacity expansion. The City’s off-site infrastructure funding shall be appropriated and disbursed according to a schedule coordinated with the phased construction timeline and set forth in Schedule 4.3.

- Developer On-Site Infrastructure. Developer shall fund Eight Million Three Hundred Thousand Dollars ($8,300,000) for on-site infrastructure improvements, including internal roadways, utilities, stormwater management, pedestrian pathways, and landscape improvements within the Property.

- Total Infrastructure Budget. The total combined infrastructure budget is Twenty Million Eight Hundred Thousand Dollars ($20,800,000).

[Drafting Note — Open Item — City Infrastructure Funding Source: The TIF District Summary Memorandum recommends the Agreement specify whether the City’s $12,500,000 off-site infrastructure commitment is funded from general revenue/capital improvement funds or from TIF. If funded from TIF, it counts against the $48,000,000 TIF Reimbursement Cap and reduces the increment available for Developer reimbursement. Developer’s position: the City’s $12,500,000 commitment is a separate City obligation funded from general revenue or capital improvement funds, not from TIF, and does not reduce the TIF Reimbursement Cap. The Term Sheet (§5.6) lists City Infrastructure Funding and TIF Reimbursement as separate line items, supporting this position. OPEN ITEM — confirm funding source and that it does not reduce the TIF Reimbursement Cap.]

[Drafting Note — Developer Position — City Infrastructure as Condition: Developer’s obligation to commence Phase I construction should be conditioned on the City’s timely performance of the off-site infrastructure improvements necessary for Phase I (e.g., water main extension, sanitary sewer upgrade). The Term Sheet (§15(d)) gives Developer a termination right if the City fails to fund its committed infrastructure obligations within the timelines specified. The Agreement should specify the City’s infrastructure completion deadlines tied to the Phase I schedule and provide Developer with extensions and remedies for City delay. OPEN ITEM.]

Section 4.4 Property Tax Abatement. The City shall provide a twelve (12)-year declining property tax abatement on Phase I improvements only, measured from the pre-development base equalized assessed value, as follows: Years 1–4 — seventy-five percent (75%) abatement; Years 5–8 — fifty percent (50%) abatement; Years 9–12 — twenty-five percent (25%) abatement; Year 13 and thereafter — full assessment with no abatement. No property tax abatement is provided for Phase II, Phase III, or Phase IV.

Section 4.5 Building Permit Fee Waiver. The City shall waive building permit fees for Phase I and Phase II of the Project, with an estimated combined value of One Million Four Hundred Thousand Dollars ($1,400,000) (Nine Hundred Twenty Thousand Dollars ($920,000) for Phase I and Four Hundred Eighty Thousand Dollars ($480,000) for Phase II). No permit fee waiver is contemplated for Phase III or Phase IV.

## ARTICLE 5. ENVIRONMENTAL MATTERS

Section 5.1 Phase II ESA; Reliance. The Parties acknowledge the Phase II Environmental Site Assessment prepared by Greenfield Environmental Consultants LLC, dated November 8, 2024 (the “Phase II ESA”), which identified the environmental conditions on the Property described in this Article 5. The City shall, at Developer’s request, obtain (or cooperate with Developer in obtaining) reliance letters from Greenfield Environmental Consultants LLC sufficient to permit the City, the Construction Lender, and their respective counsel to rely on the Phase II ESA.

[Drafting Note — Open Item — Phase II ESA Reliance: The Phase II ESA contains a confidentiality and reliance notice stating that reliance by third parties (including the City and First Prairie National Bank) requires execution of a reliance letter from Greenfield Environmental Consultants LLC on terms acceptable to GEC. The Construction Loan Term Sheet (§4.3) requires environmental clearance satisfactory to the Lender. The Agreement should require the City to cooperate in obtaining reliance letters and should allocate the cost thereof. OPEN ITEM.]

Section 5.2 Environmental Conditions.

- Parcel 12-24-300-015. No environmental contamination requiring further action was identified. No further investigation or remediation is required.

- Parcel 12-24-300-016. Petroleum hydrocarbon contamination (benzene, toluene, ethylbenzene, and xylene (“BTEX”) compounds) was identified in soil and groundwater over an area of approximately 1.8 acres, together with localized trichloroethylene (“TCE”) contamination. Remediation under the IEPA VSRP is required, at an estimated cost of Two Million Eight Hundred Thousand Dollars ($2,800,000) and an estimated timeline of fourteen (14) to eighteen (18) months, culminating in issuance of an NFR Letter.

- Parcel 12-24-300-017. Low-level metals contamination in shallow soil consistent with urban fill material was identified. An engineered barrier (clean fill cap) and an ELUC are required, at an estimated cost of Three Hundred Forty Thousand Dollars ($340,000).

- Total Estimated Environmental Remediation Costs. The total estimated environmental remediation costs for the Property are Three Million One Hundred Forty Thousand Dollars ($3,140,000).

Section 5.3 City Indemnification for Pre-Existing Environmental Conditions. The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to pre-existing environmental conditions on the Property (including Parcels 12-24-300-015, 12-24-300-016, and 12-24-300-017), including but not limited to third-party claims, governmental enforcement actions, and contribution or cost-recovery actions under federal or state environmental laws. This indemnification shall survive the expiration or termination of this Agreement and the conveyance of the Property.

[Drafting Note — Developer Position — Environmental Indemnity Scope: The contamination on Parcels 016 and 017 is pre-existing and attributable to the former Lakemont Ironworks operations (which ceased in 2009) and to fill material placed during the 1970s–1990s, all prior to Developer’s involvement. The City acquired the parcels with knowledge of the environmental conditions (the Phase II ESA notes the City’s 2018 purchase records reference a prior Phase I ESA identifying the UST farm and metal finishing operations). The Phase II ESA (Section 4.2.4) states that the current property owner (the City) bears primary responsible-party status under the Illinois Environmental Protection Act. Developer’s position: the City’s indemnity should be broad, uncapped, and survival-bearing, and should expressly cover cost overruns above the $3,140,000 estimate (see Section 5.5). The Term Sheet (§§6 and 16) provides for City indemnification of Developer for pre-existing environmental conditions. OPEN ITEM — confirm City acceptance of an uncapped, survival-bearing indemnity.]

Section 5.4 Remediation Performance.

[Drafting Note — Open Item — Remediation Performer and Cost Allocation: The Term Sheet is silent as to which party performs the remediation. The Phase II ESA (Section 8.2) notes that the City bears primary responsible-party status but that VSRP enrollment by a prospective purchaser is common in brownfield transactions, and that the parties may allocate performance responsibility contractually. Developer’s position: the City, as the owner at the time of contamination and the primary responsible party, should perform (or contract for) and bear the cost of the Parcel 016 remediation and the Parcel 017 engineered barrier, with Developer having the right (but not the obligation) to perform the remediation on the City’s behalf and to be reimbursed from TIF and/or direct City funding, provided that Developer’s performance of remediation shall not constitute an assumption of environmental liability for pre-existing conditions (which remains with the City under Section 5.3). Alternatively, if Developer performs the remediation, all remediation costs (including overruns per Section 5.5) shall be TIF-reimbursable and/or directly funded by the City. The Lakeshore Side Letter (§4.3(d)) requires Investor consent for any acceptance of environmental remediation obligations exceeding $3,140,000 without a corresponding increase in TIF reimbursement or direct City funding. OPEN ITEM — confirm performer, cost allocation, and overrun responsibility.]

- Parcel 016 Remediation. The Party designated pursuant to the foregoing shall enroll Parcel 12-24-300-016 in the IEPA VSRP, prepare and submit a RAP for IEPA approval, implement the approved remedial actions, and obtain the NFR Letter. The Parties shall use commercially reasonable efforts to initiate VSRP enrollment as soon as practicable so that the NFR Letter can be obtained by the second to fourth quarter of 2026.

- Parcel 017 Engineered Barrier. The designated Party shall install the engineered barrier (clean fill cap) and record the ELUC for Parcel 12-24-300-017.

- Vapor Intrusion Evaluation. The RAP for Parcel 016 shall include a vapor intrusion screening evaluation, and, if warranted, vapor mitigation measures shall be incorporated into the building design for structures on or adjacent to the contaminated area, as recommended in the Phase II ESA (Section 7.1).

Section 5.5 Cost Overruns. The Parties acknowledge that the Phase II ESA (Section 5.3) recommends a contingency of twenty-five percent (25%) to thirty-five percent (35%) above the base estimate, and that the total cost exposure for Parcel 016 remediation alone could reach approximately $3.5 million to $3.8 million (and combined total cost exposure approximately $3.8 million to $4.2 million) in a scenario involving significant scope expansion. Any environmental remediation costs exceeding the Total Estimated Environmental Remediation Costs of $3,140,000 shall be borne by the City (or, if Developer performs the remediation, shall be reimbursed to Developer from TIF and/or direct City funding), and shall not be charged against Developer.

[Drafting Note — Developer Position — Cost Overruns: Developer should not bear the risk of cost overruns for pre-existing contamination. The Phase II ESA expressly warns that subsurface conditions may reveal contamination beyond the currently delineated plume and recommends contractual provisions for cost overruns of at least 25–35%. The Lakeshore Side Letter (§4.3(d)) requires Investor consent for environmental obligations exceeding $3,140,000 without offsetting TIF/City funding. OPEN ITEM — confirm City acceptance of overrun responsibility.]

Section 5.6 Environmental Insurance. Developer shall obtain pollution legal liability insurance in an amount not less than Ten Million Dollars ($10,000,000), naming the City and the Construction Lender as additional insureds, with a policy term covering the full construction period and a three-year extended reporting period, as required by the Construction Loan Term Sheet (§4.3).

Section 5.7 Institutional Controls. Any institutional controls or environmental use restrictions (including the ELUC for Parcel 017 and any groundwater use restriction for Parcel 016) recorded against the Property shall be reviewed and approved by Developer’s counsel and the Construction Lender’s counsel prior to recording, and shall be included among the Permitted Exceptions. The PD-TOD development standards shall account for the engineered barrier, restricting below-grade construction in the barrier area unless proper environmental protocols are followed, as recommended in the Phase II ESA (Section 4.3.3).

Section 5.8 NFR Letter as Condition. The issuance of the NFR Letter for Parcel 016 (or, alternatively, evidence of VSRP enrollment with an approved RAP and an environmental escrow or insurance product satisfactory to the Construction Lender) shall be a condition precedent to Closing with respect to Parcel 016, as provided in Article 17.

[Drafting Note — Conflict — IEPA RAP Approval Timing: Resolution R-2025-017, Condition No. 2(b), requires that, prior to any conveyance of the Property or any portion thereof to Developer, Developer shall have submitted and IEPA shall have approved a RAP for Parcel 016. The Term Sheet (§4 and §18.2) lists IEPA approval of the RAP as a condition precedent to Closing (and, in §18.2, as a condition precedent to execution of the definitive Agreement). The Construction Loan Term Sheet (§7.1) requires, for Parcel 016, either (a) an NFR Letter, or (b) evidence of VSRP enrollment with an approved RAP and an environmental escrow/insurance product satisfactory to the Lender, as a condition precedent to closing. These provisions differ as to the required stage of IEPA approval (RAP approval vs. NFR Letter) and the timing (before DA execution vs. before conveyance vs. before loan draw-down on that parcel). Developer’s position: RAP approval (not the full NFR Letter) should be the condition precedent to DA execution and to conveyance of Parcel 016, with the NFR Letter required before vertical construction on Parcel 016 and before Construction Loan draw-down for construction activities on Parcel 016, consistent with the Construction Loan Term Sheet’s alternative (b). This sequencing protects the Phase I groundbreaking deadline. OPEN ITEM — reconcile the required IEPA milestone and timing across the Resolution, Term Sheet, and Construction Loan Term Sheet.]

## ARTICLE 6. PROJECT FINANCING AND EQUITY

Section 6.1 Equity Commitment. Developer shall contribute minimum equity of Eighty-Five Million Dollars ($85,000,000) to the Project before any Construction Loan draw-down, representing not less than approximately 20.6% of the total Project cost. The equity sources are Lakeshore Capital Partners Fund III LP ($51,000,000) and the Pellegrini Family Trust ($34,000,000). All equity shall be contributed and expended on an “equity in first” basis prior to any draw on the Construction Loan, as required by the Construction Loan Term Sheet (§3).

Section 6.2 Equity Demonstration. Developer shall demonstrate committed equity of not less than Eighty-Five Million Dollars ($85,000,000), in form and substance reasonably acceptable to the City, including executed commitment letters from equity partners, evidence of available and uncommitted capital, bank statements, or other documentation, verified by an independent certification from Developer’s auditing firm, Clearmont Accounting Group LLP.

[Drafting Note — Conflict — Equity Demonstration Trigger and Deadline: Resolution R-2025-017, Condition No. 2(a), requires Developer to demonstrate committed equity of not less than $85,000,000 within sixty (60) days of the adoption of the Resolution (i.e., on or before April 19, 2025). The Term Sheet (§7) states that Developer shall demonstrate committed equity “within 60 days of City Council approval of the definitive Agreement.” These are different triggers and deadlines. The Resolution’s deadline (April 19, 2025) is earlier and runs from the Resolution’s adoption (February 18, 2025), while the Term Sheet’s deadline runs from City Council approval of the definitive Agreement (anticipated June 2025). Developer’s position: the Term Sheet’s trigger (60 days after City Council approval of the definitive Agreement) is the operative commitment, as it is the later-negotiated business term; however, Developer should be prepared to demonstrate equity by April 19, 2025, to satisfy the Resolution’s condition, given that the Construction Loan Term Sheet (§7.1) also references the Resolution’s April 19, 2025 deadline. OPEN ITEM — reconcile the equity demonstration deadline; Developer should confirm whether early demonstration is required to keep the Resolution’s conditions satisfied.]

Section 6.3 Construction Loan. Developer has obtained a preliminary (non-binding) commitment from First Prairie National Bank for the Construction Loan in an amount of up to Two Hundred Ten Million Dollars ($210,000,000), subject to execution of this Agreement in form and substance acceptable to the Construction Lender. The Construction Loan proceeds are available for Phase I and Phase II hard and soft construction costs; availability for Phases III and IV is subject to a separate supplemental commitment or amendment.

Section 6.4 Substitute Financing. Developer may substitute the Construction Lender or obtain substitute construction financing on terms no less favorable to the City, provided that Developer shall not be required to close the Construction Loan or any substitute financing as a condition to Developer’s obligations under this Agreement except as expressly provided in Article 17.

Section 6.5 Additional Financing for Later Phases. Developer acknowledges that Phases III and IV are estimated to require additional equity and/or mezzanine financing in an amount of approximately Fifty-Eight Million Four Hundred Thousand Dollars ($58,400,000). Developer shall use commercially reasonable efforts to secure such additional financing prior to the commencement of each subsequent Phase. The structure and terms of such additional financing have not yet been determined.

[Drafting Note — Open Item — Later-Phase Financing and Dilution: The Construction Loan Term Sheet (§3 and §8.1) provides that any equity raise that results in the dilution of the Pellegrini Family Trust’s ownership interest below [50]% will require the Lender’s prior written consent and may constitute a Change of Control, and that any subordinate financing for later phases requires the Lender’s prior written consent. The Lakeshore Side Letter (§5.1, §5.3) anticipates that the approximately $58,400,000 in additional mezzanine/equity financing for later phases may dilute the Pellegrini Interest below both the 51% threshold (Lakeshore) and the 50% threshold (Term Sheet/Lender), and requires the Parties to work together to structure the Agreement’s assignment and change-of-control provisions to accommodate approved capital raises. The Agreement should not prohibit later-phase capital raises that are approved by the Construction Lender and the City, and should include the broader permitted-transfer carve-outs described in Article 16. OPEN ITEM.]

Section 6.6 Financing Condition. Developer’s obligation to commence construction of any Phase is expressly conditioned upon Developer’s receipt of construction financing for such Phase on terms satisfactory to Developer in its reasonable discretion. Developer’s failure to obtain financing for a Phase shall not constitute a default by Developer, but shall entitle Developer to the extensions and remedies provided in Article 11 and Article 13.

[Drafting Note — Developer Position — Financing Condition: The Term Sheet (§14) excludes “Developer’s failure to obtain financing” from Force Majeure. However, the Term Sheet (§15(d)) and the Resolution contemplate that Developer’s obligations are subject to financing. Developer’s position: a financing-out condition for each Phase protects Developer against the risk that the non-binding Construction Loan commitment does not result in a closed loan, and against later-phase financing risk. The Construction Loan Term Sheet is expressly non-binding and subject to credit committee approval and due diligence. The City should accept a financing condition (with notice and good-faith efforts to obtain financing) as an alternative to a hard default. This is a significant open item given the non-binding nature of the Construction Loan commitment. OPEN ITEM.]

## ARTICLE 7. PERFORMANCE SECURITY

Section 7.1 Phase I Performance Security. Prior to the conveyance of the Property to Developer, Developer shall post a performance bond in the amount of Fifteen Million Dollars ($15,000,000), issued by Ridgepoint Surety Corporation or another surety company reasonably acceptable to the City, or an irrevocable standby letter of credit in the equivalent amount issued by a nationally recognized financial institution acceptable to the City (collectively, the “Phase I Performance Security”). The Phase I Performance Security shall secure Developer’s obligation to commence and substantially complete Phase I in accordance with this Agreement.

Section 7.2 Maintenance and Release. The Phase I Performance Security shall be maintained continuously from the date of conveyance of the Property until Phase I Substantial Completion, as evidenced by issuance of a temporary or final certificate of occupancy by the City. Upon Phase I Substantial Completion, the Phase I Performance Security shall be released and returned to Developer within thirty (30) days following written request and verification of Substantial Completion by the City.

Section 7.3 Later-Phase Performance Security. The amount, form, and conditions of any performance security for Phase II, Phase III, and Phase IV shall be established by the Parties in good faith prior to the commencement of each such Phase, taking into account the scope and cost of such Phase.

[Drafting Note — Open Item — Later-Phase Performance Security: The Term Sheet (§8) and the Lakeshore Side Letter (§4.3(e)) provide that performance security amounts for later phases are to be established in the definitive Agreement. Developer’s position: later-phase performance security should be reasonable in relation to the scope of each Phase and should not be required to be posted until the commencement of the applicable Phase, and the form (bond or letter of credit) should be at Developer’s election. The Lakeshore Side Letter requires Investor consent for any modification to performance bond/LC requirements. OPEN ITEM.]

[Drafting Note — Open Item — Construction Lender Assignment of Performance Security: The Construction Loan Term Sheet (§4.1) requires, as collateral, an assignment of any performance bonds or letters of credit posted in connection with this Agreement, including the $15,000,000 Phase I performance bond. The Agreement should permit Developer to assign the Phase I Performance Security to the Construction Lender as collateral, and the City’s draw rights should be coordinated with the Construction Lender’s rights through an intercreditor or control agreement acceptable to the City, Developer, and the Construction Lender. OPEN ITEM.]

## ARTICLE 8. CONSTRUCTION STANDARDS AND REQUIREMENTS

Section 8.1 Prevailing Wage.

- To the extent required by the Illinois Prevailing Wage Act, 820 ILCS 130/0.01 et seq. (the “Prevailing Wage Act”), Developer shall comply with prevailing wage requirements for construction work performed on the Project that constitutes “public works” within the meaning of the Prevailing Wage Act. Developer shall include prevailing wage requirements in all contracts and subcontracts for such construction work, shall maintain certified payroll records, and shall make such records available to the City and the Illinois Department of Labor upon request.

- Developer shall post prevailing wage rate schedules at the construction site and shall update such postings as revised schedules are issued.

[Drafting Note — Conflict / Open Item — Scope of Prevailing Wage Coverage: The Term Sheet (§11.1) and Resolution (§8) state that “all construction performed on the Project” shall comply with the Prevailing Wage Act. The TIF District Summary Memorandum (Section V) analyzes whether the various forms of public financial assistance (land write-down, TIF, abatement, fee waivers) render the entire Project — including purely private components such as market-rate residential, private office, and the hotel — subject to prevailing wage, and recommends that the City “insist on prevailing wage coverage for all construction to eliminate ambiguity,” while acknowledging that “the Developer’s counsel [is] likely to argue[] during negotiation regarding the scope of coverage, particularly for purely private components.” Developer’s position: prevailing wage should apply to the extent required by statute (i.e., to “public works” paid for in whole or in part out of public funds, including TIF-reimbursed components, off-site public infrastructure, environmental remediation to the extent TIF-reimbursed, and the Phase IV public parking structure, public plaza, and community center), and the Agreement should delineate the components subject to prevailing wage by operation of statute versus by contractual agreement. Converting a “potentially debatable statutory question into an unambiguous contractual obligation” (as the Corporation Counsel recommends) would increase construction costs for purely private components and should be the subject of focused negotiation. OPEN ITEM — scope of prevailing wage coverage for purely private components.]

Section 8.2 LEED Certification. All buildings constructed as part of the Project shall be designed and constructed to achieve LEED Gold certification, or an equivalent green building certification as approved by the City in writing (such approval not to be unreasonably withheld), as administered by the U.S. Green Building Council. Developer shall register each building with the U.S. Green Building Council prior to commencement of construction of the applicable building and shall submit documentation of certification status to the City upon receipt of certification.

[Drafting Note — Open Item — LEED “Equivalent” Standard: Resolution R-2025-017, Condition No. 2(f), permits “an equivalent green building certification as determined acceptable by the Director of the Community Development Department.” Developer’s position: the “equivalent” standard and the decision-maker should be defined to avoid unilateral discretion; the Agreement should provide that the City’s approval of an equivalent certification shall not be unreasonably withheld and that the specific LEED rating system applicable to each building component shall be identified in a Schedule. OPEN ITEM.]

Section 8.3 Insurance. Developer shall maintain, or cause its general contractor to maintain, throughout the construction period for each Phase, the following minimum insurance coverages: (a) Commercial General Liability of not less than $10,000,000 per occurrence and $25,000,000 in the aggregate; (b) Umbrella/Excess Liability of not less than $25,000,000; (c) Builder’s Risk at full replacement value of each Phase under construction; (d) Workers’ Compensation at statutory limits; (e) Automobile Liability of $5,000,000 combined single limit; and (f) Pollution Legal Liability of not less than $10,000,000. The City and the Construction Lender shall be named as additional insureds and/or loss payees, as applicable. All carriers shall be rated A- VII or better by A.M. Best. All policies shall provide not less than thirty (30) days’ prior written notice of cancellation or material modification.

[Drafting Note — Conflict — Insurance Limits: The Term Sheet (§11.3) specifies Commercial General Liability of $10,000,000 per occurrence and $20,000,000 in the aggregate, while the Construction Loan Term Sheet (§5) specifies $10,000,000 per occurrence and $25,000,000 in the aggregate, plus Umbrella/Excess of $25,000,000 and Professional Liability of $5,000,000. The higher limits in the Construction Loan Term Sheet govern, as the Construction Lender will require them. The Agreement has been drafted to the higher (Construction Loan) standard. The Term Sheet’s lower CGL aggregate ($20,000,000) is superseded. OPEN ITEM — confirm City acceptance of the higher limits and allocation of the incremental premium cost.]

Section 8.4 Construction Monitoring. Developer shall submit quarterly construction progress reports to the City’s Community Development Department, including percentage of completion, updated schedule, and identification of any delays or anticipated deviations from the approved timeline, within thirty (30) days following the end of each calendar quarter during which active construction is occurring.

## ARTICLE 9. AFFORDABLE HOUSING

Section 9.1 Affordable Housing Commitment. Developer shall include not less than one hundred six (106) Affordable Units across the Project, representing not less than twenty percent (20%) of the total residential dwelling units, with rents restricted to households earning at or below sixty percent (60%) of AMI. The planned Affordable Unit breakdown is: (a) Phase I — sixty-four (64) Affordable Units out of three hundred twenty (320) total residential units; and (b) Phase III — forty-two (42) Affordable Units out of two hundred ten (210) total residential units.

[Drafting Note — Conflict — Affordable Unit Count: The Term Sheet (§3.5 Summary Totals) states “Total Affordable Units: At least 100 affordable units across the Project, at or below 60% AMI,” while the Term Sheet (§12), the Resolution (Condition No. 2(g)), and the Developer’s RFP Response Narrative each state 106 Affordable Units (20% of 530 total residential units). The Resolution makes the 20% minimum a condition of approval. Developer’s position: the Agreement should commit to not less than 106 Affordable Units (20%), consistent with the Resolution’s binding condition and the Term Sheet §12, while noting that the Term Sheet §3.5 “at least 100” figure appears to be an internal inconsistency. The “at least 100” language should not be relied upon as the floor, given the Resolution’s 20% condition. OPEN ITEM — confirm the binding minimum is 106 units / 20%.]

Section 9.2 Integration and Quality. Affordable Units shall be distributed proportionally across unit types (studio, one-bedroom, and two-bedroom) and shall not be segregated or concentrated on particular floors or in separate wings. Affordable Units shall be comparable in design, finishes, and amenity access to market-rate units within the same building, subject to reasonable variations consistent with industry practice.

Section 9.3 Affordability Restriction Period. Affordability restrictions shall remain in effect for a minimum period of thirty (30) years from the date of issuance of the certificate of occupancy for the applicable Phase.

Section 9.4 Affordable Housing Covenant. The affordability restrictions shall be memorialized by an Affordable Housing Covenant recorded against the applicable parcel and running with the land, in a form to be agreed by the Parties and set forth in a Schedule. Developer shall comply with the City’s Affordable Housing Compliance Program and shall provide annual income certification documentation to the City’s Community Development Department for all Affordable Units throughout the Affordability Restriction Period.

[Drafting Note — Developer Position — Affordability Covenant Form: The form of the Affordable Housing Covenant should be negotiated and attached as a Schedule before execution. Developer should seek to limit the City’s enforcement remedies to the Affordable Units themselves (e.g., loss of affordability status, monetary penalties) rather than remedies that could impair Developer’s fee simple title or the Construction Lender’s security, consistent with the title-insurability requirements of Article 3. OPEN ITEM.]

## ARTICLE 10. COMMUNITY BENEFITS

Section 10.1 Local Hiring Goal. Developer shall use commercially reasonable efforts to achieve a goal of thirty-five percent (35%) Lakemont residents for construction workforce employment across all Phases of the Project, measured on a cumulative Project-wide basis. Developer shall submit quarterly reports to the City’s Community Development Department documenting local hiring percentages. Failure to achieve the thirty-five percent (35%) local hiring goal in any given quarter or on a cumulative basis shall not, in and of itself, constitute a default under this Agreement, provided that Developer demonstrates good-faith efforts to achieve the goal, including posting job openings with the City’s workforce development partners, attending local job fairs, and providing reasonable notice of hiring opportunities to the Community Development Department.

[Drafting Note — Conflict — Local Hiring: Goal vs. Requirement: The Term Sheet (§9) frames the thirty-five percent (35%) local hiring commitment as a “goal” measured on a cumulative Project-wide basis, with express good-faith compliance and a statement that “failure to achieve the 35% local hiring goal in any given quarter or on a cumulative basis shall not, in and of itself, constitute a default.” Resolution R-2025-017, Condition No. 2(c)(i), states the local hiring requirement as “not less than thirty-five percent (35%) of all construction labor hours.” Developer’s position: the Term Sheet’s “good-faith goal” formulation (non-default for failure to achieve) is the operative and more favorable term, and the Agreement has been drafted accordingly. The Resolution’s “not less than 35%” language should be interpreted as a goal, not a hard default trigger, given the Term Sheet’s express non-default provision. OPEN ITEM — confirm City acceptance that local hiring is a good-faith goal, not a default trigger.]

Section 10.2 First-Source Hiring Program. Developer and its commercial tenants shall partner with the Lakemont Workforce Center for the recruitment, training, and hiring of individuals to fill permanent employment positions created within the Project, as required by Resolution R-2025-017, Condition No. 2(c)(iii).

[Drafting Note — Conflict / Open Item — First-Source Hiring Not in Term Sheet: Resolution R-2025-017, Condition No. 2(c)(iii), requires a first-source hiring program under which Developer and its commercial tenants partner with the Lakemont Workforce Center. The Term Sheet (§9) does not address first-source hiring for permanent positions (it addresses only construction local hiring). The first-source hiring obligation is therefore a Resolution condition not reflected in the Term Sheet. Developer’s position: the first-source hiring program should be a good-faith effort obligation (referral source, notice of openings) rather than a mandatory hiring quota, and Developer cannot bind its commercial tenants to mandatory hiring requirements (tenants make their own hiring decisions); the Agreement should impose on Developer an obligation to include first-source cooperation provisions in leases as a lease requirement, with Developer’s obligation being to require such provisions rather than to guarantee tenant compliance. OPEN ITEM — confirm scope and that the obligation is a good-faith effort, not a quota, and clarify Developer’s inability to guarantee tenant hiring decisions.]

Section 10.3 Living Wage. All permanent employees employed at retail establishments and hotel operations within the Project shall be compensated at a wage rate of not less than Seventeen Dollars and Fifty Cents ($17.50) per hour, as required by Resolution R-2025-017, Condition No. 2(c)(ii).

[Drafting Note — Conflict / Open Item — Living Wage Not in Term Sheet; Tenant-Employee Scope: Resolution R-2025-017, Condition No. 2(c)(ii), imposes a living wage requirement of not less than $17.50 per hour on “all permanent employees employed at retail establishments and hotel operations within the Project.” The Term Sheet (§9) does not address a living wage requirement at all. This is a Resolution condition not reflected in the Term Sheet. Critically, the living wage applies to employees of retail and hotel tenants/operators, not to Developer’s own employees. Developer’s position: (i) Developer cannot directly control or guarantee the wage rates paid by independent retail and hotel tenants and operators, who are separate employers; (ii) the Agreement should impose on Developer an obligation to include a living-wage lease/operating-agreement covenant in retail and hotel leases/operating agreements, with Developer’s obligation being to require such covenants rather than to guarantee tenant compliance; (iii) the living wage should be indexed or subject to periodic review and should not apply to employees of the hotel operator under a franchise/management arrangement beyond what Developer can contractually require; and (iv) a default for a tenant’s living-wage violation should be the tenant’s default under its lease, not Developer’s default under this Agreement, absent Developer’s failure to include the required covenant. This is a significant open item because it imposes a cost obligation on third-party tenants not party to this Agreement. OPEN ITEM — confirm the mechanism, the allocation of responsibility as between Developer and its tenants/operators, and the default consequences.]

## ARTICLE 11. PHASING, TIMELINES, AND FORCE MAJEURE

Section 11.1 Phasing Schedule. The Project shall be constructed in four Phases in accordance with the following schedule:

| Phase | Commencement Deadline | Substantial Completion Deadline |
| --- | --- | --- |
| Phase I | Groundbreaking no later than March 1, 2026 | September 30, 2028 (approximately 30 months) |
| Phase II | Within 12 months of Phase I Substantial Completion | Within 24 months of Phase II commencement |
| Phase III | Within 12 months of Phase II Substantial Completion | Within 30 months of Phase III commencement |
| Phase IV | Concurrent with Phase III commencement | Within 24 months of Phase IV commencement |

The commencement deadline for each subsequent Phase is measured from the Substantial Completion date of the immediately preceding Phase, as may be extended by Force Majeure. Developer shall provide quarterly construction progress reports to the City’s Community Development Department.

Section 11.2 Substantial Completion. “Substantial Completion” means the completion of construction of the applicable Phase to the point where the building or improvements can be occupied and used for their intended purpose, as evidenced by the issuance of a temporary or final certificate of occupancy by the City’s Building Department. A Phase shall be deemed Substantially Complete upon the earlier of (a) issuance of a temporary or final certificate of occupancy for the applicable Phase, or (b) the date on which the applicable Phase is complete except for minor punch-list items that do not prevent occupancy or use, provided Developer is diligently completing such items.

[Drafting Note — Open Item — Substantial Completion Definition: The Term Sheet (§13) states that Substantial Completion “generally means” completion to the point of occupancy as evidenced by a certificate of occupancy, but defers the precise definition to the definitive Agreement. Developer’s position: the definition should include a “temporary or final” certificate of occupancy and a punch-list carve-out (as drafted) so that minor incomplete items do not delay a finding of Substantial Completion. The Construction Loan Term Sheet (§9, item 9) treats failure to achieve Substantial Completion of Phase I by September 30, 2028 as an Event of Default (subject to force majeure extensions of up to 180 days and Lender-approved extensions). The Agreement’s definition should be consistent with the Construction Loan Documents. OPEN ITEM.]

Section 11.3 Force Majeure.

- Definition. “Force Majeure” means any event beyond the reasonable control of Developer that prevents or materially delays performance, including, without limitation: acts of God, fire, flood, earthquake, tornado, severe weather, pandemic, epidemic, quarantine, governmental health orders, war, terrorism, civil unrest, insurrection, strikes or labor disputes (other than those caused by Developer’s labor practices or Developer’s failure to comply with applicable labor laws), industry-wide supply chain disruptions beyond Developer’s reasonable control, governmental moratoria on construction, and actions or inactions of governmental authorities (other than the City of Lakemont) that prevent or materially delay construction. Force Majeure shall also include delays in the issuance of the NFR Letter or other IEPA approvals attributable to IEPA review timelines, regulatory requirements, or the discovery of additional contamination during remediation, and delays attributable to the City’s failure to timely perform its obligations under this Agreement (including the City’s off-site infrastructure obligations and rezoning/consolidation obligations).

- Effect. Force Majeure events shall extend the applicable deadlines for commencement and Substantial Completion on a day-for-day basis for the duration of the Force Majeure event.

- Aggregate Cap. The maximum extension of time available under this Section 11.3 shall not exceed twenty-four (24) months in the aggregate across the Project.

- Notice. Developer shall provide written notice to the City within fifteen (15) business days of the occurrence of a Force Majeure event, describing in reasonable detail the nature of the event, its anticipated duration, and its expected impact on the Project timeline, with updated notices as circumstances change.

- Mitigation. Developer shall use commercially reasonable efforts to mitigate the effects of any Force Majeure event.

- Exclusions. Force Majeure shall not include Developer’s negligence or willful misconduct.

[Drafting Note — Conflict / Open Item — Force Majeure Cap and Scope: The Term Sheet (§14) provides an aggregate Force Majeure cap of eighteen (18) months across the Project and excludes “financial inability to perform, changes in market conditions, increases in the cost of labor or materials (unless attributable to an industry-wide supply chain disruption), Developer’s failure to obtain financing, or any event caused by Developer’s negligence or willful misconduct.” Developer’s position: (i) the eighteen-month aggregate cap is insufficient for a decade-long, four-Phase Project and should be increased to twenty-four (24) months (as drafted), or alternatively applied on a per-Phase basis; (ii) the Force Majeure definition should expressly include IEPA/regulatory delays and NFR Letter delays (the Phase II ESA, Section 8.2, recommends the transactional documents address whether delay in NFR Letter issuance constitutes Force Majeure, a basis for deadline extension, or a default — Developer’s position is that it should be Force Majeure/extension, not default, given that the contamination is pre-existing and the City bears primary responsible-party status); and (iii) the Force Majeure definition should include delays caused by the City’s failure to timely perform its own obligations (rezoning, consolidation, off-site infrastructure, RAP cooperation). The Term Sheet’s exclusion of “Developer’s failure to obtain financing” is addressed separately by the financing-out condition in Section 6.6. OPEN ITEM — confirm City acceptance of a 24-month cap (or per-Phase caps) and inclusion of IEPA/regulatory and City-delay events.]

## ARTICLE 12. COMPLETION ASSURANCE

Section 12.1 Completion Assurance Mechanism. In lieu of any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other form of defeasible fee estate in favor of the City (collectively, “Defeasible Fee Interests”), the Parties agree that the City’s interest in ensuring timely completion of Phase I shall be secured by the following alternative completion-assurance mechanism, which preserves Developer’s fee simple absolute title to the Property:

- Phase I Performance Security. The Phase I Performance Security in the amount of Fifteen Million Dollars ($15,000,000) posted pursuant to Article 7, which the City may draw upon in the event of Developer’s uncured failure to achieve Phase I Substantial Completion.

- Liquidated Damages. In the event Developer fails to achieve Phase I Substantial Completion by the Phase I Substantial Completion Deadline (as extended by Force Majeure and any agreed extensions), and such failure remains uncured following the expiration of all applicable cure periods (including the Construction Lender’s extended cure period under Section 18.2), Developer shall pay to the City liquidated damages in the amount of [●] per day for each day of delay beyond the Phase I Substantial Completion Deadline, up to a maximum aggregate amount of [●]. The Parties acknowledge that the City’s actual damages in the event of a completion delay are difficult to ascertain and that the liquidated damages set forth herein represent a reasonable pre-estimate of the City’s actual damages.

- Contractual Repurchase Option. In the event Developer fails to achieve Phase I Substantial Completion within [the later of (i) the Phase I Substantial Completion Deadline plus all Force Majeure and cure extensions, or (ii) [●] months after conveyance of the Property], and such failure remains uncured following the expiration of all applicable cure periods (including the Construction Lender’s extended cure period), the City shall have the option to repurchase the Property from Developer at a repurchase price equal to the lesser of (A) the Purchase Price paid by Developer, or (B) the then-current fair market value of the Property as determined by an independent MAI appraiser mutually selected by the Parties. The City’s repurchase option shall be exercisable only after (1) the expiration of all cure periods, (2) the Construction Lender’s prior written consent or full satisfaction of the outstanding Construction Loan balance, and (3) the City’s delivery of written notice of exercise within sixty (60) days after the date the repurchase option becomes exercisable. The repurchase option shall be subordinate to the Construction Lender’s first-priority mortgage and shall not impair Developer’s fee simple absolute title except upon the City’s valid exercise in accordance with this Section.

[Drafting Note — CENTRAL CONFLICT — Reversionary Interest vs. Lender Prohibition vs. Investor Consent: This Article addresses the most significant cross-document conflict in the transaction:

- Resolution R-2025-017, Condition No. 2(h), requires Developer to grant the City a “reversionary interest” in the Property such that, if Phase I is not Substantially Complete within thirty-six (36) months of the date of conveyance of the Property to Developer, fee simple title to the Property shall automatically revert to the City, together with all improvements, subject to the City’s obligation to refund the Purchase Price (net of damages). The form, terms, and conditions of the reversionary interest are to be set forth in the Development Agreement and recorded against the Property at conveyance.

- The Construction Loan Term Sheet (Sections 4.2 and 12) expressly and unconditionally prohibits the mortgaged property from being subject to any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other form of defeasible fee estate in favor of the City or any other party. The Lender states that any such interest would (a) be uninsurable under standard ALTA title insurance policies; (b) subordinate the Lender’s first-priority mortgage to the City’s right to reclaim the property; (c) prevent the Lender from exercising standard foreclosure remedies; and (d) render the Construction Loan “impossible to close.” The Lender requires that the Development Agreement “not contain any reversionary interest, defeasible fee condition, right of re-entry, or possibility of reverter in favor of the City or any other party that would render Borrower’s fee simple title defeasible or uninsurable.”

- The Lakeshore Side Letter (Section 7(d)) provides that Developer shall not, without Investor’s prior written consent, agree to any clawback, reversionary interest, right of re-entry, repurchase option, or similar mechanism in the Development Agreement, and acknowledges that the parties must negotiate terms compatible with the Construction Lender’s requirements and Investor’s interests.

These three positions are directly in conflict. The Resolution demands a recorded reversionary interest; the Construction Lender prohibits any such interest as a condition of financing; and the Investor requires consent to any clawback mechanism. If the reversionary interest is incorporated as stated in the Resolution, the Construction Loan cannot close, which would in turn jeopardize the Project and Developer’s equity.

Developer’s position (reflected in this Article 12): the Agreement must substitute an alternative completion-assurance mechanism that satisfies the City’s legitimate interest in ensuring timely Phase I completion while preserving Developer’s fee simple absolute title and the Construction Lender’s first-priority security interest. The Construction Loan Term Sheet (Section 12) suggests acceptable alternatives, including (i) a contractual repurchase option exercisable only after satisfaction of the Construction Lender’s mortgage; (ii) a performance escrow or additional letter of credit; (iii) liquidated damages; (iv) an enhanced completion guaranty; and (v) a right of first refusal. This Article combines the Phase I Performance Security, liquidated damages, and a contractual repurchase option (subordinate to the Construction Lender’s mortgage and exercisable only after cure periods and Lender consent/satisfaction). No Defeasible Fee Interest is granted. This structure must be negotiated with and accepted by the City, the Construction Lender, and the Investor (Lakeshore Capital Partners Fund III LP) before execution. This is the single most critical open item in the transaction. OPEN ITEM — CRITICAL.]

[Drafting Note — Conflict — Reversion 36-Month Period vs. Phase I Substantial Completion Deadline: Resolution R-2025-017, Condition No. 2(h), triggers the reversion if Phase I is not Substantially Complete within thirty-six (36) months of the date of conveyance. The Phase I Substantial Completion Deadline is September 30, 2028 (approximately 30 months from the March 1, 2026 groundbreaking deadline). If the Closing/conveyance occurs in mid-2025 (the Parties’ target), the 36-month reversion period would expire in mid-2028 — approximately three months BEFORE the Phase I Substantial Completion Deadline of September 30, 2028 — and would not account for the time between conveyance and groundbreaking or for Force Majeure extensions. The 36-month reversion period is therefore shorter than the contractual Phase I completion timeline and could trigger before the Phase I Substantial Completion Deadline. Developer’s position: any completion-assurance trigger must be aligned with (and not shorter than) the Phase I Substantial Completion Deadline plus all Force Majeure and cure extensions, as reflected in Section 12.1(c). The 36-month period in the Resolution should not be carried forward as a standalone trigger. OPEN ITEM — reconcile the completion-assurance trigger date with the Phase I Substantial Completion Deadline.]

Section 12.2 No Defeasible Fee. The Parties expressly agree that nothing in this Agreement shall be construed to grant the City any Defeasible Fee Interest in the Property. Developer’s title to the Property shall remain fee simple absolute and indefeasible, subject only to the Permitted Exceptions and the contractual remedies set forth in this Article 12, which are intended to be contractual and financial in nature and not to create any estate or interest in the Property superior to or pari passu with the Construction Lender’s first-priority mortgage.

Section 12.3 Recording. A memorandum or notice of this Agreement, in a form acceptable to Developer, the City, and the Construction Lender, may be recorded against the Property. No reversionary interest, defeasible fee, or similar estate-shifting provision shall be recorded.

## ARTICLE 13. DEFAULT, CURE, AND TERMINATION

Section 13.1 Monetary Defaults. In the event of a monetary default by either Party (including Developer’s failure to pay the Purchase Price or the City’s failure to fund committed infrastructure amounts), the non-defaulting Party shall provide written notice specifying the nature and amount of the default. The defaulting Party shall have sixty (60) days from receipt of such notice to cure the default.

Section 13.2 Non-Monetary Defaults. In the event of a non-monetary default by either Party, the non-defaulting Party shall provide written notice specifying the nature of the default in reasonable detail. The defaulting Party shall have ninety (90) days from receipt of such notice to cure the default; provided, however, that if the nature of the default is such that it cannot reasonably be cured within ninety (90) days, the defaulting Party shall have such additional time as is reasonably necessary to effect a cure, so long as the defaulting Party has commenced cure efforts within the initial ninety (90) day period and is diligently and continuously pursuing cure to completion.

Section 13.3 Termination by City. The City shall have the right to terminate this Agreement upon: (a) a material breach by Developer that remains uncured after the expiration of the applicable cure period (including the Construction Lender’s extended cure period under Section 18.2); (b) Developer’s failure to commence Phase I construction within six (6) months following conveyance of the Property, subject to Force Majeure and the financing condition; (c) Developer’s abandonment of the Project, evidenced by cessation of all construction activity for a period of one hundred eighty (180) consecutive days (other than cessation caused by Force Majeure); and (d) such other events of default as may be specified in this Agreement.

Section 13.4 Termination by Developer. Developer shall have the right to terminate this Agreement upon: (a) the City’s failure to deliver clean, marketable, and insurable fee simple title to the Property at Closing in accordance with Article 3; (b) the City’s failure to fund its committed infrastructure obligations ($12,500,000) within the timelines specified in Schedule 4.3; (c) the City’s failure to timely complete the rezoning of the Property to PD-TOD or the parcel consolidation; (d) the City’s failure to obtain or maintain TIF eligibility for the Project or the unavailability of TIF funds for the purposes described in this Agreement, to the extent such failure materially and adversely affects the Project’s economics; (e) a condemnation or taking by eminent domain (by any entity other than the City) of more than fifteen percent (15%) of the Property; (f) the City’s material breach that remains uncured after the expiration of the applicable cure period; and (g) such other events of default as may be specified in this Agreement.

[Drafting Note — Developer Position — Developer Termination Rights: The Term Sheet (§15(d)) provides Developer termination rights for (a) City failure to deliver title, (b) City failure to fund infrastructure, (c) condemnation >15% by a non-City entity, and (d) other events. Developer’s position: the Agreement should expand Developer’s termination rights to include the City’s failure to timely complete rezoning and parcel consolidation (which are City obligations and conditions precedent), the City’s failure to maintain TIF eligibility (a material economic risk given the TIF reachability concerns flagged in Article 4), and the City’s material breach generally. These additional rights protect Developer against City-side delays and failures that could jeopardize the Project. OPEN ITEM — confirm City acceptance of expanded Developer termination rights.]

Section 13.5 Remedies. Upon termination of this Agreement by a non-defaulting Party, the non-defaulting Party shall have all remedies available at law or in equity, including damages, specific performance, and injunctive relief, subject in all cases to the dispute resolution provisions of Article 19. Except as expressly provided in this Agreement, neither Party shall be liable to the other for consequential, special, indirect, or punitive damages.

[Drafting Note — Developer Position — Limitation of Remedies: Developer should seek a mutual waiver of consequential, special, indirect, and punitive damages (as drafted) and a cap on Developer’s monetary liability to the City (other than the liquidated damages and performance security in Article 12 and the indemnities in Article 14) to avoid open-ended exposure. The Term Sheet (§15) does not address damage caps. OPEN ITEM — confirm City acceptance of a mutual consequential-damages waiver and a Developer liability cap.]

Section 13.6 Effect of TIF Shortfall. A shortfall in TIF Reimbursement (including the failure to reach the TIF Reimbursement Cap) shall not constitute a default by the City or by Developer, shall not constitute a material breach, and shall not be a basis for termination by either Party.

[Drafting Note — Developer Position — Mutuality of TIF Shortfall Provision: The TIF District Summary Memorandum recommends that the Agreement “expressly state that a shortfall in TIF reimbursement does not constitute a default by the City.” Developer’s position: if a TIF shortfall is not a City default, it must likewise not be a Developer default or a basis for City termination, and Developer should retain the right to seek the City’s good-faith effort to extend the TIF District (Section 4.2) and to adjust later-Phase scope or timing in response to a material TIF shortfall. The provision is drafted to be mutual. OPEN ITEM — confirm mutuality and Developer’s adjustment rights.]

## ARTICLE 14. INDEMNIFICATION

Section 14.1 Mutual Indemnification. Each Party shall indemnify, defend, and hold harmless the other Party, and its officers, employees, agents, and representatives, from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to the indemnifying Party’s negligent acts or omissions, reckless conduct, or willful misconduct in connection with the performance of its obligations under this Agreement.

Section 14.2 Developer Indemnification of City. Developer shall indemnify, defend, and hold harmless the City from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to construction activities on the Property, including without limitation claims for personal injury, death, property damage, and workers’ compensation, regardless of whether such claims are brought by Developer’s employees, contractors, subcontractors, or third parties.

Section 14.3 City Indemnification of Developer. The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to pre-existing environmental conditions on the Property, as provided in Section 5.3.

Section 14.4 Survival. The indemnification obligations set forth in this Article 14 shall survive the expiration or termination of this Agreement.

[Drafting Note — Open Item — Indemnity Caps and Carve-Outs: The Term Sheet (§16) does not address indemnity caps. Developer’s position: (i) the City’s indemnification for pre-existing environmental conditions (Sections 5.3 and 14.3) should be uncapped and survival-bearing, given the pre-existing nature of the contamination and the City’s primary responsible-party status; (ii) Developer’s mutual indemnity (Section 14.1) and construction indemnity (Section 14.2) should be subject to a mutual cap (e.g., [●] or the applicable Phase hard construction cost), except for claims arising from Developer’s willful misconduct or gross negligence and claims for personal injury, death, or property damage to the extent covered by insurance; and (iii) each Party’s indemnity should be subject to the other Party’s duty to mitigate. The Construction Loan Term Sheet does not impose indemnity caps, but Developer should seek them in negotiation with the City. OPEN ITEM — confirm caps, carve-outs, and survival terms.]

## ARTICLE 15. REPRESENTATIONS AND WARRANTIES

Section 15.1 Representations of Developer. Developer represents and warrants to the City that: (a) Developer is a limited liability company duly organized, validly existing, and in good standing under the laws of the State of Illinois; (b) Developer has full power and authority to enter into this Agreement and to perform its obligations hereunder, and the execution and delivery of this Agreement has been duly authorized by all necessary action; (c) the execution and delivery of this Agreement will not conflict with or violate Developer’s organizational documents or any other material agreement to which Developer is a party; (d) Developer has the financial capacity, development experience, and organizational resources necessary to complete the Project in accordance with the terms of this Agreement; (e) the ownership structure of Developer is as follows: Pellegrini Family Trust — 60%; Lakeshore Capital Partners Fund III LP — 25%; TransitWorks Equity Group LLC — 15%; and (f) Developer’s consolidated net worth at the entity level is approximately One Hundred Eighty-Five Million Dollars ($185,000,000), and Developer has bonding capacity of up to Seventy-Five Million Dollars ($75,000,000) through Ridgepoint Surety Corporation.

Section 15.2 Representations of the City. The City represents and warrants to Developer that: (a) the City is a home rule municipality duly organized and existing under the laws of the State of Illinois; (b) the City has full power and authority to enter into this Agreement and to perform its obligations hereunder, and the execution and delivery of this Agreement has been duly authorized by all necessary action, including approval by the City Council; (c) the City has good and marketable fee simple title to the Property, free and clear of all liens, encumbrances, and adverse claims (except the Permitted Exceptions), and has the legal authority to convey the Property to Developer; (d) the Property is located within the TIF District and TIF funds are legally available for the purposes described in this Agreement, subject to annual appropriation and the availability of increment; (e) the Resolution remains in full force and effect and has not been repealed, modified, or judicially invalidated; and (f) there are no pending or, to the City’s knowledge, threatened litigation, governmental proceedings, or environmental enforcement actions affecting the Property that could reasonably be expected to have a material adverse effect on the Project.

[Drafting Note — Developer Position — City Representations: Developer should require robust City representations, including (i) good and marketable fee simple title to each parcel individually (given the differing acquisition histories flagged in Recital A), (ii) TIF availability (subject to the acknowledged increment-availability limitation), (iii) the continuing effectiveness of the Resolution (given the 7–2 vote and political risk), and (iv) no pending litigation or environmental enforcement. The Term Sheet (§18.1) provides for these representations. The “subject to annual appropriation and the availability of increment” qualifier on the TIF representation is a concern; Developer should seek the City’s good-faith covenant to seek a TIF extension (Section 4.2) to mitigate the increment-availability risk. OPEN ITEM.]

[Drafting Note — Open Item — Title Representation and Acquisition History: The City’s title representation must be reconciled with the conflict flagged in Recital A regarding the acquisition mechanism for Parcel 12-24-300-016 (tax forfeiture 2016 per the Resolution/Term Sheet/TIF memo/RFP vs. direct purchase 2018 per the Phase II ESA). The City should represent title to each parcel by reference to the recorded deed and chain of title, and the Permitted Exceptions schedule should reflect the actual recorded encumbrances on each parcel. OPEN ITEM.]

## ARTICLE 16. ASSIGNMENT AND CHANGE OF CONTROL

Section 16.1 Restriction on Assignment. Developer may not assign this Agreement or any interest herein, in whole or in part, without the prior written consent of the City, which consent may be withheld in the City’s reasonable discretion.

Section 16.2 Permitted Assignments. Notwithstanding Section 16.1, Developer may assign this Agreement without the City’s prior written consent to:

- an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds at least a fifty percent (50%) controlling interest and which entity expressly assumes in writing all of Developer’s obligations under this Agreement;

- an affiliate or entity controlled by Developer, or to a transferee in connection with a transfer of membership interests among the existing members of Developer (Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, and TransitWorks Equity Group LLC), in each case provided that Marcus J. Pellegrini continues to serve as Manager and Chief Executive Officer of Developer (or the assignee) and the Pellegrini Interest is not reduced below fifty percent (50%);

- a transferee in connection with a capital raise or financing that has been approved by the City (such approval not to be unreasonably withheld) and by Lakeshore Capital Partners Fund III LP under the Lakeshore Side Letter, provided that Marcus J. Pellegrini continues to serve as Manager and Chief Executive Officer of Developer (or the assignee); and

- a Construction Lender-designee or a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, as provided in Section 18.4.

Developer shall provide the City with written notice of any permitted assignment under subsections (a)–(c), together with a copy of the assignment and assumption agreement, within fifteen (15) days of the effective date of such assignment.

Section 16.3 Key Person Provision. The Parties acknowledge that the City’s selection of Developer was based, in substantial part, on the qualifications, experience, and financial capacity of Marcus J. Pellegrini. Marcus J. Pellegrini shall serve as Manager and Chief Executive Officer of Developer and shall exercise day-to-day management authority over the Project. If Marcus J. Pellegrini ceases to serve as Manager and Chief Executive Officer, Developer shall, within sixty (60) days, appoint a replacement reasonably acceptable to the City (such acceptance not to be unreasonably withheld), and such cessation shall not constitute an event of default during such sixty (60) day cure period.

Section 16.4 Change of Control. A “Change of Control” shall be deemed to occur if: (a) the Pellegrini Interest falls below fifty percent (50%) of the total membership interests in Developer; (b) Marcus J. Pellegrini ceases to serve as Manager and Chief Executive Officer of Developer and is not replaced by a person reasonably acceptable to the City within sixty (60) days; or (c) any single person or entity (other than the Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, or TransitWorks Equity Group LLC) acquires twenty-five percent (25%) or more of the membership interests in Developer. A Change of Control without the City’s prior written consent (such consent not to be unreasonably withheld, conditioned, or delayed) shall constitute a material default under this Agreement, subject to the cure provisions of Section 13.2.

Section 16.5 Void Assignments. Any purported assignment in violation of this Article 16 shall be void and of no force and effect.

[Drafting Note — Conflict — Change-of-Control and Assignment Thresholds: Three different ownership thresholds appear across the source documents:

- The Construction Loan Term Sheet (§8.1) defines a Change of Control as occurring if Marcus J. Pellegrini (directly or through the Pellegrini Family Trust) ceases to hold at least a [50]% direct or indirect ownership interest in Developer, and notes that the bracketed [50]% threshold is “subject to further discussion and negotiation between Borrower and Lender during definitive documentation.” The Lender also treats a Change of Control as an immediate Event of Default.

- The Term Sheet (§10) permits assignment without City consent only to an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds at least a 50% controlling interest.

- The Lakeshore Side Letter (§5.2) defines a Change of Control as occurring if the Pellegrini Interest falls below fifty-one percent (51%), and (§4.4) grants Lakeshore enhanced consent rights if the Pellegrini Interest falls below 51%.

These thresholds (50% Lender, 50% Term Sheet, 51% Lakeshore) must be harmonized. Developer’s position: the Agreement should adopt a single, consistent threshold. A 50% threshold (consistent with the Term Sheet and the Lender’s bracketed position) is more favorable to Developer than the 51% threshold in the Lakeshore Side Letter, because it provides more headroom for the anticipated later-phase capital raises (which the Lakeshore Side Letter §5.3 acknowledges may dilute the Pellegrini Interest below both thresholds). However, the Lakeshore Side Letter is a binding agreement between Developer and Lakeshore that Developer must honor, and the 51% threshold triggers Lakeshore’s enhanced consent and Change-of-Control remedies. The Agreement has been drafted at the 50% threshold for purposes of the City-facing assignment/change-of-control provisions, but Developer must reconcile the 50% (City/Lender) and 51% (Lakeshore) thresholds internally and ensure the Agreement’s provisions do not conflict with the Lakeshore Side Letter. OPEN ITEM — CRITICAL — harmonize the ownership thresholds across the Term Sheet, the Construction Loan Term Sheet, and the Lakeshore Side Letter.]

[Drafting Note — Open Item — Broader Permitted-Transfer Carve-Outs: The Term Sheet (§10) permits assignment only to an entity in which Pellegrini holds at least 50% controlling interest — a narrow carve-out that does not accommodate internal transfers among existing members or later-phase capital raises. The Lakeshore Side Letter (§8.3) requires the Agreement’s assignment and change-of-control provisions to include: (i) carve-outs for internal transfers of membership interests among existing members of Developer; (ii) carve-outs for capital raises approved by both Lakeshore and the City; (iii) a “Key Person” provision requiring Pellegrini’s active and material involvement as Manager and CEO as an alternative or supplement to rigid percentage-of-interest thresholds; and (iv) a reasonable cure period (not less than 60 days) before any assignment default is triggered. Section 16.2(b)–(c) and Section 16.3 incorporate these carve-outs and the Key Person provision, and Section 16.3/16.4 provide a 60-day cure period. Developer’s position: these broader carve-outs are necessary to accommodate the anticipated $58,400,000 later-phase capital raise and to avoid a change-of-control default upon dilution that is approved by the City and Lakeshore. OPEN ITEM — confirm City acceptance of the broader permitted-transfer carve-outs and the Key Person alternative to rigid percentage thresholds.]

## ARTICLE 17. CONDITIONS PRECEDENT

Section 17.1 Conditions Precedent to Execution of this Agreement. The execution of this Agreement shall be subject to the satisfaction or waiver of the following conditions precedent: (a) rezoning of the Property from M-2 to PD-TOD approved by the City Council and effective under applicable law; (b) parcel consolidation of the three parcels completed or authorized by the applicable county authority; (c) IEPA approval of the RAP for Parcel 12-24-300-016 under the VSRP; (d) Developer’s demonstration of committed equity of at least $85,000,000, in form and substance reasonably acceptable to the City; (e) approval of this Agreement by the Lakemont City Council; and (f) confirmation from First Prairie National Bank that this Agreement is in a form acceptable to the Construction Lender as a condition of the Construction Loan commitment.

Section 17.2 Conditions Precedent to Closing. The obligation of the Parties to close the conveyance of the Property shall be subject to the satisfaction or waiver of the following conditions precedent: (a) execution of this Agreement by both Parties and approval by the City Council; (b) completion of the rezoning of the Property from M-2 to PD-TOD; (c) completion or authorization of parcel consolidation; (d) IEPA approval of the RAP for Parcel 12-24-300-016 (and, with respect to Parcel 016, either the NFR Letter or evidence of VSRP enrollment with an approved RAP and an environmental escrow or insurance product satisfactory to the Construction Lender); (e) Developer’s demonstration of committed equity of at least $85,000,000; (f) Developer’s posting of the Phase I Performance Security; (g) issuance of an ALTA lender’s title insurance policy and an owner’s title insurance policy, in each case in form acceptable to Developer and the Construction Lender; (h) delivery of a current ALTA/NSPS land title survey; (i) delivery of an updated MAI appraisal; (j) delivery of all insurance certificates required under Article 8; (k) issuance of all necessary building permits and governmental approvals for Phase I construction; (l) execution of a GMP or stipulated-sum construction contract with a general contractor approved by the Construction Lender; and (m) execution of the Construction Loan Documents and funding of the Construction Loan (or substitute financing).

[Drafting Note — Conflict — Conditions Precedent Lists Differ: The Term Sheet contains two different lists of conditions precedent: Section 4 (conditions to Closing) and Section 18.2 (conditions to execution of the definitive Agreement). The lists are similar but not identical (e.g., §18.2 includes City Council approval of the definitive Agreement and Lender confirmation of acceptable form; §4 includes the $15,000,000 performance security). Resolution R-2025-017, Condition No. 2(e), requires that the rezoning AND parcel consolidation be completed, adopted by ordinance, and effective prior to the execution of the Development Agreement, while the Term Sheet §18.2 requires parcel consolidation to be “completed or authorized.” Section 17.1 (conditions to execution) and Section 17.2 (conditions to Closing) consolidate and reconcile these lists. Developer’s position: parcel consolidation should be required to be “completed or authorized” (not fully completed) as a condition to execution, with full completion required as a condition to Closing, to avoid delaying execution. OPEN ITEM — reconcile the conditions-precedent lists and the consolidation-completion stage.]

[Drafting Note — Conflict — IEPA RAP Approval Timing (Execution vs. Conveyance): Resolution R-2025-017, Condition No. 2(b), requires IEPA approval of the RAP prior to any conveyance of the Property or any portion thereof. The Term Sheet §18.2 lists IEPA approval of the RAP as a condition precedent to execution of the definitive Agreement. Section 17.1(c) carries the RAP approval as a condition to execution, and Section 17.2(d) carries it (with the NFR Letter alternative) as a condition to Closing. See also the drafting note to Section 5.8. OPEN ITEM — reconcile the stage at which IEPA RAP approval is required.]

[Drafting Note — Open Item — Circular Dependency (Loan Requires Agreement; Agreement Requires Lender Confirmation): The Construction Loan Term Sheet (§7.1) makes execution of a Development Agreement “in form and substance acceptable to [the] Lender” a condition precedent to closing the Construction Loan, while the Term Sheet §18.2(vi) and Section 17.1(f) make confirmation from First Prairie National Bank that the Agreement is in acceptable form a condition precedent to execution of the Agreement. This creates a circular dependency: the Lender will not commit until the Agreement is in acceptable form, and the Agreement is not executed until the Lender confirms acceptable form. Developer’s position: the practical resolution is for the Lender to review and approve the form of the Agreement (issuing a conditional confirmation) before execution, with the definitive Construction Loan closing to follow execution, as a condition to Closing (Section 17.2(m)). The Lender’s review right (Section 18.1) and the 15-business-day review period should be sequenced before execution. OPEN ITEM — confirm sequencing with the Construction Lender.]

## ARTICLE 18. LENDER PROTECTIONS

Section 18.1 Lender Review Right. This Agreement shall be delivered to the Construction Lender in draft form not less than fifteen (15) business days prior to its proposed execution date. This Agreement shall not be executed until the Construction Lender has confirmed in writing that it is in form and substance acceptable to the Construction Lender. The Construction Lender’s review shall not be unreasonably delayed.

Section 18.2 Lender Cure Rights. The Construction Lender shall have the right (but not the obligation) to receive prompt written notice of any Developer default under this Agreement and a reasonable opportunity to cure such default. The Construction Lender’s additional cure period shall be not less than thirty (30) days beyond Developer’s cure period for monetary defaults and not less than sixty (60) days beyond Developer’s cure period for non-monetary defaults, with such periods extended as necessary if the Construction Lender is diligently pursuing a cure that requires additional time (including time necessary to obtain possession of the Property through foreclosure or appointment of a receiver).

Section 18.3 Lender Consent to Amendments. No material amendment, modification, supplement, or termination of this Agreement shall be effective without the Construction Lender’s prior written consent, which shall not be unreasonably withheld, conditioned, or delayed.

Section 18.4 Foreclosure; Assignment to Lender-Designee. This Agreement shall permit assignment to a Construction Lender-designee or to a third-party purchaser at a foreclosure sale (or pursuant to a deed-in-lieu of foreclosure) without the City’s prior consent, or, if City consent is required, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within thirty (30) days of request.

Section 18.5 Subordination of City Interests. Any lien, encumbrance, or security interest that the City may hold or acquire in the Property (other than the completion-assurance mechanisms in Article 12, which are contractual and financial and not Defeasible Fee Interests) shall be subordinated to the Construction Lender’s first-priority mortgage pursuant to a subordination and intercreditor agreement in form and substance acceptable to the Construction Lender.

Section 18.6 Estoppel Certificates. The City shall deliver estoppel certificates to the Construction Lender upon reasonable request (not more than twice per calendar year), certifying the status of this Agreement, the existence or absence of any outstanding defaults, and such other customary matters as the Construction Lender may reasonably request.

Section 18.7 No Impairment of Lender Security. Nothing in this Agreement shall be construed to impair the Construction Lender’s first-priority mortgage and security interests in the Property, the assignment of leases and rents, the assignment of contracts (including this Agreement), the assignment of TIF Reimbursement rights, the assignment of permits and entitlements, the pledge of membership interests in Developer, or the assignment of the Phase I Performance Security, in each case as required by the Construction Loan Term Sheet (§4.1).

[Drafting Note — Lender Protections Required: The provisions of this Article 18 are required by the Construction Loan Term Sheet (§12) as conditions to the Construction Loan. The Construction Lender specifically requires: (a) no reversionary/defeasible interest (addressed in Article 12); (b) Lender cure rights (Section 18.2); (c) Lender consent to material amendments (Section 18.3); (d) subordination of City interests (Section 18.5); (e) foreclosure/deed-in-lieu assignment rights (Section 18.4); and (f) estoppel certificates (Section 18.6). These provisions must be acceptable to the Construction Lender and the City. The Construction Loan Term Sheet (§9, item 5) treats any material default by Developer under this Agreement that is not cured, or any termination of this Agreement by the City for any reason, as an Event of Default under the Construction Loan — accordingly, the City’s termination rights (Section 13.3) should be carefully scoped to avoid inadvertently triggering a loan default. OPEN ITEM — confirm City acceptance of the Lender protections and coordinate the City’s termination rights with the Construction Loan default triggers.]

## ARTICLE 19. DISPUTE RESOLUTION

Section 19.1 Negotiation. The Parties shall first attempt to resolve any dispute arising under or related to this Agreement through good-faith negotiation between the City Manager (or designee) and Developer’s CEO (or designee) for a period of thirty (30) days following written notice of the dispute by either Party.

Section 19.2 Mediation. If the dispute is not resolved through negotiation within the thirty (30) day period, the dispute shall be submitted to non-binding mediation before the Lakemont Mediation Center, or such other neutral mediator as the Parties may agree upon. The costs of mediation shall be shared equally by the Parties, and each Party shall bear its own attorneys’ fees.

Section 19.3 Binding Arbitration. If the dispute is not resolved through mediation within sixty (60) days following submission to the mediator, the dispute shall be submitted to final and binding arbitration administered under the Commercial Arbitration Rules of the American Arbitration Association, conducted by a single arbitrator with experience in real estate development matters. The venue for any mediation or arbitration shall be Cook County or Lake County, Illinois.

Section 19.4 Provisional Remedies. Nothing in this Article 19 shall prevent either Party from seeking temporary restraining orders, preliminary injunctions, or other provisional judicial relief where necessary to prevent irreparable harm, pending resolution of the dispute through the procedures set forth above.

Section 19.5 Governing Law. This Agreement shall be governed by and construed in accordance with the laws of the State of Illinois, without regard to conflict-of-laws principles.

[Drafting Note — Developer Position — Dispute Resolution: The Term Sheet (§17) provides a three-step dispute resolution process (negotiation, mediation, binding arbitration) with Illinois governing law and Cook County/Lake County venue. This is generally favorable to Developer as an efficient, private dispute-resolution mechanism. Developer should ensure that the arbitrator selection process is balanced and that the arbitration award is enforceable and final. The Construction Loan Term Sheet (§13) specifies Cook County, Illinois venue for loan-related litigation; the Agreement’s arbitration venue (Cook County or Lake County) is consistent. OPEN ITEM — confirm arbitrator selection mechanics and that the dispute-resolution provisions do not conflict with the Construction Loan Documents’ dispute-resolution provisions.]

## ARTICLE 20. MISCELLANEOUS

Section 20.1 Notices. All notices, demands, requests, consents, approvals, and other communications required or permitted under this Agreement shall be in writing and shall be deemed delivered upon personal delivery, upon the date of delivery by nationally recognized overnight courier, or three (3) business days following deposit in the United States mail, registered or certified, return receipt requested, postage prepaid, addressed as follows:

If to Developer: Granite City Development LLC, 900 West Monroe Street, Suite 2200, Chicago, IL 60607, Attn: Marcus J. Pellegrini, Manager and CEO; with a copy to Thornfield & Pratt LLP, 311 South Wacker Drive, Suite 5400, Chicago, IL 60606, Attn: Catherine M. Albrecht.

If to the City: City of Lakemont, Office of the City Manager, 200 Civic Center Drive, Lakemont, IL 60048, Attn: Gerald T. Fong, City Manager; with a copy to the Office of Corporation Counsel, City of Lakemont, 200 Civic Center Drive, Lakemont, IL 60048, Attn: Rebecca A. Sinclair, Esq.; and with a copy to Ashford, Keene & Mulvaney LLP, 150 North Michigan Avenue, Suite 3200, Chicago, IL 60601, Attn: Jonathan Ashford.

Either Party may change its notice address by providing written notice to the other Party.

Section 20.2 Entire Agreement. This Agreement, together with the Exhibits and Schedules hereto, constitutes the entire agreement between the Parties with respect to the subject matter hereof and supersedes all prior negotiations, representations, warranties, and understandings relating thereto, including the Term Sheet. In the event of any conflict between this Agreement and the Term Sheet, this Agreement shall control.

[Drafting Note — Open Item — Relationship to Lakeshore Side Letter: The Lakeshore Side Letter (§10.5) provides that, in the event of any conflict between the Side Letter and the Operating Agreement with respect to Project-related matters, the Side Letter controls. The Side Letter imposes obligations on Developer (Minimum IRR, consent rights, anti-dilution protections, Change-of-Control consequences) that are internal to Developer and its investors and are not obligations of the City. This Agreement should not conflict with the Lakeshore Side Letter. Developer must ensure that the Agreement’s assignment/change-of-control provisions (Article 16), the TIF and incentive provisions (Article 4), the environmental provisions (Article 5), and the performance-security provisions (Article 7) are compatible with the Lakeshore Side Letter’s consent requirements (e.g., Lakeshore consent for Material Amendments, changes to the TIF cap, abatement schedule, phasing timelines beyond 2035, environmental obligations exceeding $3,140,000, performance-security modifications, and assignment/change-of-control provisions). The Agreement should not be construed to require Developer to breach the Lakeshore Side Letter, and Developer’s consent obligations under the Side Letter should be satisfied before Developer agrees to any Material Amendment with the City. OPEN ITEM — ensure compatibility with the Lakeshore Side Letter.]

Section 20.3 Severability. If any provision of this Agreement, or the application thereof to any person or circumstance, is held invalid or unenforceable by a court or arbitrator of competent jurisdiction, such invalidity or unenforceability shall not affect other provisions or applications of this Agreement that can be given effect without the invalid or unenforceable provision or application, and to this end the provisions of this Agreement are severable.

Section 20.4 No Waiver. No waiver of any provision of this Agreement shall be effective unless in writing and signed by the Party against whom the waiver is to be enforced. No failure or delay by any Party in exercising any right shall operate as a waiver thereof.

Section 20.5 Counterparts; Electronic Signatures. This Agreement may be executed in any number of counterparts, each of which shall be deemed an original and all of which together shall constitute one and the same instrument. Signatures transmitted by electronic means shall be deemed original signatures.

Section 20.6 Amendments. This Agreement may be amended, modified, or supplemented only by a written instrument executed by both Parties (and, with respect to material amendments, by the Construction Lender pursuant to Section 18.3 and by Lakeshore Capital Partners Fund III LP pursuant to the Lakeshore Side Letter).

Section 20.7 Assignment of Agreement as Collateral. Notwithstanding Section 16.1, Developer may grant a collateral assignment of this Agreement and Developer’s rights hereunder (including TIF Reimbursement rights) to the Construction Lender as security for the Construction Loan, as required by the Construction Loan Term Sheet (§4.1), without the City’s consent, provided that the Construction Lender agrees to be bound by the terms of this Agreement in the event of enforcement of its collateral.

Section 20.8 TIF Compliance. Any use of tax increment financing revenues in connection with the Project shall comply in all respects with the TIF Act and the Lakemont Central TIF District Redevelopment Plan and Project as adopted by Ordinance No. 2019-42, as amended. All TIF-eligible redevelopment project costs shall be determined and reimbursed in accordance with applicable provisions of Illinois law and the terms of this Agreement.

Section 20.9 Prevailing Wage Compliance. All construction work performed pursuant to this Agreement that constitutes “public works” within the meaning of the Prevailing Wage Act shall be subject to the prevailing wage requirements of said Act, including record-keeping, reporting, and certification requirements, as provided in Section 8.1.

Section 20.10 Further Assurances. Each Party shall execute and deliver such further documents and instruments and take such further actions as may be reasonably necessary to carry out the purposes of this Agreement.

Section 20.11 Effective Date. This Agreement shall be in full force and effect from and after the Effective Date.

[Drafting Note — Open Item — Additional Miscellaneous Provisions: The definitive Agreement should also address: (a) the relationship between this Agreement and the PD-TOD zoning ordinance (the zoning standards should be consistent with the Project program); (b) the City’s obligation to cooperate in good faith with rezoning, consolidation, and permit issuance; (c) the form of the special warranty deed and the bill of sale for any personal property; (d) the form of the Affordable Housing Covenant (Section 9.4); (e) the form of any memorandum of agreement to be recorded (Section 12.3); (f) the intercreditor/subordination agreement with the Construction Lender (Section 18.5); (g) the form of the Phase I Performance Security and any control agreement with the Construction Lender (Section 7.1); and (h) the exhibits and schedules listed below. These should be attached or referenced as Schedules before execution. OPEN ITEM.]

## SIGNATURE PAGE

IN WITNESS WHEREOF, the Parties have executed this Development Agreement as of the Effective Date.

GRANITE CITY DEVELOPMENT LLC

By: _______________________________

Name: Marcus J. Pellegrini

Title: Manager and Chief Executive Officer

Date: _____________________________

CITY OF LAKEMONT, ILLINOIS

By: _______________________________

Name: Gerald T. Fong

Title: City Manager

Date: _____________________________

APPROVED AS TO FORM:

Rebecca A. Sinclair, Esq.

Corporation Counsel, City of Lakemont, Illinois

Date: _____________________________

[SEAL]

## EXHIBITS AND SCHEDULES

The following Exhibits and Schedules are attached to and incorporated into this Agreement:

- Schedule 2.7-1 — Site Plan

- Schedule 2.7-2 — Phasing Plan

- Schedule 2.7-3 — Project Budget

- Schedule 3.1 — Legal Description of the Property

- Schedule 3.3 — Permitted Exceptions

- Schedule 4.3 — City Off-Site Infrastructure Schedule

- Schedule 5.4 — Environmental Remediation Plan and Cost Estimate

- Schedule 7.1 — Form of Phase I Performance Security

- Schedule 8.3 — Insurance Requirements

- Schedule 9.4 — Form of Affordable Housing Covenant

- Schedule 12.1 — Completion Assurance Mechanism (Liquidated Damages and Repurchase Option)

- Schedule 12.3 — Form of Memorandum of Agreement

- Schedule 18.5 — Form of Subordination and Intercreditor Agreement

- Exhibit A — Phase II Environmental Site Assessment (Greenfield Environmental Consultants LLC, dated November 8, 2024)

- Exhibit B — Appraisal (Crossland Appraisal Services, dated January 15, 2025)

- Exhibit C — City Council Resolution No. R-2025-017 (adopted February 18, 2025)

- Exhibit D — Negotiated Term Sheet (dated January 22, 2025)

[Drafting Note — Open Item — Exhibits and Schedules: The Exhibits and Schedules listed above are referenced for completeness but are not yet prepared. Several Schedules (Site Plan, Phasing Plan, Project Budget, Legal Description, Permitted Exceptions, City Off-Site Infrastructure Schedule, Environmental Remediation Plan, Affordable Housing Covenant, Completion Assurance Mechanism, Memorandum of Agreement, and Subordination and Intercreditor Agreement) must be prepared, negotiated, and attached before execution. The Phase II ESA, Appraisal, Resolution, and Term Sheet are existing documents that should be attached as Exhibits. OPEN ITEM — prepare and attach all Exhibits and Schedules.]

## CONSOLIDATED SUMMARY OF CROSS-DOCUMENT CONFLICTS AND OPEN ITEMS

[Drafting Note — The following is a consolidated index of the cross-document conflicts and open items flagged throughout this draft, for ease of reference during negotiation. Each item is keyed to the source documents and the relevant Article of this Agreement.]

A. Parcel Acquisition History (Recital A; Article 15). Conflict: Resolution/Term Sheet/TIF memo/RFP state Parcels 015 & 016 acquired by tax forfeiture 2016 and Parcel 017 by direct purchase 2018; Phase II ESA states Parcel 016 was acquired by direct purchase 2018 (with 017). Affects chain of title and title representations. OPEN ITEM.

B. Individual Parcel Acreages (Recital A). Conflict: RFP states 3.8/4.1/4.8 acres; Phase II ESA states 4.2/4.1/4.4 acres. Total 12.7 acres consistent. Confirm by ALTA/NSPS survey. OPEN ITEM.

C. RFP Number (Recital D). Conflict: Term Sheet references “RFP No. 2024-CD-018”; RFP Response Narrative references “RFP No. 2024-CD-07.” Confirm. OPEN ITEM.

D. Affordable Unit Count (Article 9). Conflict: Term Sheet §3.5 states “at least 100 affordable units”; Term Sheet §12, Resolution Condition 2(g), and RFP state 106 units (20%). Resolution makes 20% a condition of approval. OPEN ITEM.

E. Equity Demonstration Trigger/Deadline (Article 6). Conflict: Resolution Condition 2(a) requires demonstration within 60 days of adoption (by April 19, 2025); Term Sheet §7 requires demonstration within 60 days of City Council approval of the definitive Agreement. OPEN ITEM.

F. Reversionary Interest / Clawback (Article 12) — CRITICAL. Conflict: Resolution Condition 2(h) requires a recorded reversionary interest (auto-revert if Phase I not Substantially Complete within 36 months of conveyance); Construction Loan Term Sheet §§4.2, 12 prohibits any reversionary/defeasible interest (would make the loan impossible to close); Lakeshore Side Letter §7(d) requires Investor consent for any clawback. Developer proposes alternative completion-assurance mechanism (performance security + liquidated damages + contractual repurchase option subordinate to the Construction Lender’s mortgage). Must be accepted by the City, the Construction Lender, and Lakeshore. OPEN ITEM — CRITICAL.

G. Reversion 36-Month Period vs. Phase I Substantial Completion Deadline (Article 12). Conflict: the 36-month reversion period (from conveyance) may expire before the Phase I Substantial Completion Deadline of September 30, 2028 and does not account for Force Majeure. OPEN ITEM.

H. Change-of-Control / Assignment Thresholds (Article 16) — CRITICAL. Conflict: Construction Loan Term Sheet §8.1 uses [50]% (bracketed, subject to negotiation); Term Sheet §10 uses 50%; Lakeshore Side Letter §5.2 uses 51%. Must be harmonized. OPEN ITEM — CRITICAL.

I. Assignment Carve-Outs (Article 16). Open Item: Term Sheet §10 narrow (Pellegrini ≥50% only); Lakeshore Side Letter §8.3 requires broader carve-outs (internal transfers, approved capital raises, Key Person provision, 60-day cure). OPEN ITEM.

J. Living Wage (Article 10). Conflict/Open Item: Resolution Condition 2(c)(ii) imposes $17.50/hour living wage on retail/hotel permanent employees; Term Sheet §9 silent. Applies to tenants’ employees — enforcement/responsibility allocation open. OPEN ITEM.

K. First-Source Hiring (Article 10). Conflict/Open Item: Resolution Condition 2(c)(iii) requires first-source hiring via Lakemont Workforce Center; Term Sheet §9 silent. Developer cannot guarantee tenant hiring decisions. OPEN ITEM.

L. Local Hiring: Goal vs. Requirement (Article 10). Conflict: Term Sheet §9 = good-faith goal (non-default); Resolution Condition 2(c)(i) = “not less than 35%.” OPEN ITEM.

M. Prevailing Wage Scope (Article 8). Open Item: Term Sheet §11.1/Resolution §8 = “all construction”; TIF memo recommends broad coverage; Developer may resist purely private components. OPEN ITEM.

N. TIF Cap Reachability (Article 4) — MAJOR. Open Item: TIF memo (City internal/privileged) indicates $48M may not be reachable ($38–42M with abatement; $21–25M worst-case). City wants “shortfall not a default”; Developer wants mutuality and good-faith extension covenant. OPEN ITEM — MAJOR.

O. TIF–Abatement Interaction (Article 4). Open Item: abatement reduces TIF increment. OPEN ITEM.

P. Land Write-Down vs. TIF Cap (Article 4). Open Item: whether $9.2M write-down is charged against the $48M cap. Developer position: separate. OPEN ITEM.

Q. City Infrastructure Funding Source (Article 4). Open Item: $12.5M from TIF (counts against cap) or general revenue. Developer position: general revenue, separate. OPEN ITEM.

R. Environmental Remediation Performer (Article 5). Open Item: who performs; City = primary responsible party; VSRP enrollment by purchaser common. OPEN ITEM.

S. Environmental Cost Overruns (Article 5). Open Item: GEC recommends 25–35% contingency; exposure $3.8–4.2M. Developer position: City bears overruns. OPEN ITEM.

T. Phased Conveyance (Article 3). Conflict/Open Item: Phase II ESA recommends conveying clean parcels first; Resolution Condition 2(b) requires IEPA RAP approval before any conveyance. OPEN ITEM.

U. NFR/Remediation Delay as Force Majeure (Article 11). Open Item: Phase II ESA recommends DA address whether NFR delay = force majeure/extension/default. Developer position: force majeure/extension. OPEN ITEM.

V. Force Majeure Cap (Article 11). Open Item: Term Sheet = 18 months aggregate; Developer proposes 24 months (or per-Phase). OPEN ITEM.

W. IEPA RAP Approval Timing (Articles 5, 17). Conflict: Term Sheet §18.2 = before DA execution; Resolution Condition 2(b) = before any conveyance; Construction Loan Term Sheet §7.1 = NFR Letter or VSRP enrollment + approved RAP + escrow/insurance before loan closing. OPEN ITEM.

X. Lender Protections (Article 18). Open Items: Lender cure rights, consent to amendments, subordination, foreclosure assignment, estoppel certificates, DA review (15 business days), no reversionary interest. Must be acceptable to City and Lender. OPEN ITEM.

Y. Performance Security for Later Phases (Article 7). Open Item: amounts for Phases II–IV to be established. OPEN ITEM.

Z. Community Center Conveyance (Article 2). Open Item: “fully furnished and equipped” / “at no additional cost” — specifications, FF&E, timing. OPEN ITEM.

AA. Hotel Brand (Article 2). Open Item: “to be determined.” OPEN ITEM.

BB. Architect/General Contractor (Article 2). Open Item: “to be finalized”; Construction Lender approval required. OPEN ITEM.

CC. Political Risk / Non-Unanimous Vote (Recital F). Open Item: Resolution adopted 7–2. OPEN ITEM.

DD. Non-Binding Commitments (Recital I; Article 6). Open Item: Construction Loan and Term Sheet are non-binding; financing-out condition needed. OPEN ITEM.

EE. TIF Reimbursement Priority (Article 4). Open Item: TIF memo recommends priority (environmental, infrastructure, Phase IV public, other). OPEN ITEM.

FF. Certified Cost Documentation (Article 4). Open Item: Clearmont to provide; City audit rights. OPEN ITEM.

GG. Phase II ESA Reliance (Article 5). Open Item: third-party reliance requires GEC reliance letter. OPEN ITEM.

HH. Substantial Completion Definition (Article 11). Open Item: Term Sheet “generally” CO/TCO; needs precise definition; consistency with Construction Loan Documents. OPEN ITEM.

II. Conditions Precedent Lists (Article 17). Conflict: Term Sheet §4 vs. §18.2 differ; Resolution Condition 2(e) requires rezoning + consolidation before execution. OPEN ITEM.

JJ. Developer Termination Rights (Article 13). Open Item: expand to include City failure to rezone/consolidate and TIF availability failure. OPEN ITEM.

KK. Indemnity Caps (Article 14). Open Item: Term Sheet silent; Developer seeks caps on its indemnity (except environmental, which City bears). OPEN ITEM.

LL. Insurance Limits (Article 8). Conflict: Term Sheet §11.3 CGL $10M/$20M; Construction Loan §5 CGL $10M/$25M + umbrella $25M. Higher (loan) standard governs. OPEN ITEM.

MM. Circular Dependency — Loan/Agreement (Article 17). Open Item: loan requires DA; DA execution requires Lender confirmation. Sequencing. OPEN ITEM.

NN. Compatibility with Lakeshore Side Letter (Article 20). Open Item: ensure Agreement does not conflict with Lakeshore Side Letter (Minimum IRR, consent rights, anti-dilution, Change-of-Control). OPEN ITEM.

[END OF DRAFT — PREPARED ON BEHALF OF GRANITE CITY DEVELOPMENT LLC — FOR NEGOTIATION]

[Drafting Note — General: This draft is prepared on behalf of Granite City Development LLC and reflects the Developer’s negotiating positions. Bracketed provisions and bracketed drafting notes are not operative contract text and are intended to guide negotiation. All dollar amounts, dates, deadlines, and defined terms should be confirmed against the source documents and finalized before execution. This draft should be reviewed by Developer’s counsel (Thornfield & Pratt LLP, Catherine M. Albrecht) and coordinated with the Construction Lender (First Prairie National Bank, Sandra L. Chen) and Lakeshore Capital Partners Fund III LP (Richard Dominguez) before circulation to the City.]