# DEVELOPMENT AGREEMENT

## LAKEMONT STATION COMMONS — MIXED-USE TRANSIT-ORIENTED DEVELOPMENT

DRAFT FOR NEGOTIATION — PREPARED ON BEHALF OF THE DEVELOPER

Privileged and Confidential — Attorney Work Product / Attorney-Client Communication

This draft Development Agreement is prepared by Thornfield & Pratt LLP on behalf of Granite City Development LLC (“Developer”) for negotiation with the City of Lakemont, Illinois (“City”). It reflects the principal business terms set forth in the Negotiated Term Sheet dated January 22, 2025, the conditional approval granted by City Council Resolution No. R-2025-017 (adopted February 18, 2025), and the Developer’s proposal submitted in response to the City’s Request for Proposals. Bracketed drafting notes throughout flag cross-document conflicts among the source materials and open items requiring resolution. Bracketed text in the body denotes terms to be confirmed or negotiated. This document is non-binding until executed by both parties and approved by the Lakemont City Council.

This DEVELOPMENT AGREEMENT (this “Agreement”) is made and entered into as of [●], 2025 (the “Effective Date”), by and between GRANITE CITY DEVELOPMENT LLC, an Illinois limited liability company (“Developer”), and the CITY OF LAKEMONT, ILLINOIS, an Illinois home rule municipality (“City”). Developer and City are each referred to herein as a “Party” and collectively as the “Parties.”

## RECITALS

A. The City is the owner of certain real property located at 1400–1550 Lakemont Station Boulevard, Lakemont, Illinois 60048, consisting of three parcels identified by Parcel Identification Numbers 12-24-300-015, 12-24-300-016, and 12-24-300-017, totaling approximately 12.7 acres (553,212 square feet) (the “Site”), formerly occupied by the Lakemont Ironworks manufacturing campus and situated immediately adjacent to the Lakemont Central Metra commuter rail station.

B. The City, through its Community Development Department, conducted a competitive Request for Proposals process for the redevelopment of the Site as a mixed-use transit-oriented development.

[Drafting Note — Cross-Document Conflict:** The RFP Response Narrative (dated December 16, 2024) identifies the solicitation as RFP No. 2024-CD-07, while the Negotiated Term Sheet (dated January 22, 2025) identifies it as RFP No. 2024-CD-018. City Council Resolution No. R-2025-017 does not state a number. The correct RFP number must be confirmed and stated consistently in the Recitals and the defined term “RFP.” **]

C. Developer submitted a proposal in response to the RFP and was selected as the preferred developer based upon its qualifications, experience, project proposal, and demonstrated financial capacity.

D. Developer and the City executed a non-binding Negotiated Term Sheet dated January 22, 2025 (the “Term Sheet”), setting forth the principal business terms for the development of the Project.

E. On February 18, 2025, the Lakemont City Council adopted Resolution No. R-2025-017 (the “Resolution”), which granted conditional approval for the Project and authorized the City Manager to negotiate and execute this Agreement, subject to the conditions set forth in the Resolution.

[Drafting Note — Open Item:** The Resolution was adopted by a vote of 7–2 (not unanimous). The two dissenting votes are a political-risk factor that may affect rezoning proceedings, any further City Council action, and public support. Developer should consider whether the Agreement should lock in the terms approved by the Resolution to minimize re-litigation of approved terms. **]

[Drafting Note — Open Item:** The Term Sheet (Section 18.2(v)) lists “Approval of the definitive Agreement by the Lakemont City Council” as a condition precedent to execution, while the Resolution (Section 2 and Section 4) authorizes the City Manager to negotiate and execute the Agreement upon satisfaction of the Resolution’s conditions and approval as to form by Corporation Counsel and outside counsel — without expressly requiring a separate Council vote on the definitive Agreement. Confirm whether a separate City Council vote on the executed Agreement is required, or whether the Resolution’s authorization is sufficient. This affects closing certainty. **]

F. Developer proposes to develop the Site as “Lakemont Station Commons,” a mixed-use, transit-oriented development to be constructed in four phases, as more particularly described in this Agreement.

G. The Parties intend that this Agreement, upon execution, supersede the Term Sheet in its entirety and constitute the binding, definitive agreement of the Parties with respect to the Project.

NOW, THEREFORE, in consideration of the mutual covenants and agreements set forth herein, and other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the Parties agree as follows.

## ARTICLE 1. DEFINITIONS

### Section 1.1 Defined Terms

As used in this Agreement, capitalized terms have the meanings set forth below or as otherwise defined in the body of this Agreement. Defined terms are intended to be consistent with, and to harmonize, the usage in the Term Sheet, the Resolution, and the Construction Loan Term Sheet (defined below) to the extent practicable.

“Affordable Unit” means a residential dwelling unit restricted to occupancy by households earning at or below sixty percent (60%) of Area Median Income, as more particularly described in Article 7.

“Agreement” means this Development Agreement, including all Recitals, Exhibits, and Schedules attached hereto, as the same may be amended in accordance with its terms.

“AMI” means Area Median Income, as published annually by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area, or any successor designation.

“City Council” means the City Council of the City of Lakemont, Illinois.

“Construction Lender” means First Prairie National Bank, and any successor construction lender or assignee permitted under the Construction Loan Documents.

“Construction Loan Documents” means the definitive loan agreements, mortgages, assignments, guaranties, and other instruments evidencing and securing the construction loan facility for the Project, as described in the Preliminary Construction Loan Term Sheet dated [March ●, 2025] issued by First Prairie National Bank (the “Construction Loan Term Sheet”).

“Construction Loan Term Sheet” has the meaning set forth in the definition of Construction Loan Documents.

“Developer’s Counsel” means Thornfield & Pratt LLP.

“ELUC” means an environmental land use control, in the form of a restrictive covenant recorded against all or a portion of the Site in connection with the IEPA Voluntary Site Remediation Program, as more particularly described in Article 5.

“Force Majeure” has the meaning set forth in Section 14.3.

“IEPA” means the Illinois Environmental Protection Agency.

“Lakemont Central TIF District” means the tax increment financing district established by City Ordinance No. 2019-42, expiring December 31, 2042, pursuant to the Illinois Tax Increment Allocation Redevelopment Act, 65 ILCS 5/11-74.4-1 et seq. (the “TIF Act”).

“NFR Letter” means a No Further Remediation letter issued by IEPA under the Voluntary Site Remediation Program.

“Permitted Exceptions” means the title exceptions to which Developer takes title to the Site at Closing, as set forth on Exhibit [●] and agreed upon by the Parties and the Construction Lender, as provided in Section 3.4.

“Phase I,” “Phase II,” “Phase III,” and “Phase IV” mean the four phases of the Project described in Section 2.2.

“Project” means the Lakemont Station Commons mixed-use transit-oriented development described in Article 2.

“RAP” means a Remedial Action Plan for the environmental remediation of Parcel 12-24-300-016, submitted to and approved by IEPA under the Voluntary Site Remediation Program.

“Resolution” means City Council Resolution No. R-2025-017, adopted February 18, 2025.

“Site” means the real property described in Recital A, to be consolidated into a single parcel as provided in Section 3.2.

“Substantial Completion” means, with respect to a phase, the completion of construction of that phase such that the building or improvements can be occupied and used for their intended purpose, as evidenced by the issuance of a temporary or final certificate of occupancy by the City’s Building Department for that phase, or, where a certificate of occupancy is not applicable (e.g., the public plaza), the completion of all improvements in accordance with the approved plans and specifications such that the improvement is available for its intended public use.

[Drafting Note — Open Item:** The Term Sheet (Section 13) states that Substantial Completion “shall be defined in the definitive Agreement” and generally means completion to the point of occupancy, evidenced by a temporary or final certificate of occupancy. The Construction Loan Term Sheet (Section 9, item 9) ties the Phase I Substantial Completion deadline to September 30, 2028. The definition above is drafted to be objective and Developer-favorable (temporary or final CO suffices; public-plaza completion measured by availability for intended use). Confirm the City accepts a temporary CO as satisfying Substantial Completion, and align the definition with the Construction Lender’s milestone testing. **]

“TIF Act” has the meaning set forth in the definition of Lakemont Central TIF District.

“VSRP” means the IEPA Voluntary Site Remediation Program.

### Section 1.2 Interpretation

The headings used in this Agreement are for convenience only and do not affect interpretation. References to “Sections,” “Articles,” “Exhibits,” and “Schedules” are to sections, articles, exhibits, and schedules of this Agreement unless otherwise stated. “Including” means “including without limitation.” References to statutes include the rules and regulations promulgated thereunder and any successor provisions.

## ARTICLE 2. THE PROJECT AND DEVELOPMENT PLAN

### Section 2.1 The Project Generally

Developer shall design, entitle, construct, and deliver the Project, a mixed-use, transit-oriented development consisting of approximately 1,620,000 gross square feet across four phases, with a total estimated hard construction cost of approximately $340,000,000 and a total estimated Project cost of approximately $412,000,000. The Project program is summarized in the table set forth in Section 2.3.

### Section 2.2 Phases

The Project shall be constructed in four phases as follows:

(a) Phase I — Residential Tower A and Retail Podium. Three hundred twenty (320) residential units (256 market-rate and 64 Affordable Units); 45,000 square feet of ground-floor retail; a 480-space structured parking garage; approximately 420,000 gross square feet; estimated hard construction cost of $105,000,000.

(b) Phase II — Office Building and Retail. 280,000 square feet of Class A office space; 18,000 square feet of retail; a 350-space structured parking garage; approximately 380,000 gross square feet; estimated hard construction cost of $76,000,000.

(c) Phase III — Residential Tower B and Hotel. Two hundred ten (210) residential units (168 market-rate and 42 Affordable Units); a 150-room select-service hotel; approximately 440,000 gross square feet; estimated hard construction cost of $88,000,000.

(d) Phase IV — Public Plaza, Community Center, and Public Parking Structure. A 2.5-acre public plaza; a 28,000-square-foot community center to be conveyed to the City upon completion as provided in Section 6.9; a 600-space public parking structure; approximately 380,000 gross square feet (parking structure and community center combined); estimated hard construction cost of $71,000,000.

### Section 2.3 Project Program Summary

| Component | Phase I | Phase II | Phase III | Phase IV | Total |
| --- | --- | --- | --- | --- | --- |
| Residential units | 320 | — | 210 | — | 530 |
| Affordable Units (≤60% AMI) | 64 | — | 42 | — | 106 |
| Office (sq ft) | — | 280,000 | — | — | 280,000 |
| Retail (sq ft) | 45,000 | 18,000 | — | — | 63,000 |
| Hotel (rooms) | — | — | 150 | — | 150 |
| Community center (sq ft) | — | — | — | 28,000 | 28,000 |
| Public plaza (acres) | — | — | — | 2.5 | 2.5 |
| Parking (spaces) | 480 | 350 | — | 600 | 1,430 |
| Gross building area (sq ft) | 420,000 | 380,000 | 440,000 | 380,000 | 1,620,000 |
| Hard construction cost | $105,000,000 | $76,000,000 | $88,000,000 | $71,000,000 | $340,000,000 |

[Drafting Note — Open Item:** The Term Sheet (Section 12) refers to “at least 100 affordable units” in its introductory text, while the breakdown and the Project totals (Section 3.5) and the RFP Response and the Resolution all reflect 106 Affordable Units (20% of 530 residential units). The Agreement adopts 106 units / 20%, which satisfies the “at least 100” floor. Confirm the City concurs that the binding requirement is 106 units (20%), not merely “at least 100.” **]

### Section 2.4 Development Plan and Exhibits

The Project shall be developed in accordance with the Development Plan set forth in Exhibit [●] (Site Plan and Phasing Plan), Exhibit [●] (Project Budget), Exhibit [●] (Form of Affordable Housing Restrictive Covenant), and the other Exhibits attached hereto. The Development Plan may be refined by Developer, subject to the design-review procedures in Section 6.2, provided that any refinement that materially changes the program metrics in Section 2.3 shall require City consent, not to be unreasonably withheld.

[Drafting Note — Open Item:** The Term Sheet (Section 19) contemplates exhibits including a site plan, phasing plan, project budget, and form of restrictive covenant for affordable housing. These exhibits are not yet prepared and must be developed and attached. The Construction Loan Term Sheet (Section 7.1, items 12–13) requires an executed GMP or stipulated-sum construction contract and an architect’s certification that Phase I plans are substantially complete as conditions to loan closing. Coordinate the Development Plan exhibits with the Construction Lender’s requirements. **]

## ARTICLE 3. LAND CONVEYANCE

### Section 3.1 Conveyance; Purchase Price

Following the Effective Date and satisfaction of the conditions precedent to Closing set forth in Article 13, the City shall convey the Site (as consolidated into a single parcel) to Developer by special warranty deed, free and clear of all liens, encumbrances, and exceptions except Permitted Exceptions. The purchase price for the Site shall be $9,200,000, representing fifty percent (50%) of the appraised as-is market value of $18,400,000 established by Crossland Appraisal Services in its appraisal report dated January 15, 2025. The purchase price shall be due and payable in cash at Closing. Developer may fund the purchase price from equity, construction loan proceeds, or a combination thereof.

### Section 3.2 Parcel Consolidation

The three parcels comprising the Site (PINs 12-24-300-015, 12-24-300-016, and 12-24-300-017) shall be consolidated into a single parcel of record prior to or concurrent with Closing. The City shall be responsible for effecting the consolidation, at the City’s expense, in coordination with the applicable county authority.

[Drafting Note — Open Item:** The Phase II ESA (Section 1.3) cautions that each parcel has a distinct chain of title arising from different acquisition mechanisms (Parcel 015 by tax forfeiture in 2016; Parcels 016 and 017 by direct purchase in 2018), which may give rise to different encumbrances, easement burdens, environmental liens, unresolved tax claims, or mechanic’s liens from the City’s prior demolition/clearing work. The ESA recommends a comprehensive per-parcel title review before consolidation. The Agreement should require the City to deliver, prior to consolidation, a title commitment and underlying title documents for each individual parcel, and to clear or insure over any parcel-specific encumbrances that would impair the consolidated parcel. **]

[Drafting Note — Open Item — Phased Conveyance:** Both the Phase II ESA (Section 5.2) and the Construction Loan Term Sheet (Section 7.1, item 7) contemplate that a phased conveyance may be feasible — conveying clean Parcel 015 and Parcel 017 (after the engineered barrier) to Developer first, while Parcel 016 is conveyed after issuance of the NFR Letter — so that Phase I construction can commence on the clean portions of the Site while Parcel 016 remediation proceeds. The Term Sheet and Resolution, by contrast, contemplate a single consolidated-parcel conveyance conditioned on RAP approval. Developer should reserve the right to request a phased conveyance, subject to coordination with the PD-TOD rezoning, consolidation, and the Construction Lender’s mortgage-scope requirements. **]

### Section 3.3 Title

The City shall deliver marketable and insurable fee simple title to the Site, free and clear of all liens, encumbrances, and exceptions except Permitted Exceptions, and shall provide a standard owner’s title insurance policy issued by a nationally recognized title insurance company in the amount of the purchase price. The City shall also cause the issuance of an ALTA lender’s title insurance policy in the amount of the Construction Loan, with such endorsements as the Construction Lender may reasonably require, as a condition to Closing.

[Drafting Note — Cross-Document Conflict — Reversionary Interest / Defeasible Fee (CRITICAL):** Resolution No. R-2025-017, Condition No. 8, requires Developer to grant the City a reversionary interest in the Site, such that if Phase I is not Substantially Complete within 36 months of the date of conveyance, fee simple title automatically reverts to the City (with a refund of the purchase price, net of damages), to be recorded against the Site at conveyance. The Construction Loan Term Sheet (Sections 4.2, 7.1, and 12) strictly prohibits any reversionary interest, right of re-entry, possibility of reverter, or defeasible fee in favor of the City, stating that such an interest would render Developer’s title uninsurable, subordinate the Construction Lender’s first-priority mortgage, prevent foreclosure, and “make the Loan impossible to close.” The Lakeshore Side Letter (Section 7(d)) likewise prohibits Developer from agreeing to any reversionary interest, right of re-entry, or repurchase option without Investor consent and requires terms compatible with the Construction Lender’s requirements. This Agreement is drafted WITHOUT any reversionary interest, and instead substitutes an alternative clawback mechanism in Section 9.3 that preserves Developer’s fee simple absolute title. This is the single most important open item and must be resolved with the City before the Agreement can be executed and the Construction Loan can close. **]

[Drafting Note — Cross-Document Conflict — 36-Month Reversion Trigger vs. Phase I Substantial Completion Deadline:** Even setting aside the lender’s prohibition, the Resolution’s 36-month-from-conveyance reversion trigger is inconsistent with the Term Sheet’s Phase I Substantial Completion deadline of September 30, 2028. The Term Sheet (Section 4) targets Closing in “mid-2025.” If Closing occurs in, e.g., June or July 2025, the 36-month reversion trigger would fire in mid-2028 — approximately three months BEFORE the contractual Phase I Substantial Completion deadline of September 30, 2028. The reversion trigger must be aligned with (or run later than) the Substantial Completion deadline, and must account for Force Majeure extensions. The alternative clawback in Section 9.3 is drafted to trigger only after the Phase I Substantial Completion deadline (as extended by Force Majeure) has passed and all cure periods have expired. **]

### Section 3.4 Permitted Exceptions

Permitted Exceptions shall be limited to: (a) real estate taxes not yet due and payable; (b) standard utility and access easements that do not materially interfere with the development, use, or value of the Project; (c) this Agreement; (d) covenants and restrictions of the PD-TOD zoning ordinance; (e) environmental use controls or institutional controls (including ELUCs) recorded in connection with the IEPA VSRP NFR Letter for Parcel 12-24-300-016 and the engineered barrier for Parcel 12-24-300-017, in each case as reviewed and approved by the Construction Lender’s counsel; (f) the Affordable Housing Restrictive Covenant; and (g) such other exceptions as Developer and the Construction Lender may approve in writing.

[Drafting Note — Cross-Document Conflict:** The Construction Loan Term Sheet (Section 4.2) enumerates Permitted Exceptions that are substantially consistent with the foregoing, but expressly excludes any reversionary interest, right of re-entry, possibility of reverter, or defeasible condition. The ELUCs referenced in (e) above will constitute title encumbrances (Phase II ESA, Sections 4.2.4, 4.3.3, and 6.2) and must be acceptable to the Construction Lender and the title company. The Affordable Housing Restrictive Covenant in (f) will likewise be an encumbrance and must be acceptable to the Construction Lender. Confirm the City will not insist on any title exception that the Construction Lender will not accept. **]

### Section 3.5 Closing

Closing shall occur within thirty (30) days following the satisfaction or waiver of all conditions precedent to Closing set forth in Article 13. The Parties’ target Closing date is [mid-2025], subject to the timing of rezoning, IEPA approvals, and the satisfaction of other conditions.

## ARTICLE 4. PUBLIC INCENTIVES

### Section 4.1 Land Write-Down

The sale of the Site at fifty percent (50%) of appraised as-is market value constitutes a land write-down incentive with a value of $9,200,000. The land write-down is a separate incentive and shall not be charged against, or counted toward, the TIF Reimbursement Cap (as defined in Section 4.2).

[Drafting Note — Cross-Document Conflict / Open Item:** The TIF District Summary Memo (Section VII) states that the land write-down “is itself an eligible TIF cost” and that “[i]f the City records it as a TIF expenditure from the Special Tax Allocation Fund, it counts against the $48 million cap,” recommending that the Agreement “clearly specify whether the land write-down is charged against the TIF cap or constitutes a separate incentive funded from another source.” The Term Sheet (Section 5.6) lists the land write-down as a separate incentive from the TIF reimbursement. Developer’s position, reflected above, is that the land write-down is a separate incentive and must NOT reduce the $48,000,000 TIF Reimbursement Cap. This must be confirmed with the City; if the City insists on charging the write-down against the cap, the effective TIF available to Developer drops by $9,200,000. **]

### Section 4.2 Tax Increment Financing

(a) Cap; Pay-As-You-Go. The City shall pledge up to $48,000,000 in tax increment financing revenues over the remaining life of the Lakemont Central TIF District (the “TIF Reimbursement Cap”) to reimburse Developer for eligible TIF costs incurred in connection with the Project. TIF reimbursement shall be on a pay-as-you-go basis: Developer shall front all eligible costs and shall be reimbursed annually from available TIF increment as generated by the Project and other developments within the Lakemont Central TIF District. The City shall not issue TIF bonds or notes for the Project.

(b) Eligible TIF Costs. Eligible TIF costs shall include, without limitation: public infrastructure improvements; environmental remediation costs; parking structure construction costs; the public plaza, community center, and public parking structure components of Phase IV; and other eligible project costs under the TIF Act and the Lakemont Central TIF District Redevelopment Plan. Private development costs (including market-rate and Affordable Unit residential construction, private office, retail, and hotel construction) are not eligible.

(c) No Guarantee; Availability. TIF reimbursement is subject to the availability of increment. The City does not guarantee that the full TIF Reimbursement Cap will be reached over the remaining life of the Lakemont Central TIF District.

(d) Priority of Reimbursement. Reimbursement from available increment shall be made in the following priority order: (i) first, environmental remediation costs (Section 5.5); (ii) second, Developer’s eligible on-site infrastructure costs and the City’s off-site infrastructure costs to the extent funded by Developer and seeking reimbursement; (iii) third, the public parking structure, public plaza, and community center costs of Phase IV; and (iv) fourth, all other eligible costs.

(e) City Good-Faith Covenant re Extension. If, as of December 31, 2038, cumulative TIF reimbursement is tracking materially below the projections supporting the TIF Reimbursement Cap, the City shall use good-faith efforts to pursue an extension of the Lakemont Central TIF District or the establishment of a successor TIF district, to the extent legally available, in order to maximize reimbursement of Developer’s eligible costs.

(f) Shortfall Not a City Default. A shortfall in TIF reimbursement resulting from the availability of increment, the expiration of the Lakemont Central TIF District, or the interaction with the Phase I property tax abatement shall not, in and of itself, constitute a default by the City under this Agreement.

[Drafting Note — Cross-Document Conflict / Open Item — TIF Reachability:** The TIF District Summary Memo (Section IV) projects that, on a base case without abatement impact, cumulative increment through 2042 reaches approximately $54.2 million (exceeding the cap), but on an adjusted case incorporating the Phase I property tax abatement, cumulative increment is estimated at only $38 million to $42 million — potentially $6 million to $10 million short of the $48,000,000 cap. Under a worst-case timing scenario (maximum permitted delays), full-buildout increment collection could be reduced to as little as $21 million to $25 million. Because Developer fronts all eligible costs and is reimbursed only as increment is generated, Developer bears the timing and shortfall risk. The provisions above (priority structure, City good-faith extension covenant, and the “shortfall is not a default” clause) reflect the City’s recommended positions (TIF Memo, Section VIII). Developer should evaluate whether to accept the “shortfall is not a default” clause or negotiate alternative recourse (e.g., a City obligation to seek extension as a covenant rather than mere good-faith efforts, or a make-whole mechanism). **]

[Drafting Note — Open Item — Abatement/TIF Interaction:** The TIF Memo (Sections IV.B and VIII.4) identifies an internal tension: the Phase I property tax abatement (Section 4.4) reduces the assessed value of Phase I improvements, which directly reduces the TIF increment generated by Phase I during the abatement years. The Memo suggests structuring the abatement to apply only to the non-TIF-captured portion of the tax bill, if legally permissible, to minimize the impact on TIF increment. Developer should pursue this structuring, or otherwise confirm that the overall incentive package remains sufficient notwithstanding the abatement/TIF trade-off. **]

### Section 4.3 Infrastructure Cost-Sharing

(a) City Commitment. The City shall fund $12,500,000 for off-site infrastructure improvements necessary to support the Project, including road widening and streetscape improvements on Lakemont Station Boulevard, a new traffic signal at the Oak Street/Lakemont Station Boulevard intersection, water main extension, and sanitary sewer upgrade. The City’s infrastructure funding shall be appropriated and disbursed according to the schedule set forth in Exhibit [●], coordinated with the phased construction timeline.

(b) Funding Source. The City’s $12,500,000 infrastructure commitment shall be funded from the City’s general revenue, capital improvement funds, or other non-TIF sources, and shall not be charged against, or counted toward, the TIF Reimbursement Cap.

(c) Developer Responsibility. Developer shall fund $8,300,000 for on-site infrastructure improvements, including internal roadways, utilities, stormwater management, pedestrian pathways, and landscape improvements within the Site. Developer’s on-site infrastructure costs are eligible TIF costs to the extent they serve a documented public purpose.

[Drafting Note — Cross-Document Conflict / Open Item — Infrastructure Funding Source:** The TIF Memo (Section VII) states that the City’s $12.5 million infrastructure commitment “counts against the cap” if funded from TIF, but does not reduce the cap if funded from general revenue or capital improvement funds, and recommends the funding source be specified in the Agreement. Developer’s position, reflected in Section 4.3(b), is that the City’s $12,500,000 must be funded from non-TIF sources and must NOT reduce the TIF Reimbursement Cap. Confirm the City’s funding source. The Term Sheet (Section 15(d)(b)) gives Developer a termination right if the City fails to fund its infrastructure obligations within the timelines; this is carried forward in Section 15.3. **]

### Section 4.4 Property Tax Abatement (Phase I)

The City shall provide a twelve (12)-year declining property tax abatement on Phase I improvements only, as follows: Years 1–4, 75% abatement; Years 5–8, 50% abatement; Years 9–12, 25% abatement; Year 13 and thereafter, 0% (full assessment). The abatement shall apply to the incremental increase in assessed value attributable to the Phase I improvements, measured from the pre-development base equalized assessed value. No property tax abatement is provided for Phase II, Phase III, or Phase IV.

[Drafting Note — Open Item:** The Term Sheet (Section 18.4) states that the parties’ positions regarding the financial structure of later phases, “including any additional incentives, shall be addressed during negotiation of the definitive Agreement.” Developer may seek abatement or other incentives for Phases II–IV. The abatement requires home-rule authority and may require the consent of overlapping taxing districts; the implementation mechanism should be confirmed. **]

### Section 4.5 Permit Fee Waiver

The City shall waive building permit fees for Phase I and Phase II of the Project, with an estimated combined value of $1,400,000 ($920,000 for Phase I and $480,000 for Phase II). The permit fee waiver is a separate incentive and shall not be charged against the TIF Reimbursement Cap. No permit fee waiver is contemplated for Phase III or Phase IV.

[Drafting Note — Open Item:** Developer may seek to extend permit fee waivers to Phases III and IV. The Term Sheet (Section 5.5) limits the waiver to Phases I and II. **]

### Section 4.6 Summary of Public Incentives

| Incentive | Value |
| --- | --- |
| Land write-down | $9,200,000 |
| TIF reimbursement (up to) | $48,000,000 |
| City infrastructure funding | $12,500,000 |
| Property tax abatement (Phase I, 12 years) | To be calculated based on actual assessed values |
| Permit fee waivers (Phases I & II) | $1,400,000 |

## ARTICLE 5. ENVIRONMENTAL MATTERS

### Section 5.1 Phase II ESA; Reliance

A Phase II Environmental Site Assessment was completed by Greenfield Environmental Consultants LLC, report dated November 8, 2024 (the “Phase II ESA”), covering all three parcels comprising the Site. The key findings are summarized in Section 5.2. Developer shall use commercially reasonable efforts to obtain reliance letters from Greenfield Environmental Consultants LLC permitting the City, the Construction Lender, and Developer’s equity investors to rely on the Phase II ESA.

[Drafting Note — Open Item:** The Phase II ESA (Section 9, Reliance) states that the report was prepared for the exclusive use of Developer and Developer’s Counsel, and that any reliance by third parties — including the City, First Prairie National Bank, and Lakeshore Capital Partners Fund III LP — requires execution of a reliance letter from Greenfield on terms acceptable to Greenfield. The Construction Loan Term Sheet (Section 7.1, item 7) requires environmental clearance satisfactory to the Construction Lender. Reliance letters should be obtained as part of closing diligence. **]

### Section 5.2 Environmental Conditions

(a) Parcel 12-24-300-015. No contaminants of concern detected above applicable IEPA residential or commercial remediation objectives. No further action required.

(b) Parcel 12-24-300-016. Petroleum hydrocarbon contamination (BTEX compounds) detected in soil and shallow groundwater across approximately 1.8 acres. In addition, trichloroethylene (TCE) was detected in soil and groundwater in the vicinity of the former metal finishing area, at concentrations above IEPA Tier 1 residential remediation objectives. Remediation is required under the IEPA VSRP. Estimated remediation cost: $2,800,000. Estimated remediation timeline: 14–18 months from IEPA approval of the RAP. An NFR Letter will be required prior to construction of improvements on the affected area.

(c) Parcel 12-24-300-017. Low-level metals contamination (primarily arsenic, lead, and chromium) detected in shallow fill soil. An engineered barrier consisting of a clean fill cap and an ELUC is required for residential use. Estimated cost: $340,000.

[Drafting Note — Cross-Document Conflict — TCE Contamination:** The Term Sheet (Section 6) describes Parcel 016 contamination as “petroleum hydrocarbon contamination (BTEX compounds)” only. The Phase II ESA (Sections 4.2.2 and 4.2.3) identifies TCE (a chlorinated solvent) contamination in both soil and groundwater on Parcel 016, at concentrations above the IEPA Tier 1 residential remediation objective and the Class I groundwater quality standard. The Agreement’s environmental provisions (including the City’s indemnity in Section 5.6) are drafted to cover all pre-existing contamination, including BTEX, TCE, metals, and any other contaminants of concern, not merely BTEX. Confirm the City’s indemnity expressly covers TCE and any other pre-existing contaminants disclosed or discovered. **]

[Drafting Note — Open Item — Cost Overruns:** The Phase II ESA (Sections 4.2.4 and 5.3) recommends that project budgeting include an additional contingency of 25% to 35% above the base estimate, bringing the potential total cost exposure for Parcel 016 remediation alone to approximately $3.5 million to $3.8 million, and the combined total to approximately $3.8 million to $4.2 million (versus the $3,140,000 base estimate). The ESA further recommends that the transactional documents “clearly address the responsibility for funding such overruns.” Section 5.5 allocates overrun risk to the City. Confirm the City accepts overrun responsibility for pre-existing contamination. **]

[Drafting Note — Open Item — Vapor Intrusion:** The Phase II ESA (Sections 7.1 and 8.1) recommends a vapor intrusion screening evaluation for Parcel 016 (including soil gas sampling within proposed building footprints) and, if warranted, vapor mitigation measures (sub-slab depressurization, vapor barriers, passive venting) incorporated into building design. Vapor intrusion evaluation and mitigation costs are not included in any cost estimate. Section 5.5 treats these as environmental remediation costs borne by the City. Confirm. **]

[Drafting Note — Open Item — Off-Site Groundwater Monitoring:** The Phase II ESA (Section 8.3) recommends installation of at least two off-site groundwater monitoring points in the downgradient direction, on or adjacent to the Lakemont Central Metra station property, requiring coordination with Metra for access. The Agreement should specify which Party is responsible for coordinating Metra access; Developer’s position is that the City should assist, given Metra’s status as a public agency. **]

### Section 5.3 Remediation Responsibility and Performance

The City shall be responsible for performing, or causing to be performed, and for funding, the environmental remediation of Parcel 12-24-300-016 (including the BTEX and TCE contamination) and the engineered barrier installation on Parcel 12-24-300-017, in each case in accordance with the RAP and the Phase II ESA recommendations. Alternatively, at Developer’s election, Developer may perform the remediation as the VSRP applicant, in which case the City shall reimburse Developer for all remediation costs (including cost overruns as provided in Section 5.5) as a first-priority TIF-reimbursable cost and/or from non-TIF City funds. The Party performing the remediation shall engage Greenfield Environmental Consultants LLC (or a mutually acceptable successor) and shall be responsible for regulatory interaction with IEPA.

[Drafting Note — Open Item — Performance Responsibility:** The Phase II ESA (Section 8.2(a)) recommends that the transactional documents “clearly identify which party — the Developer or the City — will be responsible for performing or contracting for the remediation,” noting that the City, as the property owner at the time of contamination awareness, “bears primary responsible-party status under the Illinois Environmental Protection Act.” The Term Sheet (Section 6) does not clearly allocate performance responsibility. The provision above gives Developer the option to perform (with City funding) or to require the City to perform. Confirm the City’s position. **]

### Section 5.4 Regulatory Pathway; NFR Letter; Conditions

(a) VSRP Enrollment and RAP. The VSRP applicant shall enroll Parcel 12-24-300-016 in the IEPA VSRP and shall prepare and submit the RAP for IEPA review and approval. IEPA approval of the RAP for Parcel 12-24-300-016 shall be a condition precedent to Closing, as provided in Section 13.1.

(b) NFR Letter. An NFR Letter shall be obtained for Parcel 12-24-300-016 prior to construction of improvements on the affected area of that parcel. The NFR Letter (and the engineered barrier and ELUC for Parcel 017) shall be obtained prior to any Construction Loan draw-down for construction activities on the affected parcel, as required by the Construction Loan Term Sheet.

(c) Alternative to NFR Letter at Closing. Notwithstanding the foregoing, satisfaction of the environmental condition precedent to Closing may be achieved by either (i) an NFR Letter for Parcel 016, or (ii) evidence of VSRP enrollment with an approved RAP, together with an environmental escrow or insurance product satisfactory to the Construction Lender sufficient to cover the estimated remediation costs plus a 25% contingency.

[Drafting Note — Cross-Document Conflict — NFR Letter vs. RAP Approval as Condition Precedent:** The Term Sheet (Section 4, condition (iv)) and the Resolution (Condition No. 3(b)) require IEPA approval of the RAP (not the NFR Letter) as the condition precedent to conveyance, while the Term Sheet (Section 6) separately requires the NFR Letter “prior to construction of improvements on the affected area.” The Construction Loan Term Sheet (Section 7.1, item 7) permits either an NFR Letter or VSRP enrollment with an approved RAP plus an environmental escrow/insurance product ($2.8 million plus 25% contingency = $3.5 million). The provision above harmonizes these by making RAP approval (or the alternative in (c)) the condition to Closing, and the NFR Letter the condition to construction on the affected area. **]

[Drafting Note — Open Item — Remediation Timeline vs. Phase I Groundbreaking:** The Phase II ESA (Section 5.2) estimates the NFR Letter for Parcel 016 will be obtained 14 to 18 months from VSRP enrollment; if enrollment begins in the first quarter of 2025, the NFR Letter could be obtained in the second to fourth quarter of 2026. The Phase I groundbreaking deadline is March 1, 2026 (Term Sheet, Section 3.1). The ESA notes that this timeline is consistent with the groundbreaking deadline only if (a) Phase I construction is staged to begin on the clean portions of the Site (Parcels 015 and 017) while Parcel 016 remediation proceeds concurrently, or (b) the Phase I building footprint does not extend onto the contaminated portion of Parcel 016. The Agreement should expressly permit Phase I construction to commence on clean portions of the Site before the NFR Letter for Parcel 016 is issued, and should treat delay in NFR Letter issuance as a Force Majeure event or a basis for deadline extension (see Section 14.3). **]

### Section 5.5 Cost Allocation; Overruns

The City shall bear all environmental remediation costs for pre-existing contamination on the Site, including the base estimates of $2,800,000 (Parcel 016) and $340,000 (Parcel 017), and all cost overruns above those estimates, including overruns resulting from discovery of additional contamination, expanded excavation scope, extended groundwater treatment, supplemental regulatory requirements, vapor intrusion evaluation and mitigation, and off-site groundwater monitoring. Environmental remediation costs are eligible TIF costs and shall be reimbursed on a first-priority basis as provided in Section 4.2(d). To the extent Developer advances remediation costs, Developer shall be entitled to TIF reimbursement and/or direct City funding of overruns.

[Drafting Note — Open Item:** The TIF District Summary Memo (Section VI.B) recommends environmental remediation be first priority for TIF reimbursement, “align[ed] with the City’s interest in ensuring contamination is addressed promptly and mitigat[ing] the City’s indemnification exposure for pre-existing environmental conditions.” Developer’s position is consistent with first-priority reimbursement. The cost-overrun allocation to the City reflects the pre-existing nature of the contamination and the City’s responsible-party status (Phase II ESA, Section 4.2.4). **]

### Section 5.6 City Environmental Indemnity

The City shall indemnify, defend, and hold harmless Developer, its members, managers, officers, employees, agents, contractors, and successors, from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to pre-existing environmental conditions on the Site (including, without limitation, the BTEX and TCE contamination on Parcel 016, the metals contamination on Parcel 017, vapor intrusion, off-site migration, and any contamination discovered during remediation or construction), including third-party claims, governmental enforcement actions, and contribution or cost-recovery actions under federal or state environmental laws. This indemnity is in addition to (and not limited by) the City’s remediation cost obligations in Section 5.5, is not capped, and shall survive the expiration or termination of this Agreement.

[Drafting Note — Open Item:** The Term Sheet (Section 16) provides a City environmental indemnity for pre-existing conditions, and the Phase II ESA confirms the contamination is pre-existing and attributable to the former Lakemont Ironworks (which ceased operations in 2009), with the City having acquired Parcels 016 and 017 in 2018 with knowledge of the environmental conditions. Developer’s position is that the City’s environmental indemnity should be broad (covering all pre-existing contaminants, including TCE), uncapped, and surviving. Confirm the City will not seek to cap the indemnity or limit it to BTEX only. **]

### Section 5.7 Institutional Controls

Any ELUC or institutional control recorded against the Site in connection with the VSRP or the engineered barrier shall be a Permitted Exception, shall be reviewed and approved by the Construction Lender’s counsel prior to recording, and shall be referenced in the consolidation plat by legal description. The PD-TOD development standards shall account for the engineered barrier on Parcel 017 by restricting below-grade construction in the barrier area unless proper environmental protocols are followed.

## ARTICLE 6. DEVELOPMENT OBLIGATIONS AND CONSTRUCTION STANDARDS

### Section 6.1 General Development Obligation

Developer shall design, construct, and deliver the Project in accordance with this Agreement, the Development Plan, the PD-TOD zoning, and applicable law, in four phases and in accordance with the phasing and timelines set forth in Article 14.

### Section 6.2 Design Review and Approval

Developer shall submit plans and specifications for each phase to the City’s Community Development Department for design review. The City shall review and respond within [thirty (30)] business days of submission. City approval shall not be unreasonably withheld, conditioned, or delayed, and shall be deemed granted if the City does not respond within the review period. The City’s design review shall be limited to consistency with the Development Plan, the PD-TOD zoning standards, and applicable codes, and shall not extend to aesthetic matters within Developer’s discretion.

[Drafting Note — Open Item:** The Term Sheet (Section 19) contemplates “design review and approval procedures” and “construction monitoring” in the definitive Agreement, but does not specify the review period, the scope of review, or a deemed-approval mechanism. The deemed-approval provision above is Developer-favorable and should be confirmed with the City. **]

### Section 6.3 Prevailing Wage

(a) Scope. All construction work performed on the Project that constitutes “public works” within the meaning of the Illinois Prevailing Wage Act, 820 ILCS 130/0.01 et seq. (the “Prevailing Wage Act”), shall comply with the Prevailing Wage Act. Without limiting the foregoing, prevailing wage shall apply to: (i) the off-site public infrastructure improvements funded by the City; (ii) on-site infrastructure improvements to the extent TIF-reimbursed; (iii) environmental remediation to the extent TIF-reimbursed; and (iv) the Phase IV public parking structure, public plaza, and community center.

(b) Good-Faith Dispute as to Private Components. The Parties acknowledge that the applicability of the Prevailing Wage Act to purely private components of the Project (including market-rate residential, private office, retail, and hotel construction) is a matter of statutory interpretation that may be debatable. To the extent the Prevailing Wage Act is determined by a court or the Illinois Department of Labor to apply to such private components by operation of law, Developer shall comply. Except as required by law, this Agreement shall not be construed as a voluntary contractual expansion of prevailing wage obligations beyond the statutory scope.

[Drafting Note — Cross-Document Conflict — Prevailing Wage Scope:** The Term Sheet (Section 11.1) states that prevailing wages shall apply to “all construction performed on the Project,” which the TIF District Summary Memo (Section V.B) notes “converts a potentially debatable statutory question into an unambiguous contractual obligation” and “may increase construction costs for components — such as market-rate residential units, private office space, and the hotel — that might otherwise be argued to fall outside the statutory mandate.” The TIF Memo (Section V.B) further notes that the City’s “strongest position is the broad interpretation” while “the Developer’s counsel will likely resist the scope of coverage for purely private components.” Developer’s position, reflected above, is to limit the contractual prevailing wage obligation to the statutory public-works scope and to resist a voluntary contractual expansion to purely private components. This is a significant cost issue and a key negotiation point. The Resolution (Section 8) references prevailing wage for “public works.” **]

(c) Compliance Mechanics. Developer shall include prevailing wage requirements in all construction contracts and subcontracts for work subject to the Prevailing Wage Act, shall maintain certified payroll records and make them available to the City and the Illinois Department of Labor upon request, and shall post prevailing wage rate schedules at the construction site.

### Section 6.4 LEED Certification

(a) Standard. All buildings within the Project shall be designed and constructed to achieve LEED Gold certification (or an equivalent green building certification approved by the City in writing) as administered by the U.S. Green Building Council. Developer shall register each building with the U.S. Green Building Council prior to commencement of construction of that building.

(b) Good-Faith Pursuit. Developer’s obligation is to design and construct each building to LEED Gold standards and to pursue LEED Gold certification in good faith. Because certification is determined by a third party (the U.S. Green Building Council) and depends on factors outside Developer’s reasonable control, Developer does not guarantee achievement of certification. If certification is not achieved, Developer shall provide the City with a report detailing the status of the certification process and any deficiencies, and shall use commercially reasonable efforts to cure curable deficiencies.

[Drafting Note — Open Item:** The Term Sheet (Section 11.2) and the Resolution (Condition No. 3(f)) require all buildings to “achieve LEED Gold certification,” but the Term Sheet also contemplates a report on deficiencies if certification is not achieved — implying that strict certification is not an absolute guarantee. The Construction Loan Term Sheet (Section 6.1) requires buildings to be “designed and constructed to achieve LEED Gold certification or an equivalent green building standard.” Developer’s position is that the obligation is to design and construct to LEED Gold standards and pursue certification in good faith, not to guarantee third-party certification. The “or equivalent” language provides additional flexibility. Confirm the City accepts a good-faith-pursuit standard and that failure to achieve certification (despite good-faith efforts) is not an uncured default. **]

### Section 6.5 Insurance

Developer shall maintain, or cause its general contractor to maintain, throughout the construction period for each phase, the following minimum insurance coverages: (a) Commercial General Liability (CGL) of $10,000,000 per occurrence and $25,000,000 in the aggregate; (b) Umbrella/Excess Liability of $25,000,000 per occurrence and in the aggregate; (c) Builder’s Risk on an all-risk basis at full replacement value of each phase under construction; (d) Workers’ Compensation at statutory limits; (e) Automobile Liability of $5,000,000 combined single limit; (f) Professional Liability (Architect/Engineer) of $5,000,000; and (g) Pollution Legal Liability of $10,000,000. The City and the Construction Lender shall each be named as additional insured (and, as to Builder’s Risk and Pollution Legal Liability, as loss payee) as their interests may appear. All carriers shall be rated A- VII or better by A.M. Best or an equivalent rating organization. All policies shall provide at least thirty (30) days’ prior written notice to the City and the Construction Lender of cancellation, non-renewal, or material modification.

[Drafting Note — Cross-Document Conflict — Insurance Limits:** The Term Sheet (Section 11.3) requires CGL of $10,000,000 per occurrence and $20,000,000 in the aggregate, while the Construction Loan Term Sheet (Section 5) requires CGL of $10,000,000 per occurrence and $25,000,000 in the aggregate. The Construction Loan Term Sheet also requires Professional Liability of $5,000,000 and Pollution Legal Liability of $10,000,000, which the Term Sheet does not mention. The Agreement adopts the higher/more comprehensive requirements (CGL $25,000,000 aggregate; Professional Liability $5,000,000; Pollution Legal Liability $10,000,000) to satisfy the Construction Lender. The Phase II ESA (Section 4.2.4) and the Construction Loan Term Sheet (Section 4.3) both support pollution legal liability insurance. Confirm the City accepts the higher limits and the additional coverages. **]

### Section 6.6 Construction Monitoring; Budget

Developer shall construct the Project in accordance with plans and specifications approved by the City (under Section 6.2) and the Construction Lender. Developer shall maintain a construction budget that includes a minimum 5% hard-cost contingency for each phase. Developer shall provide the City with quarterly construction progress reports, including percentage of completion, updated schedule, and identification of delays or anticipated deviations, within thirty (30) days following the end of each calendar quarter.

[Drafting Note — Open Item:** The Construction Loan Term Sheet (Section 6.1) requires a Lender-approved construction budget with a minimum 5% hard-cost contingency per phase and provides that no material change orders (individually exceeding $500,000 or in aggregate exceeding $2,500,000 per phase) shall be implemented without the Construction Lender’s prior written consent, and that the Construction Lender shall employ an independent construction monitor at Developer’s expense. The Term Sheet (Section 13) requires quarterly progress reports. The TIF District Summary Memo (Section V.C) recommends monthly certified payroll records. Reporting frequencies differ across documents (monthly certified payroll, quarterly progress reports, monthly draw requests). Developer should seek to harmonize reporting to avoid duplicative burden. **]

### Section 6.7 Construction Contracts

Developer shall enter into a Guaranteed Maximum Price (GMP) or stipulated-sum construction contract with a qualified general contractor for each phase, in form acceptable to the Construction Lender.

[Drafting Note — Open Item:** The Construction Loan Term Sheet (Section 7.1, item 12) requires an executed GMP or stipulated-sum construction contract with a Construction Lender-approved general contractor as a condition to loan closing. The Term Sheet does not address construction-contract form. Confirm the City does not impose additional construction-contract requirements beyond the Construction Lender’s. **]

### Section 6.8 Sustainability Design Features

The Project shall incorporate the sustainability design features described in the Development Plan, including, without limitation, electric vehicle charging stations at a minimum of 10% of all parking spaces, bicycle storage at a minimum of one space per two residential units, and dedicated bicycle parking at commercial building entrances, to the extent consistent with LEED Gold standards.

[Drafting Note — Open Item:** The RFP Response (Section 4.1) committed to specific sustainability features (EV charging at 10% of spaces; bicycle storage at one per two units). The Term Sheet (Section 11.2) addresses LEED Gold but does not specify these features. The Agreement incorporates them as design features consistent with LEED Gold. Confirm the City accepts these as design guidelines rather than rigid minimums that could conflict with LEED optimization. **]

### Section 6.9 Community Center Conveyance

The 28,000-square-foot community center shall be designed in consultation with the City’s Parks and Recreation Department, in accordance with a program and budget agreed upon by the Parties and set forth in Exhibit [●]. Upon Substantial Completion of Phase IV, Developer shall convey the community center to the City in fee simple, in the agreed-upon condition (building shell and core, with the agreed fit-out), at no additional cost to the City. The conveyance shall be subject to the City’s acceptance and to the City’s assumption of operation and maintenance.

[Drafting Note — Cross-Document Conflict — Community Center Scope:** The Term Sheet (Section 3.4) describes the community center as “to be designed in consultation with the City’s Parks and Recreation Department and conveyed to the City upon completion at no additional cost.” The RFP Response (Section 5.5) describes the community center as “to be designed to City specifications and conveyed to the City upon completion, fully furnished and equipped per the agreed-upon specifications.” “In consultation with” (Term Sheet) is more favorable to Developer than “to City specifications” (RFP), and “at no additional cost” (Term Sheet) is more favorable than “fully furnished and equipped” (RFP). Developer’s position is that the design is collaborative (with an agreed program and budget), and the conveyance condition is the agreed fit-out, not an open-ended “fully furnished and equipped” obligation. Confirm the scope and budget of the conveyance obligation. **]

## ARTICLE 7. AFFORDABLE HOUSING

### Section 7.1 Affordable Units

Developer shall include 106 Affordable Units across the Project (64 in Phase I and 42 in Phase III), representing twenty percent (20%) of the 530 total residential units, with rents restricted to households earning at or below 60% of AMI.

### Section 7.2 Distribution and Quality

Affordable Units shall be distributed proportionally across unit types (studio, one-bedroom, and two-bedroom) and shall not be segregated or concentrated on particular floors or in separate wings. Affordable Units shall be comparable in design, finishes, and amenity access to market-rate units within the same building, subject to reasonable variations consistent with industry practice.

### Section 7.3 Affordability Restriction Period

Affordability restrictions shall remain in effect for a minimum period of thirty (30) years from the date of issuance of the certificate of occupancy for the applicable phase. The affordability restrictions shall be memorialized by a restrictive covenant (the “Affordable Housing Restrictive Covenant”) recorded against the applicable parcel and running with the land, in the form set forth in Exhibit [●]. The Affordable Housing Restrictive Covenant shall be a Permitted Exception and shall be acceptable to the Construction Lender.

### Section 7.4 Compliance and Reporting

Developer shall comply with the City’s Affordable Housing Compliance Program and shall provide annual income certification documentation to the City’s Community Development Department for all Affordable Units throughout the affordability restriction period.

[Drafting Note — Open Item:** The 30-year affordability restriction and the recorded Affordable Housing Restrictive Covenant will be a long-term encumbrance on the residential parcels and must be acceptable to the Construction Lender as a Permitted Exception. The annual income certification and reporting obligation is an ongoing administrative burden; Developer should confirm the scope and frequency of reporting and seek to align it with other reporting obligations. **]

## ARTICLE 8. COMMUNITY BENEFITS

### Section 8.1 Local Hiring Goal

Developer shall use commercially reasonable efforts to achieve a goal of 35% Lakemont residents for construction workforce employment across all phases of the Project, measured on a cumulative project-wide basis and encompassing both direct employees and employees of general contractors, subcontractors, and material suppliers performing construction work on the Site. Developer shall submit quarterly reports to the City’s Community Development Department documenting local hiring percentages, within thirty (30) days following the end of each calendar quarter during which active construction is occurring.

### Section 8.2 Good-Faith Compliance; No Default for Goal Shortfall

Failure to achieve the 35% local hiring goal in any given quarter or on a cumulative basis shall not, in and of itself, constitute a default under this Agreement, provided that Developer demonstrates good-faith efforts to achieve the goal, including at minimum posting job openings with the City’s workforce development partners, attending local job fairs, and providing reasonable notice of hiring opportunities to the Community Development Department.

[Drafting Note — Cross-Document Conflict — Local Hiring Measurement and Default Consequence:** The Term Sheet (Section 9) measures the 35% goal by “workforce employment” (headcount) and provides that failure to achieve the goal is not a default (good-faith compliance only). The Resolution (Condition No. 3(c)(i)) measures the goal by “construction labor hours” performed by Lakemont residents. Headcount and labor-hours are different metrics. The Agreement adopts the Term Sheet’s headcount metric and good-faith/no-default formulation, which is Developer-favorable. Confirm the City accepts headcount measurement and the no-default formulation. **]

### Section 8.3 First-Source Hiring Program

Developer shall implement a first-source hiring program in partnership with the Lakemont Workforce Center, whereby the Workforce Center will serve as the initial referral source for construction positions generated by the Project. Developer and its general contractor shall notify the Lakemont Workforce Center of available construction positions prior to broader recruitment.

### Section 8.4 Living Wage; Permanent Positions

[Drafting Note — Cross-Document Conflict — Living Wage and First-Source Hiring for Permanent Positions (SIGNIFICANT):** The Resolution (Condition No. 3(c)) requires the Development Agreement to incorporate a Community Benefits Agreement or community benefits provisions requiring, at minimum: (i) the 35% local hiring goal for construction; (ii) a living wage requirement mandating that all permanent employees employed at retail establishments and hotel operations within the Project be compensated at not less than $17.50 per hour; and (iii) a first-source hiring program for permanent employment positions created within the Project. Neither the living wage requirement nor the first-source hiring program for permanent positions appears in the Term Sheet (Section 9), which addresses only construction local hiring. The RFP Response (Section 6.2) mentions a first-source hiring program for “both construction and permanent positions” but does not mention a living wage. The living wage and permanent-position first-source obligations are new obligations not bargained for in the Term Sheet. Developer’s positions: (a) Developer does not control the employment practices of its retail and hotel tenants, and any living wage/first-source obligations as to permanent positions should be imposed on tenants through lease provisions (with Developer’s obligation limited to including such requirements in leases), not as direct Developer obligations; (b) the $17.50/hour living wage should be subject to adjustment only by mutual agreement and should not apply to positions not within the Project; (c) the scope, enforceability, and cost impact of these obligations must be carefully negotiated. These provisions are left open for negotiation and are not yet incorporated as binding Developer covenants above. **]

### Section 8.5 Additional Community Benefits

Any additional community benefit obligations beyond those set forth in this Article 8 shall be as agreed by the Parties in writing. The public amenities delivered by the Project (the public plaza, community center, and public parking structure in Phase IV) constitute substantial community benefits.

## ARTICLE 9. PERFORMANCE SECURITY

### Section 9.1 Phase I Performance Security

As a condition precedent to Closing, Developer shall post a $15,000,000 performance bond (issued by Ridgepoint Surety Corporation or another surety company reasonably acceptable to the City and the Construction Lender) or an irrevocable standby letter of credit issued by a nationally recognized financial institution acceptable to the City and the Construction Lender (collectively, the “Phase I Performance Security”). The Phase I Performance Security shall secure Developer’s obligation to commence and substantially complete Phase I in accordance with this Agreement.

### Section 9.2 Form; Draw Mechanics; Release

The amount, form, conditions, and draw mechanics of the Phase I Performance Security shall be as set forth in Exhibit [●], and shall be acceptable to the Construction Lender. The Phase I Performance Security shall be maintained continuously from the date of Closing until Phase I Substantial Completion. Upon Phase I Substantial Completion, the Phase I Performance Security shall be released and returned to Developer within thirty (30) days following written request and verification of Substantial Completion by the City.

### Section 9.3 Alternative Completion Assurance (In Lieu of Reversionary Interest)

In lieu of any reversionary interest, right of re-entry, possibility of reverter, or defeasible fee in favor of the City, and to address the City’s interest in ensuring timely completion of Phase I while preserving Developer’s fee simple absolute title, the Parties shall implement one or more of the following alternative completion-assurance mechanisms, as agreed in Exhibit [●]: (a) a contractual repurchase option in favor of the City, exercisable only upon (i) Developer’s failure to achieve Phase I Substantial Completion by the deadline in Section 14.1 (as extended by Force Majeure), (ii) expiration of all cure periods (including the Construction Lender’s extended cure period), and (iii) the Construction Lender’s prior written consent or full satisfaction of the outstanding Construction Loan, with the repurchase price equal to the lesser of the original purchase price or then-current fair market value; (b) an additional escrow deposit or irrevocable standby letter of credit held by a mutually acceptable escrow agent, drawable by the City upon a completion failure; (c) liquidated damages payable to the City in a predetermined amount representing a reasonable pre-estimate of the City’s actual damages, as an unsecured contractual obligation; (d) an enhanced completion guaranty from Developer’s principals; and/or (e) a right of first refusal in favor of the City as to any default-related disposition, subordinate to the Construction Lender’s mortgage. In all cases, Developer’s fee simple title shall remain absolute and indefeasible, and the Construction Lender’s mortgage shall remain a first-priority lien.

[Drafting Note — Cross-Document Conflict — Reversionary Interest (CRITICAL; see also Section 3.3 note):** This Section implements the alternative clawback mechanisms recommended by the Construction Loan Term Sheet (Section 12) to replace the reversionary interest required by Resolution No. R-2025-017, Condition No. 8. The Construction Lender states that the reversionary interest “would make the Loan impossible to close” and proposes the alternatives listed above. The Lakeshore Side Letter (Section 7(d)) requires Investor consent to any clawback/reversionary/repurchase mechanism and requires compatibility with the Construction Lender’s requirements. The specific mechanism(s) to be adopted must be negotiated among Developer, the City, the Construction Lender, and the Investor. Developer’s preference is a mechanism that does not impair fee simple title or the Construction Lender’s first-priority mortgage (e.g., liquidated damages, an escrow/letter of credit, or a repurchase option exercisable only after the Construction Loan is satisfied). **]

### Section 9.4 Performance Security for Later Phases

[Drafting Note — Open Item:** The Term Sheet (Section 8) addresses performance security only for Phase I. The Lakeshore Side Letter (Section 4.3(e)) notes that “amounts for later phases [are] to be established in the Development Agreement.” Developer’s bonding capacity through Ridgepoint Surety Corporation is up to $75,000,000 (Term Sheet, Section 7; RFP Response, Section 2.1) — a $15,000,000 Phase I bond plus bonds for later phases could approach or exceed this capacity. Developer’s position is that performance security should be limited to Phase I (or a reasonable, capped amount), and that any later-phase security should be negotiated separately and should not exhaust Developer’s bonding capacity. Confirm the City’s expectations for later-phase performance security. **]

## ARTICLE 10. FINANCING; LENDER PROTECTIONS

### Section 10.1 Construction Financing

Developer anticipates financing the Project with a construction loan facility of up to $210,000,000 from First Prairie National Bank (as described in the Construction Loan Term Sheet), committed equity of $85,000,000, TIF reimbursement, and additional debt/mezzanine financing for later phases. Developer’s financing arrangements are not conditions to the City’s obligations except as expressly stated in this Agreement.

### Section 10.2 Lender Protections

The Parties acknowledge that the Construction Lender’s commitment is conditioned on the form and substance of this Agreement being acceptable to the Construction Lender. Accordingly, this Agreement shall include, and the City shall cooperate to implement, the following lender-protective provisions:

(a) No Defeasible Fee. This Agreement shall not grant the City any reversionary interest, right of re-entry, possibility of reverter, or defeasible fee, as provided in Sections 3.3 and 9.3.

(b) Lender Notice and Cure Rights. The Construction Lender shall have the right (but not the obligation) to receive prompt written notice of any Developer default under this Agreement and a reasonable opportunity to cure, with the Construction Lender’s additional cure period being not less than thirty (30) days beyond Developer’s cure period for monetary defaults and not less than sixty (60) days beyond Developer’s cure period for non-monetary defaults, extended as necessary if the Construction Lender is diligently pursuing a cure (including time necessary to obtain possession through foreclosure or a receiver).

(c) Lender Consent to Amendments. No material amendment, modification, supplement, or termination of this Agreement shall be effective without the Construction Lender’s prior written consent, not to be unreasonably withheld, conditioned, or delayed.

(d) Subordination of City Interests. Any lien, encumbrance, or security interest that the City may hold or acquire in the Site (other than the eliminated reversionary interest) shall be subordinated to the Construction Lender’s mortgage pursuant to a subordination and intercreditor agreement in form acceptable to the Construction Lender.

(e) Foreclosure / Deed-in-Lieu Assignment. This Agreement shall permit assignment to a Construction Lender-designee or to a third-party purchaser at a foreclosure sale (or pursuant to a deed-in-lieu) without the City’s prior consent, or if City consent is required, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within thirty (30) days of request.

(f) Estoppel Certificates. The City shall deliver estoppel certificates to the Construction Lender upon reasonable request (not more than twice per calendar year), certifying the status of this Agreement, the existence or absence of outstanding defaults, and such other customary matters as the Construction Lender may reasonably request.

(g) Lender Review of Agreement. This Agreement shall be delivered to the Construction Lender in draft form not less than fifteen (15) business days prior to its proposed execution date and shall not be executed until the Construction Lender confirms in writing that it is acceptable.

[Drafting Note — Open Item:** The lender-protective provisions above are required by the Construction Loan Term Sheet (Section 12) and are generally favorable to Developer because they protect Developer’s financing. The City, however, may resist certain provisions — particularly the foreclosure/deed-in-lieu assignment without City consent (Section 10.2(e)) and the subordination of City interests (Section 10.2(d)). These are key negotiation points with the City. The Construction Loan Term Sheet (Section 12) states that the reversionary interest, if incorporated as stated in the Resolution, “would make the Loan impossible to close.” **]

### Section 10.3 Additional Financing for Later Phases

Approximately $58,400,000 in additional debt or mezzanine financing will be required for Phases II through IV. The structure and terms of this additional financing have not yet been determined and will be finalized as the Project progresses, subject to the Construction Lender’s and the Investor’s consent as required under the Construction Loan Documents and the Lakeshore Side Letter.

[Drafting Note — Open Item — Potential Financing Gap:** The Construction Loan Term Sheet (Section 2.1) limits the $210,000,000 facility to Phase I ($105,000,000), Phase II ($76,000,000), and infrastructure/contingency ($29,000,000). Phases III ($88,000,000) and IV ($71,000,000) entail approximately $159,000,000 in hard costs alone, plus soft costs, while the sources-and-uses tables (Term Sheet, Section 7; Construction Loan Term Sheet, Schedule C) identify only approximately $58,400,000 in “additional debt/mezzanine” for later phases. There may be a financing gap for Phases III and IV that would need to be filled by additional equity, cash flow from earlier phases, or other sources. The Agreement should not require Developer to commence Phases III or IV without financing in place, and Developer should preserve the right to extend or restructure later-phase timing if financing is not available on commercially reasonable terms. Confirm the phasing deadlines (Article 14) accommodate this. **]

## ARTICLE 11. ASSIGNMENT AND CHANGE OF CONTROL

### Section 11.1 Restriction on Assignment

Developer may not assign this Agreement or any interest therein, in whole or in part, without the prior written consent of the City, which consent may be withheld in the City’s reasonable discretion; provided that the City’s consent shall not be required for any Permitted Transfer (as defined in Section 11.2).

### Section 11.2 Permitted Transfers

Notwithstanding Section 11.1, the following transfers shall be permitted without the City’s prior written consent (collectively, “Permitted Transfers”):

(a) Internal Transfers. Transfers of membership interests among the existing members of Developer (Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, and TransitWorks Equity Group LLC) that do not reduce the Pellegrini Interest (as defined in Section 11.4) below the Pellegrini Threshold (as defined in Section 11.4);

(b) Estate Planning Transfers. Transfers by Marcus J. Pellegrini for estate-planning purposes to family trusts or entities controlled by Pellegrini, provided Pellegrini retains management control;

(c) Capital Raises. Transfers or issuances of membership interests in connection with capital raises for the Project that have been approved by the Investor (Lakeshore Capital Partners Fund III LP) and that do not reduce the Pellegrini Interest below the Pellegrini Threshold, or that are accompanied by a Key Person undertaking as provided in Section 11.4;

(d) Affiliate Assignment. Assignment to an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds at least the Pellegrini Threshold controlling interest and which expressly assumes in writing all of Developer’s obligations under this Agreement;

(e) Lender Disposition. Assignment to a Construction Lender-designee or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu, as provided in Section 10.2(e); and

(f) Limited Partner Transfers. Transfers of non-managing limited partnership interests in Lakeshore Capital Partners Fund III LP among its existing or admitted limited partners.

Developer shall provide the City with written notice of any Permitted Transfer, together with a copy of the assignment and assumption agreement (if any), within fifteen (15) days of the effective date thereof.

### Section 11.3 Key Person Provision

As an alternative or supplement to the percentage-of-interest thresholds, the Parties acknowledge that the City’s selection of Developer was based in substantial part on the qualifications, experience, and financial capacity of Marcus J. Pellegrini. Accordingly, Marcus J. Pellegrini shall serve as Manager and Chief Executive Officer of Developer and shall exercise day-to-day management authority over the Project. If Pellegrini ceases to serve as Manager and Chief Executive Officer, he shall be replaced by a person reasonably approved by the City (such approval not to be unreasonably withheld) within sixty (60) days.

### Section 11.4 Pellegrini Threshold; Harmonization

The “Pellegrini Interest” means the aggregate direct and indirect membership interest in Developer held by Marcus J. Pellegrini and/or the Pellegrini Family Trust. The “Pellegrini Threshold” means [fifty percent (50%)] / [fifty-one percent (51%)], as finally agreed among the Parties, the Construction Lender, and the Investor.

[Drafting Note — Cross-Document Conflict — Change-of-Control / Assignment Thresholds (SIGNIFICANT):** Three different controlling-interest thresholds appear across the source documents: (i) the Term Sheet (Section 10) permits assignment without City consent to an entity in which Pellegrini holds at least 50% controlling interest; (ii) the Construction Loan Term Sheet (Section 8.1) defines a Change of Control if Pellegrini ceases to hold at least [50]% (bracketed, subject to negotiation), and also if any single investor/group acquires 25% or more; and (iii) the Lakeshore Side Letter (Section 5.2) defines a Change of Control if the Pellegrini Interest falls below 51%, and (Section 4.4) grants the Investor enhanced consent rights (over any amendment, not just Material Amendments) if the Pellegrini Interest falls below 51%. The Side Letter (Section 5.3) expressly acknowledges that future capital raises for later phases may dilute the Pellegrini Interest below both the 51% (Side Letter) and 50% (Term Sheet) thresholds, and commits the parties to negotiate a “broader permitted transfer carve-out that accommodates internal transfers among existing members and capital raises approved by both Investor and the City.” The Pellegrini Threshold must be harmonized across this Agreement, the Construction Loan Documents, and the Lakeshore Side Letter. Developer’s position is to (a) adopt a single threshold (preferably 50%, the most flexible), (b) include the broad Permitted Transfer carve-outs in Section 11.2 (internal transfers, estate planning, approved capital raises, lender disposition), (c) use the Key Person provision in Section 11.3 as an alternative to rigid percentage thresholds, and (d) include a reasonable cure period (not less than 60 days) before any assignment default is triggered (Lakeshore Side Letter, Section 8.3). **]

[Drafting Note — Open Item — 25% Acquisition Trigger:** The Construction Loan Term Sheet (Section 8.1(c)) and the Lakeshore Side Letter (Section 5.2(iii)) both treat acquisition of 25% or more of Developer’s membership interests by a new investor as a Change of Control. The Term Sheet (Section 10) does not include a 25% trigger. Confirm whether the Agreement should include a 25% acquisition trigger and how it interacts with the Permitted Transfer for approved capital raises. **]

### Section 11.5 Effect of Violation

Any purported assignment in violation of this Article 11 shall be void and of no force and effect and shall constitute a material default under this Agreement, subject to the cure provisions of Article 15 and the cure period referenced in Section 11.4.

## ARTICLE 12. REPRESENTATIONS AND WARRANTIES

### Section 12.1 Mutual Representations

Each Party represents and warrants that it has full power and authority to enter into this Agreement and to perform its obligations hereunder, and that the execution and delivery of this Agreement has been duly authorized by all necessary action.

### Section 12.2 Developer Representations

Developer represents and warrants that: (a) it is an Illinois limited liability company duly organized, validly existing, and in good standing; (b) it has the financial capacity, development experience, and organizational resources necessary to complete the Project; (c) its current ownership structure is Pellegrini Family Trust (60%), Lakeshore Capital Partners Fund III LP (25%), and TransitWorks Equity Group LLC (15%), and no other person holds any ownership, equity, or profits interest; (d) its entity-level net worth is approximately $185,000,000; (e) it has bonding capacity of up to $75,000,000 through Ridgepoint Surety Corporation; and (f) there are no environmental conditions on the Site other than those disclosed in the Phase II ESA.

### Section 12.3 City Representations

The City represents and warrants that: (a) it has good and marketable fee simple title to the Site, free and clear of all liens, encumbrances, and adverse claims (except Permitted Exceptions), and has the legal authority to convey the Site to Developer; (b) the Site is located within the Lakemont Central TIF District and TIF funds are legally available for the purposes described in this Agreement, subject to annual appropriation and the availability of increment; and (c) the adoption of the Resolution duly authorized the City Manager to negotiate and execute this Agreement.

[Drafting Note — Open Item:** The Term Sheet (Section 18.1) and the Construction Loan Term Sheet (Section 11) contain customary representations. The City’s representation regarding the authority of the City Manager to execute this Agreement (Section 12.3(c)) is important given the open item in the Recitals regarding whether a separate City Council vote is required. Developer should seek a City representation that the Resolution constitutes sufficient City Council authorization for execution of this Agreement. **]

## ARTICLE 13. CONDITIONS PRECEDENT

### Section 13.1 Conditions Precedent to Closing

The obligation of each Party to proceed to Closing is subject to the satisfaction or waiver of the following conditions precedent:

(a) Execution and delivery of this Agreement by both Parties and approval by the City Council (to the extent required);

(b) Completion of rezoning of the Site from M-2 to PD-TOD, with the rezoning final and non-appealable or the applicable appeal period expired without the filing of any appeal;

(c) Completion or authorization of parcel consolidation of the three parcels into a single parcel of record;

(d) IEPA approval of the RAP for Parcel 12-24-300-016 (or the alternative in Section 5.4(c));

(e) Developer’s demonstration of committed equity of at least $85,000,000, in form and substance reasonably acceptable to the City;

(f) Developer’s posting of the Phase I Performance Security;

(g) Delivery of marketable and insurable title to the Site, subject only to Permitted Exceptions, and issuance of the owner’s and lender’s title insurance policies;

(h) Confirmation from First Prairie National Bank that this Agreement is in a form acceptable to the Construction Lender; and

(i) Satisfaction of the Construction Lender’s conditions precedent to the Construction Loan, to the extent applicable to Closing.

### Section 13.2 Equity Demonstration Deadline

Developer shall demonstrate committed equity of at least $85,000,000 in accordance with Section 13.1(e).

[Drafting Note — Cross-Document Conflict — Equity Demonstration Deadline/Trigger:** The Resolution (Condition No. 3(a)) requires Developer to demonstrate committed equity of not less than $85,000,000 within sixty (60) days of the adoption of the Resolution (i.e., on or before April 19, 2025), verified by an independent certification from Clearmont Accounting Group LLP. The Term Sheet (Section 7) requires demonstration within sixty (60) days of City Council approval of the definitive Agreement (targeted June 2025). The Term Sheet also lists equity demonstration as both a condition precedent to execution of the definitive Agreement (Section 18.2(iv)) and a condition precedent to Closing (Section 4(v)). The Construction Loan Term Sheet (Section 7.1, item 8) references the Resolution’s April 19, 2025 deadline. The Resolution’s April 19, 2025 deadline is earlier and more onerous than the Term Sheet’s trigger. The Parties must reconcile: (i) the applicable deadline (April 19, 2025 per Resolution, or 60 days after Agreement approval per Term Sheet); (ii) the form of evidence (the Resolution requires independent certification by Clearmont; the Term Sheet allows audited account statements, subscription agreements, or other reasonable evidence; the Construction Loan requires executed subscription agreements, fund commitment letters, and proof of liquid assets); and (iii) whether equity demonstration is a condition to Agreement execution, to Closing, or both. Developer’s position is to align on a single, achievable deadline and a form of evidence that satisfies both the City and the Construction Lender. **]

### Section 13.3 Conditions Precedent to Each Phase

Commencement of construction of each phase shall be subject to: (a) satisfaction of the Construction Lender’s conditions to the applicable draw; (b) issuance of necessary building permits; (c) for Parcel 12-24-300-016, issuance of the NFR Letter (or the alternative in Section 5.4(c)) to the extent construction will occur on the affected area; and (d) the City’s completion of the off-site infrastructure improvements necessary to support that phase, to the extent applicable.

## ARTICLE 14. PHASING, TIMELINES, AND FORCE MAJEURE

### Section 14.1 Phasing Schedule

The Project shall be constructed in four phases in accordance with the following schedule:

| Phase | Commencement Deadline | Substantial Completion Deadline |
| --- | --- | --- |
| Phase I | Groundbreaking no later than March 1, 2026 | September 30, 2028 |
| Phase II | Within 12 months of Phase I Substantial Completion | Within 24 months of Phase II commencement |
| Phase III | Within 12 months of Phase II Substantial Completion | Within 30 months of Phase III commencement |
| Phase IV | Concurrent with Phase III commencement | Within 24 months of Phase IV commencement |

The commencement deadline for each subsequent phase is measured from the Substantial Completion date of the immediately preceding phase, as may be extended by Force Majeure.

### Section 14.2 Construction Progress Reports

Developer shall provide quarterly construction progress reports to the City’s Community Development Department, including percentage of completion, updated schedule, and identification of delays or anticipated deviations, within thirty (30) days following the end of each calendar quarter.

### Section 14.3 Force Majeure

(a) Definition. “Force Majeure” means any event beyond Developer’s reasonable control, including, without limitation: acts of God, fire, flood, earthquake, tornado, severe weather, pandemic, epidemic, quarantine, governmental health orders, war, terrorism, civil unrest, insurrection, strikes or labor disputes (other than those caused by Developer’s labor practices or failure to comply with labor laws), industry-wide supply chain disruptions, governmental moratoria on construction, delays in IEPA review or approval of the RAP or NFR Letter, delays in rezoning or parcel consolidation, and actions or inactions of governmental authorities (other than the City of Lakemont) that prevent or materially delay construction.

(b) Effect. Force Majeure events shall extend the applicable deadlines for commencement and Substantial Completion on a day-for-day basis for the duration of the event.

(c) Aggregate Cap. The maximum extension of time available under this Section 14.3 shall not exceed [eighteen (18) months] in the aggregate across the Project.

(d) Notice and Mitigation. Developer shall provide written notice to the City within fifteen (15) business days of the occurrence of a Force Majeure event and shall use commercially reasonable efforts to mitigate its effects.

(e) Exclusions. Force Majeure shall not include financial inability to perform, changes in market conditions, increases in the cost of labor or materials (unless attributable to an industry-wide supply chain disruption), Developer’s failure to obtain financing, or any event caused by Developer’s negligence or willful misconduct.

[Drafting Note — Cross-Document Conflict / Open Item — Force Majeure Cap:** The Term Sheet (Section 14) provides an aggregate Force Majeure cap of 18 months across the Project. The Construction Loan Term Sheet (Section 9, item 9) provides Force Majeure extensions of up to 180 days (6 months) for the Phase I Substantial Completion default trigger, plus the Construction Lender’s extension options (two 6-month extensions). The 18-month aggregate cap may be insufficient given that the Parcel 016 remediation timeline alone is 14–18 months (Phase II ESA, Section 5.2), and IEPA/regulatory delays, rezoning delays, and supply chain disruptions could each consume substantial portions of the cap. Developer’s position is to (a) broaden the Force Majeure definition to expressly include IEPA/regulatory delays and rezoning/consolidation delays (reflected above), and (b) seek to increase or eliminate the aggregate cap, or at minimum exclude IEPA/regulatory delays from the cap. Confirm the City’s position on the cap and the expanded definition. **]

[Drafting Note — Open Item — Phase I Groundbreaking Deadline vs. Remediation/Conveyance Timeline:** The Phase I groundbreaking deadline of March 1, 2026 may be inconsistent with the remediation and conveyance timeline if Closing is conditioned on RAP approval and the NFR Letter for Parcel 016 is not issued until the second to fourth quarter of 2026 (Phase II ESA, Section 5.2). The Term Sheet (Section 15(b)) gives the City a termination right if Developer fails to commence Phase I within six (6) months of land conveyance, which is a conveyance-relative trigger, while the March 1, 2026 deadline is a fixed date. Developer should seek to (a) measure the Phase I groundbreaking deadline from Closing rather than as a fixed date, or (b) expressly permit Phase I construction to commence on the clean portions of the Site before the NFR Letter for Parcel 016 is issued, and (c) treat NFR Letter delays as Force Majeure. **]

## ARTICLE 15. DEFAULT, CURE, AND TERMINATION

### Section 15.1 Monetary Defaults

In the event of a monetary default by either Party, the non-defaulting Party shall provide written notice specifying the nature and amount of the default. The defaulting Party shall have sixty (60) days from receipt of such notice to cure.

### Section 15.2 Non-Monetary Defaults

In the event of a non-monetary default by either Party, the non-defaulting Party shall provide written notice specifying the nature of the default in reasonable detail. The defaulting Party shall have ninety (90) days from receipt of such notice to cure; provided that if the default cannot reasonably be cured within 90 days, the defaulting Party shall have such additional time as is reasonably necessary, so long as it has commenced cure efforts within the initial 90-day period and is diligently and continuously pursuing cure to completion.

### Section 15.3 Termination by Developer

Developer shall have the right to terminate this Agreement upon: (a) the City’s failure to deliver clean, marketable, and insurable title to the Site at Closing; (b) the City’s failure to fund its committed infrastructure obligations ($12,500,000) within the timelines specified in Exhibit [●]; (c) the City’s failure to achieve rezoning or parcel consolidation as required by Section 13.1; (d) a condemnation or taking by eminent domain (by any entity other than the City) of more than 15% of the Site; (e) the City’s material breach of its environmental indemnity or remediation obligations that remains uncured after the applicable cure period; (f) impairment or expiration of the Lakemont Central TIF District such that the TIF Reimbursement Cap cannot be achieved, to the extent not caused by Developer; and (g) such other events as may be specified in this Agreement.

### Section 15.4 Termination by City

The City shall have the right to terminate this Agreement upon: (a) a material breach by Developer that remains uncured after the expiration of the applicable cure period (including the Construction Lender’s extended cure period); (b) Developer’s failure to commence Phase I construction within six (6) months following Closing; (c) Developer’s abandonment of the Project, evidenced by cessation of all construction activity for a period of 180 consecutive days (other than cessation caused by Force Majeure); and (d) such other events as may be specified in this Agreement.

[Drafting Note — Open Item:** The Term Sheet (Section 15) provides the foregoing termination triggers. Developer’s position is to (a) preserve and expand Developer’s termination rights (Section 15.3), including for City failure to achieve rezoning/consolidation, City breach of environmental indemnity, and TIF impairment; (b) ensure the City’s termination rights are subject to the Construction Lender’s extended cure period (Section 10.2(b)); and (c) confirm the condemnation threshold (15%) is consistent between this Agreement and the Construction Loan Term Sheet (Section 9, item 8). **]

### Section 15.5 Remedies

Upon termination by a non-defaulting Party, the non-defaulting Party shall have all remedies available at law or in equity, including damages, specific performance, and injunctive relief, subject to the dispute resolution provisions of Article 17. Without limiting the foregoing, Developer shall have the right to specific performance of the City’s obligations to convey the Site, to achieve rezoning and consolidation, to fund infrastructure, and to provide the public incentives.

## ARTICLE 16. INDEMNIFICATION

### Section 16.1 Mutual Indemnification

Each Party shall indemnify, defend, and hold harmless the other Party, and its officers, employees, agents, and representatives, from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to the indemnifying Party’s negligent acts or omissions, reckless conduct, or willful misconduct in connection with the performance of its obligations under this Agreement.

### Section 16.2 Developer Indemnification of City

Developer shall indemnify, defend, and hold harmless the City from and against claims arising from or related to construction activities on the Site, including claims for personal injury, death, property damage, and workers’ compensation, regardless of whether brought by Developer’s employees, contractors, subcontractors, or third parties; provided that such indemnity shall not extend to claims arising from pre-existing environmental conditions, which are covered by the City’s indemnity in Section 5.6.

### Section 16.3 City Environmental Indemnification

The City’s environmental indemnification obligations are set forth in Section 5.6 and are incorporated herein by reference.

### Section 16.4 Survival

The indemnification obligations set forth in this Article 16 and in Section 5.6 shall survive the expiration or termination of this Agreement.

[Drafting Note — Open Item:** Developer’s position is that the City’s environmental indemnity (Section 5.6) should be broad and uncapped (covering all pre-existing contamination, including TCE, vapor intrusion, and cost overruns), while Developer’s construction indemnity (Section 16.2) should be limited to claims not arising from pre-existing conditions and should be backed by insurance. Confirm the City accepts the carve-out of pre-existing environmental conditions from Developer’s construction indemnity. **]

## ARTICLE 17. DISPUTE RESOLUTION

### Section 17.1 Negotiation

The Parties shall first attempt to resolve any dispute arising under or related to this Agreement through good-faith negotiation between the City Manager (or designee) and Developer’s CEO (or designee) for a period of thirty (30) days following written notice of the dispute.

### Section 17.2 Mediation

If the dispute is not resolved through negotiation within the 30-day period, the dispute shall be submitted to non-binding mediation before a neutral mediator mutually agreed by the Parties (or, failing agreement, before the Lakemont Mediation Center or such other mediator as the Parties may agree). The costs of mediation shall be shared equally, and each Party shall bear its own attorneys’ fees.

### Section 17.3 Binding Arbitration

If the dispute is not resolved through mediation within sixty (60) days following submission to the mediator, the dispute shall be submitted to final and binding arbitration administered under the Commercial Arbitration Rules of the American Arbitration Association, conducted by a single arbitrator with experience in real estate development matters. The venue for mediation and arbitration shall be Cook County or Lake County, Illinois.

### Section 17.4 Governing Law

This Agreement shall be governed by and construed in accordance with the laws of the State of Illinois.

### Section 17.5 Provisional Remedies

Nothing in this Article 17 shall prevent either Party from seeking temporary restraining orders, preliminary injunctions, or other provisional judicial relief where necessary to prevent irreparable harm, pending resolution of the dispute through the procedures set forth above.

[Drafting Note — Open Item:** The Term Sheet (Section 17) provides for negotiation, mediation (Lakemont Mediation Center), and binding arbitration (AAA), with venue in Cook County or Lake County. The Construction Loan Term Sheet (Section 13) provides for litigation in Cook County state or federal courts (not arbitration). The Lakeshore Side Letter (Section 10.2) provides for negotiation, AAA mediation, and AAA arbitration in Cook County. The dispute-resolution forums differ between this Agreement (arbitration) and the Construction Loan (litigation). Developer’s preference is generally arbitration (faster, private, experienced arbitrator). Confirm the City accepts arbitration and the venue. Confirm the availability of the Lakemont Mediation Center. **]

## ARTICLE 18. MISCELLANEOUS

### Section 18.1 Term

This Agreement shall become effective on the Effective Date and shall continue in full force and effect until the Substantial Completion of all phases of the Project and the satisfaction of all surviving obligations, including the affordability restriction period (30 years) and the environmental indemnities.

### Section 18.2 Notices

All notices shall be in writing and shall be deemed delivered upon personal delivery, upon delivery by nationally recognized overnight courier, or three business days following deposit in the U.S. mail, registered or certified, return receipt requested, postage prepaid, addressed as follows:

If to Developer: Granite City Development LLC, 900 West Monroe Street, Suite 2200, Chicago, IL 60607, Attn: Marcus J. Pellegrini, Manager and CEO; with a copy to Thornfield & Pratt LLP, 311 South Wacker Drive, Suite 5400, Chicago, IL 60606, Attn: Catherine M. Albrecht.

If to City: City of Lakemont, Office of the City Manager, 200 Civic Center Drive, Lakemont, IL 60048, Attn: Gerald T. Fong, City Manager; with a copy to Office of Corporation Counsel, City of Lakemont, 200 Civic Center Drive, Lakemont, IL 60048, Attn: Rebecca A. Sinclair, Esq.; and with a copy to Ashford, Keene & Mulvaney LLP, 150 North Michigan Avenue, Suite 3200, Chicago, IL 60601, Attn: Jonathan Ashford.

[Drafting Note — Open Item:** The Lakeshore Side Letter (Section 6) requires Developer to provide the Investor (Lakeshore Capital Partners Fund III LP, Attn: Richard Dominguez) with copies of all material correspondence with the City and the Construction Lender, and prompt notice of any default under this Agreement or the construction loan. The Construction Loan Term Sheet (Section 12(b)) requires the Construction Lender to receive prompt written notice of any Developer default under this Agreement. The Agreement should provide for notice copies to the Construction Lender (Sandra L. Chen, First Prairie National Bank) and the Investor (Richard Dominguez, Lakeshore Capital Partners Fund III LP) for notices of default and material amendments. Add these as additional copy recipients. **]

### Section 18.3 Confidentiality; FOIA

The terms and contents of this Agreement are confidential and shall not be disclosed by either Party to any third party, except: (a) to each Party’s legal counsel, financial advisors, accountants, lenders, and equity investors; (b) as required by applicable law or governmental regulation, including the Illinois Freedom of Information Act (5 ILCS 140/) as applicable to the City; and (c) to the extent necessary for City Council proceedings and governmental approvals. The City shall use commercially reasonable efforts to claim available exemptions under the Freedom of Information Act for trade secrets and commercial information designated confidential by Developer.

[Drafting Note — Open Item:** The Term Sheet (Section 20) contains a confidentiality provision with FOIA carve-outs. Because the City is subject to the Illinois Freedom of Information Act, Developer’s confidential business and financial information may be subject to disclosure. Developer should seek protections (confidential-treatment designations, FOIA exemptions for trade secrets/commercial information under 5 ILCS 140/7(1)(g)). Confirm the City will cooperate in asserting exemptions. **]

### Section 18.4 Amendments

This Agreement may be amended only by a written instrument executed by both Parties, and, with respect to any material amendment, with the Construction Lender’s prior written consent as provided in Section 10.2(c) and the Investor’s consent as required under the Lakeshore Side Letter.

### Section 18.5 Assignment

Assignment and change of control are governed by Article 11.

### Section 18.6 Severability

If any provision of this Agreement is held invalid or unenforceable, such invalidity shall not affect other provisions that can be given effect, and the provisions are severable.

### Section 18.7 Entire Agreement; Supersession

This Agreement, including its Recitals, Exhibits, and Schedules, constitutes the entire agreement between the Parties with respect to the subject matter hereof and supersedes the Term Sheet in its entirety upon execution. The Term Sheet shall be of no further force and effect upon execution of this Agreement.

### Section 18.8 Costs and Expenses

Each Party shall bear its own costs and expenses incurred in connection with the negotiation and preparation of this Agreement, including legal fees and consultant fees.

### Section 18.9 Counterparts; Electronic Signatures

This Agreement may be executed in counterparts, each of which shall be deemed an original, and signatures transmitted by electronic means shall be deemed original signatures.

### Section 18.10 Authority

The City represents that the execution and delivery of this Agreement by the City Manager has been duly authorized by the City Council through the adoption of the Resolution, and that no further City Council action is required to authorize execution, except as expressly stated in this Agreement.

[Drafting Note — Open Item:** Section 18.10 is drafted to confirm that the Resolution constitutes sufficient City Council authorization for execution of this Agreement by the City Manager, addressing the open item in the Recitals. If the City takes the position that a separate City Council vote on the executed Agreement is required, this Section must be revised and the additional approval added as a condition precedent in Article 13. **]

## SIGNATURE PAGE

IN WITNESS WHEREOF, the Parties have executed this Development Agreement as of the Effective Date.

GRANITE CITY DEVELOPMENT LLC

By: _______________________

Name: Marcus J. Pellegrini

Title: Manager and Chief Executive Officer

Date: _______________________

CITY OF LAKEMONT, ILLINOIS

By: _______________________

Name: Gerald T. Fong

Title: City Manager

Date: _______________________

APPROVED AS TO FORM:

Rebecca A. Sinclair, Esq.

Corporation Counsel, City of Lakemont, Illinois

## SCHEDULE OF CROSS-DOCUMENT CONFLICTS AND OPEN ITEMS

The following consolidated schedule summarizes the principal cross-document conflicts and open items flagged in the bracketed drafting notes throughout this draft, for ease of reference in negotiation. Each item is keyed to the relevant Agreement section.

| # | Type | Issue | Source Documents | Agreement Section |
| --- | --- | --- | --- | --- |
| 1 | Conflict | RFP number discrepancy (2024-CD-07 vs. 2024-CD-018) | RFP Response; Term Sheet; Resolution | Recital B |
| 2 | Open Item | Resolution adopted 7–2 (not unanimous); political risk | Resolution | Recital E |
| 3 | Open Item | Whether separate City Council vote on definitive Agreement is required | Term Sheet §18.2(v); Resolution §§2, 4 | Recital E; §18.10 |
| 4 | Conflict (CRITICAL) | Reversionary interest / defeasible fee required by Resolution but prohibited by Construction Lender and Investor | Resolution Cond. 8; Construction Loan TS §§4.2, 7.1, 12; Lakeshore Side Letter §7(d) | §§3.3, 9.3 |
| 5 | Conflict | 36-month-from-conveyance reversion trigger vs. Sept. 30, 2028 Phase I SC deadline | Resolution Cond. 8; Term Sheet §§3.1, 13 | §3.3 |
| 6 | Open Item | Per-parcel title review before consolidation; distinct chains of title | Phase II ESA §1.3 | §3.2 |
| 7 | Open Item | Phased conveyance (clean parcels first) vs. single consolidated conveyance | Phase II ESA §5.2; Construction Loan TS §7.1 | §3.2 |
| 8 | Conflict | ELUCs / Affordable Housing Covenant as title encumbrances; lender acceptability | Phase II ESA §§4.2.4, 4.3.3, 6.2; Construction Loan TS §4.2 | §3.4 |
| 9 | Conflict / Open Item | Land write-down charged against TIF cap or separate incentive | TIF Memo §VII; Term Sheet §5.6 | §4.1 |
| 10 | Conflict / Open Item | TIF cap reachability ($38–42M adjusted vs. $48M cap); shortfall risk borne by Developer | TIF Memo §IV | §4.2 |
| 11 | Open Item | Abatement/TIF interaction (abatement reduces increment) | TIF Memo §§IV.B, VIII.4 | §4.2 |
| 12 | Conflict / Open Item | City infrastructure $12.5M funding source (TIF vs. general revenue) | TIF Memo §VII; Term Sheet §5.3 | §4.3 |
| 13 | Open Item | Abatement limited to Phase I; later-phase incentives open | Term Sheet §18.4 | §4.4 |
| 14 | Open Item | Permit fee waivers limited to Phases I–II | Term Sheet §5.5 | §4.5 |
| 15 | Open Item | Phase II ESA third-party reliance letters required | Phase II ESA §9 | §5.1 |
| 16 | Conflict | TCE contamination on Parcel 016 not described in Term Sheet (BTEX only) | Phase II ESA §§4.2.2, 4.2.3; Term Sheet §6 | §5.2 |
| 17 | Open Item | Remediation cost overruns ($3.8–4.2M vs. $3.14M base); overrun responsibility | Phase II ESA §§4.2.4, 5.3 | §5.5 |
| 18 | Open Item | Vapor intrusion evaluation and mitigation costs not estimated | Phase II ESA §§7.1, 8.1 | §§5.2, 5.5 |
| 19 | Open Item | Off-site groundwater monitoring requires Metra access; coordination responsibility | Phase II ESA §8.3 | §5.2 |
| 20 | Open Item | Remediation performance responsibility (City vs. Developer) | Phase II ESA §8.2(a); Term Sheet §6 | §5.3 |
| 21 | Conflict | NFR Letter vs. RAP approval as condition precedent to conveyance | Term Sheet §§4, 6; Resolution Cond. 3(b); Construction Loan TS §7.1 | §5.4 |
| 22 | Open Item | Remediation timeline (14–18 mos.) vs. March 1, 2026 groundbreaking | Phase II ESA §5.2; Term Sheet §3.1 | §§5.4, 14.3 |
| 23 | Open Item | City environmental indemnity scope (all contaminants, uncapped, surviving) | Term Sheet §16; Phase II ESA §4.2.4 | §5.6 |
| 24 | Open Item | Design review period, scope, deemed-approval mechanism | Term Sheet §19 | §6.2 |
| 25 | Conflict (SIGNIFICANT) | Prevailing wage scope: “all construction” (Term Sheet) vs. statutory public-works scope (Developer position) | Term Sheet §11.1; TIF Memo §V; Resolution §8 | §6.3 |
| 26 | Open Item | LEED Gold: strict certification guarantee vs. good-faith pursuit | Term Sheet §11.2; Resolution Cond. 3(f); Construction Loan TS §6.1 | §6.4 |
| 27 | Conflict | Insurance: CGL aggregate ($20M Term Sheet vs. $25M Loan); additional coverages (Professional $5M, Pollution $10M) | Term Sheet §11.3; Construction Loan TS §5 | §6.5 |
| 28 | Open Item | Reporting frequency harmonization (monthly/quarterly across docs) | Term Sheet §§9, 13; TIF Memo §V.C; Construction Loan TS §6.2; Lakeshore Side Letter §6 | §6.6 |
| 29 | Open Item | Construction contract form (GMP/stipulated-sum, lender-approved) | Construction Loan TS §7.1 | §6.7 |
| 30 | Open Item | Sustainability features (EV 10%, bike storage) as design guidelines | RFP Response §4.1; Term Sheet §11.2 | §6.8 |
| 31 | Conflict | Community center: “in consultation with” / “at no additional cost” (Term Sheet) vs. “to City specifications” / “fully furnished and equipped” (RFP) | Term Sheet §3.4; RFP Response §5.5 | §6.9 |
| 32 | Open Item | Affordable unit count: “at least 100” (Term Sheet) vs. 106/20% (RFP, Resolution) | Term Sheet §12; RFP Response; Resolution | §§2.3, 7.1 |
| 33 | Open Item | 30-year affordability covenant as lender-acceptable Permitted Exception; reporting burden | Term Sheet §12; Construction Loan TS §4.2 | §7.3 |
| 34 | Conflict | Local hiring measurement: headcount (Term Sheet) vs. labor hours (Resolution); no-default formulation | Term Sheet §9; Resolution Cond. 3(c)(i) | §8.2 |
| 35 | Conflict (SIGNIFICANT) | Living wage ($17.50/hr) and first-source hiring for permanent positions required by Resolution but absent from Term Sheet | Resolution Cond. 3(c); Term Sheet §9; RFP Response §6.2 | §8.4 |
| 36 | Conflict (CRITICAL) | Alternative clawback mechanism in lieu of reversionary interest; mechanism selection | Resolution Cond. 8; Construction Loan TS §12; Lakeshore Side Letter §7(d) | §9.3 |
| 37 | Open Item | Performance security for later phases; bonding capacity ($75M) constraint | Term Sheet §8; Lakeshore Side Letter §4.3(e); RFP Response §2.1 | §9.4 |
| 38 | Open Item | Lender-protective provisions (cure rights, consent, subordination, foreclosure assignment, estoppel) — City negotiation | Construction Loan TS §12 | §10.2 |
| 39 | Open Item | Potential financing gap for Phases III–IV ($159M hard costs vs. $58.4M additional debt) | Construction Loan TS §2.1; Term Sheet §7 | §10.3 |
| 40 | Conflict (SIGNIFICANT) | Change-of-control / assignment thresholds: 50% (Term Sheet), [50]% (Loan), 51% (Side Letter); 25% acquisition trigger | Term Sheet §10; Construction Loan TS §8.1; Lakeshore Side Letter §§4.4, 5.2 | §§11.2, 11.4 |
| 41 | Open Item | Key Person provision and ≥60-day cure period before assignment default | Lakeshore Side Letter §8.3 | §§11.3, 11.4 |
| 42 | Open Item | City representation re City Manager authority / Resolution sufficiency | Term Sheet §18.1; Resolution §§2, 4 | §12.3 |
| 43 | Conflict | Equity demonstration deadline/trigger: April 19, 2025 (Resolution) vs. 60 days after Agreement approval (Term Sheet); form of evidence | Resolution Cond. 3(a); Term Sheet §§4, 7, 18.2; Construction Loan TS §7.1 | §13.2 |
| 44 | Conflict / Open Item | Force Majeure cap: 18 months aggregate (Term Sheet) vs. 180 days Phase I (Loan); sufficiency given 14–18 mos. remediation | Term Sheet §14; Construction Loan TS §9 | §14.3 |
| 45 | Open Item | Phase I groundbreaking (fixed March 1, 2026) vs. conveyance/remediation timeline | Term Sheet §3.1; Phase II ESA §5.2 | §14.3 |
| 46 | Open Item | Developer termination rights expansion; condemnation threshold consistency | Term Sheet §15; Construction Loan TS §9 | §15.3 |
| 47 | Open Item | Developer construction indemnity carve-out for pre-existing environmental conditions | Term Sheet §16; Phase II ESA §4.2.4 | §16.2 |
| 48 | Open Item | Dispute resolution forum: arbitration (Agreement) vs. litigation (Loan); venue; Lakemont Mediation Center availability | Term Sheet §17; Construction Loan TS §13; Lakeshore Side Letter §10.2 | §17.3 |
| 49 | Open Item | Notice copies to Construction Lender and Investor for defaults/amendments | Lakeshore Side Letter §6; Construction Loan TS §12 | §18.2 |
| 50 | Open Item | Confidentiality / FOIA protections for Developer’s confidential information | Term Sheet §20 | §18.3 |
| 51 | Open Item | Substantial Completion definition (temporary CO sufficiency; public-plaza standard) | Term Sheet §13; Construction Loan TS §9 | §1.1 |
| 52 | Open Item | Hotel brand “to be determined” at Phase III | Term Sheet §3.3; RFP Response §5.4 | §2.2(c) |
| 53 | Open Item | TransitWorks (15% member) managed by former public transit officials — potential conflict given Metra coordination needs | Term Sheet §1.2; RFP Response §2.2 | §12.2(c) |
| 54 | Open Item | Updated appraisal at loan closing (Jan. 15, 2025 appraisal may be stale); land price lock | Construction Loan TS §§6.2, 7.1, 11 | §3.1 |

End of Draft Development Agreement.

This draft is prepared on behalf of Granite City Development LLC for negotiation purposes. Bracketed drafting notes and the consolidated schedule above identify cross-document conflicts among the source materials (Negotiated Term Sheet, RFP Response Narrative, City Council Resolution No. R-2025-017, Construction Loan Term Sheet, Lakeshore Side Letter, Phase II ESA Summary, and TIF District Summary Memo) and open items requiring resolution. This document is non-binding until duly executed by both Parties and approved by the Lakemont City Council.