# DEVELOPMENT AGREEMENT

## LAKEMONT STATION COMMONS MIXED-USE TRANSIT-ORIENTED DEVELOPMENT

[DRAFT — PREPARED ON BEHALF OF GRANITE CITY DEVELOPMENT LLC (DEVELOPER)]

[Drafting Note — Purpose and Scope of Draft: This Development Agreement (“Agreement”) is drafted on behalf of, and to protect the interests of, Granite City Development LLC (“Developer”). It is based on the following source documents: (i) City Council Resolution No. R-2025-017 (adopted Feb. 18, 2025); (ii) Negotiated Term Sheet dated Jan. 22, 2025; (iii) Preliminary Construction Loan Term Sheet from First Prairie National Bank (March 2025); (iv) Lakeshore Capital Partners Fund III LP Side Letter dated Feb. 10, 2025; (v) Phase II Environmental Site Assessment Executive Summary by Greenfield Environmental Consultants LLC (Nov. 8, 2024); (vi) RFP Response Narrative by Granite City Development LLC (Dec. 16, 2024); and (vii) Corporation Counsel TIF District Summary Memo (March 5, 2025). Bracketed drafting notes throughout flag (a) cross-document conflicts and (b) open items requiring negotiation, lender confirmation, or further diligence. Bracketed text in the operative provisions denotes terms to be confirmed or negotiated.]

This DEVELOPMENT AGREEMENT (this “Agreement”) is made and entered into as of [•], 2025 (the “Effective Date”), by and between the CITY OF LAKEMONT, ILLINOIS, an Illinois home rule municipality (the “City”), and GRANITE CITY DEVELOPMENT LLC, an Illinois limited liability company (the “Developer”). The City and the Developer are referred to herein individually as a “Party” and collectively as the “Parties.”

[Drafting Note — Effective Date / Execution Timing: The Negotiated Term Sheet targets a June 2025 execution date, contingent on rezoning and IEPA approval of the Remedial Action Plan for Parcel 016. Resolution R-2025-017 requires rezoning to PD-TOD to be completed and effective prior to execution of this Agreement (Condition #5). The Construction Lender requires the rezoning to be “final and non-appealable, or that the applicable appeal period has expired” as a condition to loan closing. Open item: confirm whether the appeal period must run before execution, which may push execution beyond June 2025.]

## RECITALS

A. The Property. The City is the owner of certain real property commonly known as 1400–1550 Lakemont Station Boulevard, Lakemont, Illinois 60048, consisting of three (3) parcels of record identified by Parcel Identification Numbers 12-24-300-015, 12-24-300-016, and 12-24-300-017, totaling approximately 12.7 acres (553,212 square feet) (collectively, the “Property”). The Property constitutes the former site of the Lakemont Ironworks manufacturing campus, which ceased industrial operations in 2009, and is situated immediately adjacent to the Lakemont Central Metra commuter rail station.

[Drafting Note — Parcel Acreage Conflict: The Phase II ESA reports individual parcel sizes of approximately 4.2 acres (015), 4.1 acres (016), and 4.4 acres (017), while the RFP Response Narrative reports approximately 3.8 acres (015), 4.1 acres (016), and 4.8 acres (017). The aggregate (12.7 acres / 553,212 sq ft) is consistent across documents. Open item: reconcile individual parcel acreages against the ALTA/NSPS survey to be delivered at closing.]

[Drafting Note — Parcel Acquisition History Conflict: Resolution R-2025-017, the RFP Response, and the TIF Memo state that the City acquired Parcels 015 and 016 through tax forfeiture proceedings in 2016 and Parcel 017 by direct purchase in 2018. The Phase II ESA states that Parcel 015 was acquired by tax forfeiture in 2016, while Parcels 016 and 017 were acquired by direct purchase in 2018. This discrepancy affects chain-of-title analysis and the title encumbrances that may follow each parcel into consolidation. Open item: confirm acquisition history for each parcel through title commitment review before conveyance.]

[Drafting Note — County Reference Inconsistency: Several documents refer to “Lake County” (RFP Response: “Lake County Recorder’s Office”; TIF Memo; Lakeshore Side Letter), while the parcel PIN format (12-24-300-xxx) and certain venue provisions reference Cook County. Open item: confirm the county of record for the Property and for parcel consolidation proceedings, and reconcile notice/venue provisions accordingly.]

B. RFP Selection. The City, through its Community Development Department, conducted a competitive Request for Proposals process for the redevelopment of the Property as a mixed-use transit-oriented development. Developer was selected as the preferred developer based upon its qualifications, experience, project proposal, and demonstrated financial capacity.

[Drafting Note — RFP Number Conflict: The Negotiated Term Sheet references “RFP No. 2024-CD-018,” while the RFP Response Narrative references “RFP No. 2024-CD-07.” Open item: confirm the correct RFP number and correct the recital accordingly.]

C. Resolution. On February 18, 2025, the City Council adopted Resolution No. R-2025-017 (the “Resolution”), granting conditional approval for the Project and authorizing the City Manager to negotiate and execute this Agreement, subject to the conditions set forth in Section 3 of the Resolution.

D. Term Sheet. The City Manager and the Developer’s Manager executed a non-binding Negotiated Term Sheet dated January 22, 2025 (the “Term Sheet”), setting forth the principal economic and legal terms proposed to govern this Agreement.

E. The Project. Developer proposes to develop the Property as a four-phase mixed-use transit-oriented development to be known as “Lakemont Station Commons” (the “Project”), with a total gross building area of approximately 1,620,000 square feet and a total estimated Project cost of approximately Four Hundred Twelve Million Dollars ($412,000,000).

F. Public Incentives. In consideration of Developer’s undertaking to redevelop the Property, remediate pre-existing environmental contamination, construct public infrastructure and amenities, and provide affordable housing and community benefits, the City has agreed to convey the Property at a discounted price and to provide the public incentives described in this Agreement.

G. Authority. The City represents that it has the authority, acting through its City Manager pursuant to the Resolution, to enter into this Agreement, subject to approval as to form by Corporation Counsel.

NOW, THEREFORE, in consideration of the mutual covenants and agreements set forth herein, and other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the Parties agree as follows:

## ARTICLE 1. DEFINITIONS AND INTERPRETATION

1.1 Definitions. In addition to terms defined elsewhere in this Agreement, the following capitalized terms shall have the meanings set forth below:

“Affordable Unit” means a residential dwelling unit restricted to occupancy by households earning at or below sixty percent (60%) of Area Median Income, as determined by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area.

“Affordable Housing Covenant” means the restrictive covenant recorded against the Property pursuant to Section 7.3, running with the land and restricting the Affordable Units for a minimum of thirty (30) years.

“AMI” means Area Median Income, as published annually by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area, or any successor designation.

“Appraised Value” means the as-is fair market value of the Property of Eighteen Million Four Hundred Thousand Dollars ($18,400,000), as established in the appraisal report of Crossland Appraisal Services dated January 15, 2025.

“Construction Lender” means First Prairie National Bank, or any successor construction lender approved by the City in accordance with Section 12.3.

“Construction Loan Documents” means the construction loan agreement, mortgage, assignment of leases and rents, assignment of contracts, assignment of TIF reimbursement rights, pledge of membership interests, guaranties, and other loan documents between Developer and the Construction Lender.

“ELUC” means an environmental land use control, in the form of a restrictive covenant, recorded against the Property in connection with the IEPA Voluntary Site Remediation Program.

“Force Majeure” has the meaning set forth in Section 14.1.

“Gross Building Area” means, with respect to any phase of the Project, the total gross square footage of buildings and improvements constructed in such phase, as set forth in Exhibit B.

“IEPA” means the Illinois Environmental Protection Agency.

“Lender-Approved Form” means, with respect to this Agreement or any ancillary document, a form that has been reviewed and approved in writing by the Construction Lender as acceptable to it.

“NFR Letter” means a No Further Remediation letter issued by the IEPA under the Voluntary Site Remediation Program.

“Permitted Exceptions” means the title exceptions set forth in Exhibit C, which shall be limited to: (i) real estate taxes not yet due and payable; (ii) standard utility and access easements that do not materially interfere with the development, use, or value of the Property; (iii) this Agreement; (iv) covenants and restrictions of the PD-TOD zoning ordinance; (v) environmental use controls or institutional controls recorded in connection with the IEPA NFR Letter and engineered barrier requirements, in each case as approved by the Construction Lender’s counsel; and (vi) such other exceptions as Developer and the Construction Lender may approve in writing.

[Drafting Note — Permitted Exceptions / Reversionary Interest: The Construction Loan Term Sheet (Section 4.2) prohibits, “under no circumstances,” any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, or fee simple subject to condition subsequent in favor of the City or any other party, and requires insurable fee simple absolute title. The definition of Permitted Exceptions above is drafted to exclude any such defeasible interest. This directly conflicts with Resolution R-2025-017, Condition #8, which contemplates a reversionary interest as a clawback mechanism. See Article 10 (Completion Assurance) for the Developer’s proposed alternative. This is the single most significant cross-document conflict and must be resolved with the City before execution or the construction loan cannot close.]

“Phase” means each of Phase I, Phase II, Phase III, and Phase IV of the Project, as described in Exhibit B.

“Phase I Substantial Completion” means Substantial Completion of Phase I.

“Project” has the meaning set forth in Recital E and as further described in Exhibit B.

“Property” has the meaning set forth in Recital A.

“Purchase Price” means Nine Million Two Hundred Thousand Dollars ($9,200,000).

“RAP” means a Remedial Action Plan for the environmental remediation of Parcel 12-24-300-016, submitted to and approved by the IEPA under the Voluntary Site Remediation Program.

“Substantial Completion” means, with respect to a Phase, the completion of construction of such Phase to the point where the building or improvements can be occupied and used for their intended purpose, as evidenced by the issuance of a temporary or final certificate of occupancy by the City’s Building Department, subject only to punch list items and minor incomplete work that do not prevent such occupancy and use.

[Drafting Note — Substantial Completion: The Term Sheet (Section 13) defines Substantial Completion generally as completion to the point of occupancy/use, evidenced by a temporary or final certificate of occupancy, with the precise definition to be set in the definitive Agreement. The definition above is drafted in favor of Developer by (i) expressly permitting a temporary certificate of occupancy to satisfy the standard and (ii) excluding punch list and minor incomplete work. Open item: confirm the City accepts a temporary CO as sufficient and agree on a defined dollar threshold or scope of “minor incomplete work” that does not delay Substantial Completion.]

“TIF Act” means the Illinois Tax Increment Allocation Redevelopment Act, 65 ILCS 5/11-74.4-1 et seq., as amended.

“TIF District” means the Lakemont Central Tax Increment Financing District established by City Ordinance No. 2019-42, expiring December 31, 2042.

“TIF Reimbursement” has the meaning set forth in Section 5.2.

“VSRP” means the IEPA Voluntary Site Remediation Program.

1.2 Interpretation. The headings used in this Agreement are for convenience only and shall not affect interpretation. References to “Sections,” “Articles,” and “Exhibits” are to sections, articles, and exhibits of this Agreement unless otherwise stated. The words “include,” “includes,” and “including” shall be deemed to be followed by “without limitation.” This Agreement shall be construed as if drafted jointly by the Parties; no presumption or burden of proof shall arise favoring or disfavoring either Party by virtue of authorship.

## ARTICLE 2. THE PROPERTY; CONVEYANCE; TITLE

2.1 Conveyance. Upon the satisfaction or waiver of the conditions precedent set forth in Article 11, the City shall convey the Property to Developer by special warranty deed, in form acceptable to Developer and the Construction Lender, for the Purchase Price of Nine Million Two Hundred Thousand Dollars ($9,200,000), representing fifty percent (50%) of the Appraised Value. The Purchase Price shall be due and payable at closing. Developer may fund the Purchase Price from equity, construction loan proceeds, or a combination thereof.

2.2 Title. The City shall deliver marketable and insurable fee simple absolute title to the Property, free and clear of all liens, encumbrances, restrictions, reversionary interests, rights of re-entry, possibilities of reverter, defeasible conditions, and other title defects or exceptions, except for the Permitted Exceptions. The City shall provide, at the City’s expense, a standard owner’s title insurance policy issued by a nationally recognized title insurance company in the amount of the Purchase Price, together with an ALTA lender’s title insurance policy in the amount of the Construction Loan, with such endorsements as the Construction Lender may require.

[Drafting Note — Title Cost Allocation: The Term Sheet (Section 4) provides that the City shall provide an owner’s title policy in the amount of the purchase price. The Construction Loan Term Sheet (Section 4.2) requires an ALTA lender’s policy in the amount of $210,000,000 with numerous endorsements. Open item: confirm which Party bears the cost of the lender’s policy and endorsements (the Loan Term Sheet’s “Expenses” provision states Borrower bears all Lender title insurance premiums, suggesting Developer pays for the lender policy). Clarify cost responsibility for both policies here.]

2.3 No Defeasible Fee; No Reversionary Interest. The City acknowledges and agrees that Developer’s title to the Property shall be fee simple absolute and indefeasible. The City shall not record, and this Agreement shall not create, any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other form of defeasible fee estate in favor of the City or any other party. The Parties acknowledge that any such interest would render Developer’s title uninsurable and would prevent the Construction Lender from making the construction loan. The completion-assurance mechanism set forth in Article 10 shall be the sole and exclusive remedy of the City in the event of a completion failure, and shall be in lieu of any reversionary or defeasible interest.

[Drafting Note — Central Conflict (Resolution #8 vs. Construction Lender vs. Lakeshore Side Letter): Resolution R-2025-017, Condition #8, requires Developer to grant the City a reversionary interest such that, if Phase I is not Substantially Complete within thirty-six (36) months of conveyance, fee simple title automatically reverts to the City (subject to a refund of the Purchase Price, net of damages). The Construction Loan Term Sheet (Sections 4.2, 7.1, 9, and 12) states that any reversionary or defeasible interest is “strictly prohibited,” would render the Loan “impossible to close,” and lists the imposition of any such interest as an Event of Default. The Lakeshore Side Letter (Section 7(d)) requires Investor consent to any clawback or reversionary interest and requires compatibility with the Construction Lender’s requirements. Section 2.3 and Article 10 reflect the Developer’s position that the reversionary interest must be eliminated and replaced with an alternative clawback mechanism. This is the threshold issue that must be resolved with the City (and approved by the Construction Lender and Lakeshore) before this Agreement can be executed and the loan can close.]

[Drafting Note — Timing Conflict (36-Month Reversion Trigger vs. Phase I Substantial Completion Deadline): Resolution #8 measures the reversion trigger from the date of conveyance (36 months), while the Phase I Substantial Completion deadline is September 30, 2028 (Term Sheet Section 13; Resolution recitals). If conveyance occurs in mid-2025 (e.g., June 2025), the 36-month reversion trigger would occur in June 2028 — approximately three months before the contractual Substantial Completion deadline of September 30, 2028. Under the Developer’s proposed alternative in Article 10, the completion-assurance mechanism is tied to the contractual Substantial Completion deadline (as extended by Force Majeure and City-caused delays), not to a fixed 36-month period from conveyance, thereby eliminating this internal inconsistency.]

2.4 Parcel Consolidation. The three parcels comprising the Property shall be consolidated into a single parcel of record prior to or concurrent with conveyance. The City shall be responsible for effectuating the consolidation, including resolution of any title encumbrances, easements, environmental liens, unresolved tax claims, or mechanic’s liens unique to the respective chains of title of the individual parcels arising from the City’s tax forfeiture and direct-purchase acquisitions.

[Drafting Note — Consolidation Risk (ESA Section 1.3): The Phase II ESA warns that each parcel has a distinct chain of title arising from different acquisition mechanisms (tax forfeiture for 015; direct purchase for 016/017 per ESA, or tax forfeiture for 015/016 and direct purchase for 017 per the Resolution), and that consolidation may be complicated by parcel-specific encumbrances. The ESA recommends a comprehensive per-parcel title review before consolidation. Section 2.4 allocates consolidation responsibility and encumbrance resolution to the City. Open item: confirm the City accepts this allocation and that the consolidation plat will expressly reference the ELUC area on former Parcel 017 by legal description (per ESA Section 4.3.3).]

2.5 Phased Conveyance. Notwithstanding Section 2.1, if the NFR Letter for Parcel 12-24-300-016 has not been issued by the closing date, the Parties shall cooperate in good faith to implement a phased conveyance under which Parcels 12-24-300-015 and 12-24-300-017 (or the portions of the Property not requiring the NFR Letter) are conveyed to Developer on the closing date, and Parcel 12-24-300-016 is conveyed to Developer promptly upon issuance of the NFR Letter, in each case subject to the terms of this Agreement and the Construction Loan Documents.

[Drafting Note — Phased Conveyance (ESA Sections 4.1.3, 5.2, 8.2(d)): The Phase II ESA recommends a phased conveyance approach — conveying clean Parcel 015 (and 017, before or after the engineered barrier) first, while Parcel 016 remediation proceeds — to allow early construction on clean parcels and reduce project-wide delay risk. The ESA notes this requires coordination with PD-TOD rezoning, parcel consolidation, and the Construction Lender’s mortgage scope. Resolution #8 and the Term Sheet (Section 4) contemplate a single consolidated conveyance. Open item: confirm with the City, the Construction Lender, and title company whether phased conveyance is feasible and whether the PD-TOD rezoning and consolidation can accommodate phased delivery or interim land-use approvals.]

## ARTICLE 3. THE PROJECT; DEVELOPMENT PROGRAM; PHASING

3.1 Development Program. Developer shall design, construct, and develop the Project in four (4) phases in accordance with the development program, square footages, unit counts, parking counts, and estimated hard construction costs set forth in Exhibit B, which is incorporated herein by reference. The Project shall include, in the aggregate: five hundred thirty (530) residential dwelling units, of which one hundred six (106) shall be Affordable Units; sixty-three thousand (63,000) square feet of retail space; two hundred eighty thousand (280,000) square feet of Class A office space; one hundred fifty (150) hotel rooms; one thousand four hundred thirty (1,430) structured parking spaces; a 2.5-acre public plaza; and a twenty-eight thousand (28,000) square foot community center.

[Drafting Note — Affordable Unit Count Conflict: Resolution R-2025-017 and the RFP Response specify 106 Affordable Units (64 in Phase I + 42 in Phase III), representing 20% of 530 total residential units. The Negotiated Term Sheet (Section 12) states “at least 100 affordable units” and separately states “Project Total: 106 affordable units out of 530.” The “at least 100” floor is lower than the 106-unit plan and lower than the 20% minimum in Resolution Condition #7. Section 3.1 locks in 106 units (which exceeds both the “at least 100” floor and the 20% minimum). Open item: confirm the City accepts 106 as the binding number and that the 20% minimum (not the “at least 100” floor) is the governing standard, so that any future unit-count adjustment maintains the 20% ratio.]

3.2 Phasing Schedule. Developer shall construct the Project in accordance with the following schedule:

| Phase | Commencement Deadline | Substantial Completion Deadline |
| --- | --- | --- |
| Phase I | Groundbreaking no later than March 1, 2026 | September 30, 2028 (30 months) |
| Phase II | Within 12 months of Phase I Substantial Completion | Within 24 months of Phase II commencement |
| Phase III | Within 12 months of Phase II Substantial Completion | Within 30 months of Phase III commencement |
| Phase IV | Concurrent with Phase III commencement | Within 24 months of Phase IV commencement |

3.3 Extension for City-Caused and Regulatory Delays. The commencement and Substantial Completion deadlines set forth in Section 3.2 shall be extended on a day-for-day basis for any delay caused by the City’s failure to perform its obligations under this Agreement (including failure to complete rezoning, parcel consolidation, off-site infrastructure, or conveyance) or by delays in governmental approvals required to be obtained by the City. Such extensions shall be in addition to, and shall not be counted against, the Force Majeure cap set forth in Section 14.3.

[Drafting Note — Groundbreaking Deadline vs. Conveyance/Remediation Timing: The Phase I groundbreaking deadline of March 1, 2026 is fixed, but conveyance is targeted for mid-2025 and is itself contingent on rezoning, parcel consolidation, and IEPA approval of the RAP for Parcel 016 (Resolution Condition #2; Term Sheet Section 4). The Phase II ESA estimates 14–18 months from VSRP enrollment to NFR Letter issuance. If VSRP enrollment begins in Q1 2025, the NFR Letter may not issue until Q2–Q4 2026 — after the March 1, 2026 groundbreaking deadline. Section 3.3 protects Developer by extending deadlines for City-caused and regulatory delays. Open item: confirm the City agrees that delays in rezoning, consolidation, RAP approval, or NFR issuance extend the groundbreaking and Substantial Completion deadlines, and that such delays are not counted against the Force Majeure cap.]

3.4 Subsequent-Phase Financing. Developer’s obligation to commence Phase II, Phase III, and Phase IV is expressly conditioned upon Developer’s receipt of construction financing or other capital sufficient to complete such Phase on terms satisfactory to Developer. Developer shall not be in default for failure to commence a subsequent Phase if Developer has performed its obligations with respect to all prior Phases and the failure to commence is due solely to the unavailability of financing on commercially reasonable terms, provided that Developer uses commercially reasonable efforts to obtain such financing.

[Drafting Note — Later-Phase Financing Risk: The Construction Loan Term Sheet (Section 2.1) makes availability for Phases III and IV subject to a “separate supplemental commitment or amendment, to be negotiated at the appropriate time,” and the Term Sheet/RFP identify approximately $58,400,000 in additional debt/mezzanine financing for later phases (structure and terms undetermined). The Lakeshore Side Letter (Section 7(a)) requires Investor consent for Project indebtedness exceeding $268,400,000 in the aggregate. Section 3.4 protects Developer by making subsequent-phase commencement contingent on financing. Open item: confirm the City accepts a financing condition for later phases and that failure to secure later-phase financing (after performing earlier phases) is not a default triggering termination or clawback.]

3.5 Design Review. Developer shall submit plans and specifications for each Phase to the City for design review and approval in accordance with the PD-TOD zoning ordinance and the procedures to be set forth in Exhibit D. The City shall review and approve or provide written comments on submitted plans within [thirty (30)] business days of submission. Plans deemed approved if no written objection is provided within such period. The City’s approval shall not be unreasonably withheld, conditioned, or delayed.

[Drafting Note — Design Review: The Term Sheet (Section 19) contemplates “design review and approval procedures” in the definitive Agreement but does not specify timelines. Section 3.5 establishes a deemed-approval mechanism favorable to Developer. Open item: negotiate the review period and the scope of City design-review authority versus ministerial PD-TOD compliance review.]

## ARTICLE 4. PUBLIC INCENTIVES

4.1 Land Write-Down. The conveyance of the Property at the Purchase Price of $9,200,000, representing a fifty percent (50%) discount from the Appraised Value, constitutes a land write-down incentive with a value of Nine Million Two Hundred Thousand Dollars ($9,200,000). The land write-down shall not be charged against, and shall not reduce, the TIF Reimbursement cap set forth in Section 5.2.

[Drafting Note — Land Write-Down vs. TIF Cap (TIF Memo Section VII): The Corporation Counsel TIF Memo recommends that the development agreement “clearly specify whether the land write-down is charged against the TIF cap or constitutes a separate incentive funded from another source,” because if recorded as a TIF expenditure it counts against the $48,000,000 cap. Section 4.1 provides that the land write-down is a separate incentive not charged against the TIF cap — favorable to Developer. Open item: confirm the City agrees the land write-down is funded from a source other than the Special Tax Allocation Fund and does not reduce the TIF cap.]

4.2 Tax Increment Financing Reimbursement.

- Pledge. The City shall pledge up to Forty-Eight Million Dollars ($48,000,000) in tax increment revenues over the remaining life of the TIF District to reimburse Developer for eligible TIF costs incurred in connection with the Project (the “TIF Reimbursement”). Eligible TIF costs shall include, without limitation: public infrastructure improvements, environmental remediation costs, parking structure construction costs, the public plaza and community center, and other eligible project costs under the TIF Act.

- Pay-As-You-Go. TIF Reimbursement shall be on a pay-as-you-go basis. Developer shall front all eligible costs and shall be reimbursed annually from available tax increment as generated by the Project and other developments within the TIF District. The City shall not issue TIF bonds or notes for the Project.

- Priority of Reimbursement. TIF Reimbursement shall be made in the following priority order: (i) first, environmental remediation costs for Parcels 016 and 017; (ii) second, public infrastructure costs, including the City’s off-site infrastructure commitment and Developer’s eligible on-site infrastructure expenditures; (iii) third, the public parking structure, public plaza, and community center costs associated with Phase IV; and (iv) fourth, all other eligible costs.

- Not a General Obligation. TIF Reimbursement is payable solely from available increment deposited in the Special Tax Allocation Fund and is not a general obligation of the City. The City shall have no obligation to make TIF Reimbursement payments from general revenue or any other source.

- Good-Faith Effort to Extend. If, as of December 31, 2038, cumulative TIF Reimbursement is tracking materially below the projections supporting the $48,000,000 cap, the City shall use good-faith efforts to seek an extension of the TIF District or the adoption of a successor TIF district, to the extent legally permissible, in order to maximize reimbursement of Developer’s eligible costs.

- Shortfall Not a Default. A shortfall in TIF Reimbursement, whether due to insufficient increment generation, the expiration of the TIF District, assessment appeals, or otherwise, shall not constitute a default by the City under this Agreement, except to the extent such shortfall results from the City’s breach of its obligations under this Section 5.2.

[Drafting Notes — TIF Reimbursement Risk (TIF Memo Sections IV, VI, VII): (1) The Corporation Counsel TIF Memo concludes that the $48,000,000 cap “may not be fully reachable” given the December 31, 2042 expiration and the Phase I property tax abatement’s effect on increment. Under an adjusted scenario incorporating the abatement, cumulative increment through 2042 is estimated at approximately $38–42 million — potentially $6–10 million short of the cap. (2) The Memo recommends the priority structure reflected in Section 5.2(c), with environmental remediation reimbursed first. (3) The Memo recommends a City covenant to use good-faith efforts to seek a TIF extension if reimbursement is tracking below projections by a benchmark date (the Memo suggests 2038), reflected in Section 5.2(e). (4) The Memo recommends an express provision that a TIF shortfall is not a City default, reflected in Section 5.2(f). (5) The Memo flags an internal tension: the Phase I abatement benefits Developer by reducing property taxes but simultaneously reduces the TIF increment available for reimbursement. Open items: (i) confirm the City accepts the priority structure and the good-faith extension covenant; (ii) consider whether the abatement can be structured to apply only to the non-TIF-captured portion of the tax bill (if legally permissible) to mitigate the abatement-TIF tension; (iii) Developer should recognize that, under pay-as-you-go, Developer bears the timing and shortfall risk, and should size its pro forma accordingly.]

4.3 Infrastructure Cost-Sharing.

- City Off-Site Infrastructure. The City shall fund Twelve Million Five Hundred Thousand Dollars ($12,500,000) for off-site infrastructure improvements, including the widening of Lakemont Station Boulevard, installation of a new traffic signal at the Oak Street intersection, extension of the water main, and upgrade of sanitary sewer capacity. The City’s off-site infrastructure funding shall be appropriated and disbursed according to a schedule coordinated with the phased construction timeline and set forth in Exhibit E. The City’s off-site infrastructure commitment shall not be charged against, and shall not reduce, the TIF Reimbursement cap.

[Drafting Note — Infrastructure Funding Source (TIF Memo Section VII): The TIF Memo recommends specifying whether the City’s $12,500,000 infrastructure commitment is funded from general revenue/capital funds (in which case it does not reduce the TIF cap) or from TIF (in which case it counts against the cap). Section 4.3(a) provides that the City’s commitment is not charged against the TIF cap — favorable to Developer. Open item: confirm the City’s funding source and that the commitment is separate from the TIF cap.]

- Developer On-Site Infrastructure. Developer shall fund Eight Million Three Hundred Thousand Dollars ($8,300,000) for on-site infrastructure improvements, including internal roadways, utilities, stormwater management, pedestrian pathways, and landscape improvements. Developer’s on-site infrastructure expenditures shall be eligible for TIF Reimbursement to the extent they serve a documented public purpose, supported by certified cost documentation.

- City Performance Obligation. The City’s failure to fund or complete its off-site infrastructure obligations in accordance with the schedule in Exhibit E shall constitute a material default by the City and shall entitle Developer to the remedies set forth in Article 13, including extension of the Project deadlines under Section 3.3.

4.4 Property Tax Abatement. The City shall provide a twelve (12)-year declining property tax abatement on Phase I improvements only, as follows: Years 1–4 — seventy-five percent (75%) abatement; Years 5–8 — fifty percent (50%) abatement; Years 9–12 — twenty-five percent (25%) abatement; Year 13 and thereafter — full assessment with no abatement. The abatement shall apply to the incremental increase in assessed value attributable to the Phase I improvements, measured from the pre-development base equalized assessed value.

[Drafting Note — Abatement Scope and Later Phases: The Term Sheet (Section 18.4) confirms the abatement applies to Phase I only and that no abatement is provided for Phases II–IV, with later-phase incentives “to be addressed during negotiation of the definitive Agreement.” Open item: Developer may seek abatement or additional incentives for later phases; this is left open for negotiation.]

4.5 Building Permit Fee Waiver. The City shall waive building permit fees for Phase I and Phase II of the Project, with an estimated combined value of One Million Four Hundred Thousand Dollars ($1,400,000) ($920,000 for Phase I and $480,000 for Phase II). No permit fee waiver is contemplated for Phase III or Phase IV. The permit fee waivers shall not be charged against the TIF Reimbursement cap.

## ARTICLE 5. ENVIRONMENTAL MATTERS

5.1 City Indemnification for Pre-Existing Conditions. The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to pre-existing environmental conditions on the Property, including but not limited to the BTEX and TCE contamination on Parcel 12-24-300-016 and the metals contamination in fill material on Parcel 12-24-300-017, as identified in the Phase II Environmental Site Assessment prepared by Greenfield Environmental Consultants LLC dated November 8, 2024, including third-party claims, governmental enforcement actions, and contribution or cost-recovery actions under federal or state environmental laws. This indemnification shall survive the expiration or termination of this Agreement.

[Drafting Note — Environmental Indemnity: The Term Sheet (Section 16) and Resolution recitals provide for City indemnification of Developer for pre-existing environmental conditions. The Phase II ESA (Sections 4.2.4, 8.2) confirms the contamination is pre-existing and attributable to the former Lakemont Ironworks (ceased 2009), that the City acquired the parcels with knowledge of the conditions, and that the City bears primary responsible-party status under the Illinois Environmental Protection Act. Section 5.1 reflects the Developer’s position that the City bears full responsibility for pre-existing contamination. Open item: confirm the scope of the indemnity (e.g., whether it is capped, whether it covers cost overruns, and the survival period) and whether the City requires any carve-outs.]

5.2 Remediation Responsibility and Cost Allocation.

- Performance. The City shall be responsible for performing, or causing to be performed, the environmental remediation of Parcel 12-24-300-016 under the VSRP and the installation of the engineered barrier on Parcel 12-24-300-017, in each case in accordance with the recommendations of the Phase II ESA and the RAP approved by the IEPA, and shall engage and supervise the environmental consultant and remediation contractors and serve as the named applicant on the VSRP enrollment and NFR Letter application. [Alternatively, Developer shall perform the remediation as the City’s agent, with all costs funded by the City or reimbursed to Developer on a priority basis through TIF Reimbursement and/or direct City funding.]

- Cost. The City shall bear the cost of environmental remediation, currently estimated at Three Million One Hundred Forty Thousand Dollars ($3,140,000) ($2,800,000 for Parcel 016 and $340,000 for Parcel 017). Environmental remediation costs are eligible TIF costs and shall be reimbursed on a first-priority basis pursuant to Section 5.2(c) of Article 4.

- Cost Overruns. The City shall bear the cost of any remediation cost overruns above the estimates set forth above. The Parties acknowledge that the Phase II ESA recommends budgeting an additional contingency of twenty-five to thirty-five percent (25–35%) above the base estimate, bringing the potential total cost exposure for Parcel 016 remediation alone to approximately $3.5–3.8 million, and the combined total to approximately $3.8–4.2 million. The City shall be responsible for funding such overruns.

[Drafting Notes — Remediation Cost/Overrun Allocation (ESA Sections 4.2.4, 5.3, 8.2): (1) The Phase II ESA expressly states that the allocation of remediation costs between the City (current owner) and Developer (prospective purchaser) “is beyond the scope of this environmental assessment and should be addressed through appropriate contractual provisions,” and recommends that the transactional documents (i) clearly identify which party performs the remediation, engages the consultant, and is the VSRP applicant; (ii) establish whether the Developer or City bears the upfront cost and the reimbursement mechanism; and (iii) establish a clear mechanism for allocating cost overruns, with the ESA recommending 25–35% additional contingency. (2) The Lakeshore Side Letter (Section 4.3(d)) requires Investor consent for any acceptance of environmental remediation obligations exceeding $3,140,000 without a corresponding increase in TIF reimbursement or direct City funding. Sections 5.2(a)–(c) allocate remediation performance, cost, and overruns to the City — favorable to Developer and consistent with the pre-existing nature of the contamination. Open items: (i) confirm the City accepts full remediation cost and overrun responsibility (the City may seek to cap its exposure or require Developer to perform with TIF reimbursement); (ii) if Developer performs the remediation, ensure the reimbursement mechanism is reliable and front-loaded; (iii) obtain Lakeshore consent if any structure shifts remediation cost to Developer above $3,140,000.]

5.3 NFR Letter; VSRP. IEPA approval of the RAP for Parcel 12-24-300-016 is a condition precedent to conveyance of Parcel 12-24-300-016, as set forth in Article 11. The NFR Letter for Parcel 12-24-300-016 shall be obtained prior to residential development on that parcel. The Parties shall cooperate to sequence remediation, conveyance, and construction so as to minimize delay to the Project schedule, including through the phased conveyance mechanism in Section 2.5.

[Drafting Note — NFR Letter Timing (ESA Sections 5.2, 8.2(d); Loan Term Sheet Section 7.1): Resolution Condition #2 requires IEPA approval of the RAP (not the NFR Letter) prior to conveyance. The Construction Loan Term Sheet (Section 7.1) requires, for Parcel 016, either (a) an NFR Letter, or (b) VSRP enrollment with an approved RAP plus an environmental escrow or insurance product satisfactory to the Lender (covering $2,800,000 plus 25% contingency = $3,500,000), prior to any loan draw-down for construction on that parcel. The ESA estimates 14–18 months from VSRP enrollment to NFR Letter issuance. Open items: (i) confirm whether the RAP approval (Resolution standard) or the NFR Letter (ESA/Lender practical standard) is the conveyance trigger for Parcel 016; (ii) if the NFR Letter is required before conveyance of 016, the 14–18 month timeline may push 016 conveyance into 2026–2027, reinforcing the need for phased conveyance under Section 2.5; (iii) coordinate the environmental escrow/insurance product with the Construction Lender.]

5.4 Environmental Insurance. Developer shall obtain pollution legal liability insurance in an amount not less than Ten Million Dollars ($10,000,000), naming the City and the Construction Lender as additional insureds, with a policy term covering the full construction period and a three-year extended reporting period.

[Drafting Note — Environmental Insurance (Loan Term Sheet Section 4.3): The Construction Loan Term Sheet requires $10,000,000 pollution legal liability insurance naming the Lender as additional insured, with a three-year extended reporting period. Section 5.4 adds the City as an additional insured. Open item: confirm the City’s required insured status and whether the City requires any separate environmental insurance or escrow.]

5.5 Institutional Controls. Any ELUC or institutional control recorded against the Property in connection with the VSRP or the engineered barrier shall be reviewed and approved by Developer’s counsel and the Construction Lender’s counsel prior to recording, and shall be reflected in the Permitted Exceptions. The PD-TOD zoning standards shall restrict below-grade construction in the engineered barrier area on former Parcel 017 unless proper environmental protocols (including IEPA notification and an approved soil management plan) are followed.

[Drafting Note — Institutional Controls (ESA Sections 4.3.3, 6.2): The ESA notes that the ELUC to be recorded against Parcel 017 constitutes a title encumbrance that will apply to the specific geographic area of former Parcel 017 regardless of consolidation, and recommends that the consolidation plat reference the ELUC area by legal description and that PD-TOD development standards account for the engineered barrier (restricting below-grade construction). Section 5.5 incorporates these recommendations. Open item: confirm the PD-TOD ordinance accommodates these restrictions and that the ELUC is acceptable to the Construction Lender and title company.]

## ARTICLE 6. CITY OBLIGATIONS

6.1 Rezoning. The City shall, at its sole cost and expense, complete the rezoning of the Property from M-2 (General Manufacturing) to PD-TOD (Planned Development–Transit Oriented District), including application filing, plan commission review, public hearings, and City Council action, so that the rezoning is adopted by ordinance and effective prior to the execution of this Agreement. The rezoning shall accommodate the density, building heights, use mix (including residential, office, retail, hotel, and public uses), and design standards contemplated by the Project.

[Drafting Note — Rezoning as City Obligation: Resolution Condition #5 requires the rezoning to be completed and effective prior to execution of this Agreement, and authorizes the City Manager to initiate rezoning proceedings. The RFP Response estimates the rezoning process at four to six months. Section 6.1 frames rezoning as a City obligation with cost borne by the City. Open item: confirm the City accepts rezoning as its sole responsibility and that rezoning delays extend the Project deadlines under Section 3.3.]

6.2 Parcel Consolidation. The City shall complete the consolidation of the three parcels into a single parcel of record prior to or concurrent with conveyance, as set forth in Section 2.4.

6.3 Off-Site Infrastructure. The City shall fund and complete the off-site infrastructure improvements in accordance with Section 4.3 and Exhibit E.

6.4 TIF Administration. The City shall administer the TIF Reimbursement in accordance with Section 5.2, including establishing and maintaining the Special Tax Allocation Fund, processing Developer’s reimbursement requests, and using good-faith efforts to seek a TIF extension if required by Section 5.2(e).

6.5 Community Center Acceptance. Upon Substantial Completion of Phase IV, the City shall accept conveyance of the community center in fee simple, in accordance with Section 7.5.

## ARTICLE 7. DEVELOPER OBLIGATIONS

7.1 Construction Standards; LEED. Developer shall construct the Project in accordance with plans and specifications approved under Section 3.5 and all applicable laws, codes, and ordinances. All buildings constructed as part of the Project shall achieve LEED Gold certification, or an equivalent green building certification as approved by the City in writing. Developer shall register each building with the U.S. Green Building Council prior to commencement of construction of the applicable building.

[Drafting Note — LEED Equivalent: Resolution Condition #6 and the Term Sheet (Section 11.2) require LEED Gold “or an equivalent green building certification as determined acceptable by the Director of the Community Development Department.” Section 7.1 preserves the “equivalent” flexibility. Open item: define the process and standard for City approval of an equivalent certification.]

7.2 Prevailing Wage. Developer shall comply with the Illinois Prevailing Wage Act (820 ILCS 130/0.01 et seq.) with respect to all construction work performed on the Project that constitutes “public works” within the meaning of said Act. Developer shall include prevailing wage requirements in all contracts and subcontracts for such work, maintain certified payroll records, and make such records available to the City and the Illinois Department of Labor upon request.

[Drafting Notes — Prevailing Wage Scope Conflict (TIF Memo Section V; Term Sheet Section 11.1; Resolution Section 8): (1) The Corporation Counsel TIF Memo recommends that, given the substantial public financial assistance (land write-down, TIF, abatement, fee waivers), the Prevailing Wage Act “likely applies to all construction activity on the project site, not merely the TIF-reimbursed components,” and notes that the Term Sheet’s “all construction” language converts a debatable statutory question into a contractual obligation. (2) The Term Sheet (Section 11.1) states prevailing wage shall apply to “all construction performed on the Project.” (3) Resolution Section 8 references prevailing wage for “public works.” (4) Section 7.2 is drafted to limit the contractual prevailing wage obligation to work that constitutes “public works” under the Act — favorable to Developer, which may reduce costs on purely private components (market-rate residential, office, hotel). This is a point the City is likely to resist. Open items: (i) negotiate the scope of the contractual prevailing wage obligation — Developer’s counsel (Thornfield & Pratt) is expected to resist broad application to purely private components; (ii) if the City insists on “all construction,” Developer should seek corresponding concessions; (iii) note that broad prevailing wage application may increase construction costs on private components and affect the Lakeshore Minimum IRR (Side Letter Section 3).]

7.3 Affordable Housing. Developer shall include not less than one hundred six (106) Affordable Units across the Project, representing not less than twenty percent (20%) of the total residential dwelling units, restricted to households earning at or below sixty percent (60%) of AMI. Affordable Units shall be distributed proportionally across unit types and shall not be segregated or concentrated. Affordable Units shall be comparable in design, finishes, and amenity access to market-rate units within the same building. Affordability restrictions shall remain in effect for a minimum of thirty (30) years from the date of issuance of the certificate of occupancy for the applicable phase, memorialized by the Affordable Housing Covenant recorded against the Property. Developer shall comply with the City’s Affordable Housing Compliance Program and provide annual income certification documentation.

[Drafting Note — Affordable Housing: See drafting note under Section 3.1 regarding the “at least 100” vs. 106 conflict. Section 7.3 locks in 106 units / 20% / 30-year restriction, consistent with Resolution Condition #7 and the Term Sheet (Section 12). Open item: confirm the form of the Affordable Housing Covenant and the monitoring/compliance procedures.]

7.4 Community Benefits.

- Local Hiring Goal. Developer shall use commercially reasonable efforts to achieve a goal of thirty-five percent (35%) Lakemont residents for construction workforce employment across all phases of the Project, measured on a cumulative project-wide basis. Developer shall submit quarterly reports to the City’s Community Development Department documenting local hiring percentages. Failure to achieve the 35% goal shall not, in and of itself, constitute a default under this Agreement, provided that Developer demonstrates good-faith efforts to achieve the goal, including posting job openings with the City’s workforce development partners, attending local job fairs, and providing reasonable notice of hiring opportunities.

- First-Source Hiring. Developer and its commercial tenants shall partner with the Lakemont Workforce Center for the recruitment, training, and hiring of individuals to fill permanent employment positions created within the Project, using commercially reasonable efforts.

- Living Wage. Developer shall ensure that all permanent employees directly employed by Developer in retail and hotel operations within the Project are compensated at a wage rate of not less than Seventeen Dollars and Fifty Cents ($17.50) per hour. Developer shall use commercially reasonable efforts to require its commercial tenants to adopt comparable wage standards, through lease provisions where commercially practicable.

[Drafting Notes — Community Benefits Conflict (Resolution Condition #3 vs. Term Sheet Section 9): (1) Resolution Condition #3 mandates, as a minimum: (i) a 35% local hiring goal; (ii) a living wage of $17.50/hour for “all permanent employees employed at retail establishments and hotel operations”; and (iii) a first-source hiring program with the Lakemont Workforce Center. (2) The Term Sheet (Section 9) addresses only local hiring as a goal (with good-faith compliance and no-default-on-failure language) and is silent on living wage and first-source hiring. (3) Section 7.4 is drafted to favor Developer by: (i) keeping local hiring as a good-faith goal that does not trigger default on failure (per the Term Sheet); (ii) limiting the binding living wage obligation to Developer’s own direct employees, with only a commercially reasonable effort to extend to tenants (Developer does not control tenant wage decisions and should not guarantee them); and (iii) making first-source hiring a commercially reasonable effort rather than a hard mandate. Open items: (i) the City is likely to insist on the broader Resolution language (mandatory living wage for all retail/hotel employees, including tenants); Developer should resist guaranteeing tenant wages it cannot control; (ii) confirm whether the living wage obligation applies to hotel brand/flag operators and franchise employees; (iii) note that the hotel flag is “to be determined” (Term Sheet Section 3.3), and wage obligations may affect flag selection.]

7.5 Community Center Conveyance. Upon Substantial Completion of Phase IV, Developer shall convey the 28,000-square-foot community center to the City in fee simple, by special warranty deed, at no additional cost to the City. The community center shall be designed in consultation with the City’s Parks and Recreation Department and shall be conveyed in substantially complete condition, subject to punch list items. The City shall accept conveyance within [thirty (30)] days of notice of Substantial Completion.

[Drafting Note — Community Center “At No Additional Cost”: The Resolution, RFP Response, and Term Sheet provide that the community center is to be conveyed to the City “upon completion at no additional cost” / “fully furnished and equipped.” The cost of the community center is included within the $71,000,000 Phase IV hard construction cost. Open items: (i) clarify whether “fully furnished and equipped” is required and, if so, the budget and standard for furnishings/equipment; (ii) confirm the City’s acceptance obligation and timing; (iii) address the City’s ongoing operational and maintenance responsibilities post-conveyance; (iv) confirm whether the community center conveyance is a condition to Phase IV Substantial Completion or a post-completion obligation.]

7.6 Insurance. Developer shall maintain, or cause its general contractor to maintain, throughout the construction period for each Phase, the following minimum insurance coverages: (a) Commercial General Liability of not less than $10,000,000 per occurrence and $25,000,000 in the aggregate; (b) Umbrella/Excess Liability of $25,000,000; (c) Builder’s Risk at full replacement value of each Phase under construction; (d) Workers’ Compensation at statutory limits; (e) Automobile Liability of $5,000,000 combined single limit; (f) Professional Liability (Architect/Engineer) of $5,000,000; and (g) Pollution Legal Liability of $10,000,000 (per Section 5.4). The City and the Construction Lender shall be named as additional insureds/loss payees, as applicable. All carriers shall be rated A- VII or better by A.M. Best. All policies shall provide not less than thirty (30) days’ prior written notice of cancellation or material modification.

[Drafting Note — Insurance Conflict (Term Sheet Section 11.3 vs. Loan Term Sheet Section 5): The Term Sheet requires CGL of $10,000,000 per occurrence / $20,000,000 aggregate, and does not require Professional Liability or Pollution Legal Liability. The Construction Loan Term Sheet requires CGL of $10,000,000 per occurrence / $25,000,000 aggregate, plus Professional Liability ($5,000,000) and Pollution Legal Liability ($10,000,000). Section 7.6 aligns to the more comprehensive Loan Term Sheet requirements (higher CGL aggregate, professional and pollution coverage) to satisfy the Lender, and adds the City as additional insured. Open item: confirm the City accepts the higher CGL aggregate and the additional coverages, and clarify cost responsibility (Developer bears these premiums).]

7.7 Reporting. Developer shall provide quarterly construction progress reports to the City’s Community Development Department, including percentage of completion, updated schedule, and identification of delays, within thirty (30) days following the end of each calendar quarter during which active construction is occurring.

## ARTICLE 8. PERFORMANCE SECURITY

8.1 Performance Security. Prior to conveyance of the Property, Developer shall post a performance bond in the amount of Fifteen Million Dollars ($15,000,000), issued by Ridgepoint Surety Corporation or another surety company reasonably acceptable to the City, or an irrevocable standby letter of credit in the equivalent amount issued by a nationally recognized financial institution acceptable to the City (collectively, the “Performance Security”). The Performance Security shall secure Developer’s obligation to commence and substantially complete Phase I in accordance with this Agreement.

8.2 Form and Draw Mechanics. The amount, form, conditions, and draw mechanics of the Performance Security shall be set forth in Exhibit F, in form and substance reasonably acceptable to the City, Developer, and the Construction Lender.

8.3 Release. The Performance Security shall be maintained continuously from the date of conveyance until Phase I Substantial Completion. Upon Phase I Substantial Completion, the City shall release and return the Performance Security to Developer within thirty (30) days following written request and verification of Substantial Completion by the City.

8.4 Burn-Down. The Performance Security shall be subject to a burn-down schedule, pursuant to which the amount of the Performance Security shall be reduced as Phase I construction milestones are achieved, as set forth in Exhibit F.

[Drafting Notes — Performance Security (Resolution Condition #4; Term Sheet Section 8; Loan Term Sheet Sections 4.1, 7.1; Lakeshore Side Letter Section 4.3(e)): (1) Resolution Condition #4 and the Term Sheet require a $15,000,000 performance bond or LC securing Phase I completion, posted prior to conveyance and released upon Phase I Substantial Completion. (2) The Construction Loan Term Sheet requires the $15,000,000 bond/LC as a condition precedent to loan closing and assigns it to the Lender as collateral. (3) The Lakeshore Side Letter requires Investor consent for any modification to the performance bond/LC requirements. (4) Sections 8.1–8.4 preserve Developer’s flexibility to use either a bond or an LC, provide for release upon Phase I Substantial Completion, and add a burn-down schedule favorable to Developer. Open items: (i) reconcile the City’s and the Construction Lender’s respective interests in the Performance Security — if the Lender takes an assignment of the bond/LC as collateral, confirm the City’s security position and whether a separate instrument or shared arrangement is required; (ii) confirm the burn-down schedule and milestone triggers in Exhibit F; (iii) obtain Lakeshore consent for the final form.]

## ARTICLE 9. COMPLETION ASSURANCE (IN LIEU OF REVERSIONARY INTEREST)

9.1 No Reversionary Interest. As provided in Section 2.3, the City shall not hold, and this Agreement shall not create, any reversionary interest, right of re-entry, possibility of reverter, or other defeasible fee interest in the Property. The mechanisms set forth in this Article 9 shall constitute the sole and exclusive remedies of the City in the event of a Phase I completion failure, and are expressly intended to satisfy the City’s legitimate interest in ensuring timely Phase I completion while preserving Developer’s fee simple absolute title and the Construction Lender’s first-priority security interest.

9.2 Liquidated Damages. In the event Developer fails to achieve Phase I Substantial Completion by the Phase I Substantial Completion deadline (as extended pursuant to Section 3.3 and Article 14), and such failure continues uncured following the expiration of all applicable cure periods (including the Construction Lender’s cure rights under Article 15), Developer shall pay to the City liquidated damages in the amount of [•] per [month/day] of delay, representing the Parties’ reasonable pre-estimate of the City’s actual damages resulting from the completion delay. The Parties acknowledge and agree that the City’s actual damages in the event of a completion delay would be difficult to ascertain and that the liquidated damages amount is a reasonable pre-estimate and not a penalty.

9.3 Repurchase Option. In lieu of, and as an alternative to, liquidated damages, and only upon (a) Developer’s failure to achieve Phase I Substantial Completion within [•] months following the Phase I Substantial Completion deadline (as extended), (b) expiration of all cure periods (including the Construction Lender’s extended cure period under Article 15), and (c) the Construction Lender’s prior written consent or full satisfaction of the outstanding Construction Loan balance, the City shall have a contractual option to repurchase the Property at a price equal to the lesser of (i) the Purchase Price paid by Developer or (ii) the then-current fair market value of the Property as determined by an independent MAI appraiser mutually selected by the Parties. The repurchase option shall be subordinate to the Construction Lender’s mortgage and shall be exercisable only after the Construction Lender’s security interest has been satisfied or consented to.

9.4 Enhanced Completion Guaranty. Developer shall cause its principals to provide an enhanced completion guaranty guaranteeing completion of Phase I within the agreed timeframe, providing the City with a direct contractual remedy against the guarantors (and their assets, other than the Property) in the event of a completion failure, in form and substance set forth in Exhibit G.

[Drafting Notes — Completion Assurance / Central Conflict Resolution (Resolution #8 vs. Loan Term Sheet Section 12 vs. Lakeshore Side Letter Section 7(d)): (1) The Construction Loan Term Sheet (Section 12) expressly proposes the alternatives reflected in Article 9 — (i) a contractual repurchase option exercisable only after Lender consent or Loan satisfaction; (ii) a performance escrow / additional LC; (iii) liquidated damages; (iv) an enhanced completion guaranty; and (v) a right of first refusal — as substitutes for the reversionary interest. (2) Article 9 combines liquidated damages (Section 9.2), a repurchase option exercisable only post-Lender-satisfaction (Section 9.3), and an enhanced completion guaranty (Section 9.4) — all of which preserve Developer’s fee simple absolute title and the Lender’s first-priority lien. (3) The Lakeshore Side Letter (Section 7(d)) requires Investor consent to any clawback/repurchase mechanism and requires compatibility with the Construction Lender’s requirements; the repurchase option’s subordination to the Lender’s mortgage is consistent with this. Open items: (i) negotiate the liquidated damages amount and the delay period before the repurchase option becomes exercisable (bracketed [•] amounts); (ii) confirm the City accepts this alternative structure in lieu of the reversionary interest required by Resolution #8 — this requires the City Council to depart from Condition #8, likely by resolution or by treating this Article as satisfying the “form, terms, and conditions” of the clawback to be “set forth in detail in the Development Agreement” (Resolution #8); (iii) obtain Construction Lender written confirmation that Article 9 is acceptable; (iv) obtain Lakeshore consent; (v) confirm the enhanced completion guaranty is acceptable to the guarantors (Pellegrini/Pellegrini Family Trust) and consistent with the Loan Term Sheet’s completion guaranty.]

## ARTICLE 10. CONDITIONS PRECEDENT

10.1 Conditions Precedent to Execution. The execution of this Agreement is subject to the satisfaction or waiver of the following conditions: (a) rezoning of the Property from M-2 to PD-TOD approved by the City Council and effective; (b) parcel consolidation completed or authorized; (c) IEPA approval of the RAP for Parcel 12-24-300-016; (d) Developer’s demonstration of committed equity of at least $85,000,000; (e) approval of this Agreement by the City Council; and (f) confirmation from the Construction Lender that this Agreement is in a form acceptable to the Lender.

[Drafting Note — Equity Demonstration Timing Conflict (Resolution Condition #1(a) vs. Term Sheet Section 18.2): Resolution Condition #1(a) requires Developer to demonstrate $85,000,000 in committed equity within sixty (60) days of adoption of the Resolution (i.e., on or before April 19, 2025), verified by Clearmont Accounting Group LLP. The Term Sheet (Section 18.2) requires demonstration within sixty (60) days of City Council approval of the definitive Agreement (a later date, approximately June–July 2025). The RFP Response indicates equity commitment letters were dated November 2024 (Lakeshore Nov. 22, 2024; Pellegrini Family Trust Nov. 18, 2024), suggesting the equity is already committed. Open items: (i) confirm whether the April 19, 2025 deadline has been satisfied or whether the Term Sheet’s later trigger governs; (ii) confirm the form of equity demonstration (subscription agreements, fund commitment letters, bank statements) and the Clearmont verification requirement.]

10.2 Conditions Precedent to Closing. The obligation of the Parties to close the conveyance is subject to the satisfaction or waiver of the following conditions: (a) execution of this Agreement and approval by the City Council; (b) completion of rezoning; (c) completion or authorization of parcel consolidation; (d) IEPA approval of the RAP for Parcel 12-24-300-016 (and, if phased conveyance is used, the NFR Letter for Parcel 016 prior to conveyance of that parcel); (e) Developer’s demonstration of committed equity of at least $85,000,000; (f) Developer’s posting of the Performance Security; (g) issuance of the ALTA lender’s title insurance policy and owner’s title insurance policy; (h) delivery of a current ALTA/NSPS survey; (i) updated MAI appraisal; (j) environmental clearance satisfactory to the Construction Lender; (k) all insurance policies in effect; (l) all necessary building permits and governmental approvals for Phase I; (m) an executed GMP or stipulated-sum construction contract with a general contractor approved by the Construction Lender; and (n) the Construction Lender’s confirmation that all conditions to its loan closing have been satisfied.

[Drafting Note — Conditions Precedent to Closing: The conditions in Section 10.2 are drawn from the Term Sheet (Section 4) and the Construction Loan Term Sheet (Section 7.1), harmonized to satisfy both the City and the Lender. Open items: (i) confirm the City’s conditions match the Resolution conditions; (ii) confirm the Construction Lender’s full conditions list (the Loan Term Sheet Section 7.1 includes 17 conditions, several of which — legal opinions, organizational documents, guaranties, intercreditor/subordination — are Lender-facing and reflected here by reference to Lender confirmation).]

## ARTICLE 11. ASSIGNMENT AND CHANGE OF CONTROL

11.1 Restriction on Assignment. Developer may not assign this Agreement or any interest herein, in whole or in part, without the prior written consent of the City, which consent may be withheld in the City’s reasonable discretion, except as permitted under Section 11.2.

11.2 Permitted Assignments. Notwithstanding Section 11.1, Developer may assign this Agreement without the City’s prior written consent to an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds a controlling interest and which expressly assumes in writing all of Developer’s obligations under this Agreement, provided that Developer gives the City written notice of any such assignment, with a copy of the assignment and assumption agreement, within fifteen (15) days of the effective date. The following transfers shall not require the City’s consent and shall not constitute a Change of Control: (a) transfers among the existing members of Developer (Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, and TransitWorks Equity Group LLC); (b) transfers by Pellegrini for estate planning purposes to family trusts or entities controlled by Pellegrini, provided Pellegrini retains management control; (c) transfers of non-managing limited partnership interests in Lakeshore Capital Partners Fund III LP among its existing or admitted limited partners; and (d) capital raises or equity issuances approved by Lakeshore Capital Partners Fund III LP (as required under the Lakeshore Side Letter) and the City.

11.3 Key Person Provision. As an alternative to, and in lieu of, a rigid percentage-of-interest threshold, the Parties acknowledge that the City’s selection of Developer was based in substantial part on the qualifications, experience, and financial capacity of Marcus J. Pellegrini. Accordingly, Marcus J. Pellegrini shall serve as Manager and Chief Executive Officer of Developer and shall exercise day-to-day management authority over the Project. If Marcus J. Pellegrini ceases to serve in such role, he shall be replaced by a person reasonably approved by the City (and by Lakeshore Capital Partners Fund III LP under the Lakeshore Side Letter) within sixty (60) days. No assignment default shall be triggered until the expiration of such sixty (60)-day cure period.

11.4 Change of Control. A “Change of Control” shall be deemed to occur if: (a) Marcus J. Pellegrini (directly or through the Pellegrini Family Trust) ceases to hold at least a [fifty percent (50%)] direct or indirect ownership interest in Developer; (b) Marcus J. Pellegrini ceases to serve as Manager/CEO of Developer and is not replaced by a person reasonably approved by the City within sixty (60) days; or (c) any single investor or group of affiliated investors (other than the existing members) acquires twenty-five percent (25%) or more of the membership interests in Developer. Any Change of Control without the City’s prior written consent shall constitute a material default under this Agreement.

[Drafting Notes — Assignment / Change-of-Control Threshold Conflict (Term Sheet Section 10 vs. Loan Term Sheet Section 8.1 vs. Lakeshore Side Letter Sections 4.4, 5.2, 8.3): (1) The Term Sheet (Section 10) permits assignment without City consent to an entity in which Pellegrini holds “at least a 50% controlling interest.” (2) The Construction Loan Term Sheet (Section 8.1) defines Change of Control using a bracketed [50]% threshold (subject to further negotiation), plus a 25% single-investor threshold, and treats Change of Control as an immediate Event of Default. (3) The Lakeshore Side Letter (Section 5.2) defines Change of Control using a 51% Pellegrini Interest threshold, and Section 4.4 grants Lakeshore enhanced consent rights over all Development Agreement amendments (not just Material Amendments) if the Pellegrini Interest falls below 51%. The Side Letter expressly states the 51% threshold is “intended to provide Investor with enhanced governance protections at a level above the assignment restriction threshold contemplated in the Term Sheet (which requires Pellegrini to hold at least fifty percent (50%)).” (4) Section 11.4 uses a [50]% threshold (bracketed) to match the Term Sheet and Loan Term Sheet, but the 51% Lakeshore threshold creates a gap: if the Pellegrini Interest falls between 50% and 51%, Lakeshore gains enhanced consent rights under the Side Letter while no Change of Control is triggered under this Agreement or the Loan. Open items: (i) reconcile the 50% (Term Sheet/Loan) and 51% (Lakeshore) thresholds — the Lakeshore Side Letter (Section 8.3) commits the parties to “work together in good faith to structure the Development Agreement’s assignment and change-of-control provisions in a manner that is compatible with Investor’s rights… and Developer’s anticipated future capital needs”; (ii) confirm the final threshold with the City, the Construction Lender, and Lakeshore; (iii) the bracketed [50]% in the Loan Term Sheet is expressly “subject to further discussion and negotiation.”]

[Drafting Note — Future Capital Raises / Dilution (Loan Term Sheet Section 3; Lakeshore Side Letter Sections 5.1, 5.3): The approximately $58,400,000 in additional debt/mezzanine/equity anticipated for Phases III and IV may dilute the Pellegrini Interest below both the 50% and 51% thresholds, triggering Change of Control under the Loan (requiring Lender consent) and enhanced Lakeshore consent rights. Section 11.2(d) creates a carve-out for capital raises approved by Lakeshore and the City. Open items: (i) confirm the City accepts this carve-out; (ii) confirm the Construction Lender’s consent requirements for dilution below 50% (Loan Term Sheet Section 8.1 “Note on 50% Threshold”); (iii) coordinate with Lakeshore’s preemptive and anti-dilution rights (Side Letter Section 5.1).]

11.5 Construction Lender Transfers. Notwithstanding Section 11.1, Developer may assign this Agreement to a Construction Lender-designee or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, without the City’s prior consent; provided that, if City consent is required by applicable law, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within thirty (30) days of request. See Article 15 (Lender Protections).

## ARTICLE 12. DEFAULTS; CURE; REMEDIES; TERMINATION

12.1 Monetary Defaults. In the event of a monetary default by either Party, the non-defaulting Party shall provide written notice specifying the nature and amount of the default. The defaulting Party shall have sixty (60) days from receipt of such notice to cure the default.

12.2 Non-Monetary Defaults. In the event of a non-monetary default by either Party, the non-defaulting Party shall provide written notice specifying the nature of the default in reasonable detail. The defaulting Party shall have ninety (90) days from receipt of such notice to cure the default; provided that, if the default cannot reasonably be cured within ninety (90) days, the defaulting Party shall have such additional time as is reasonably necessary to effect a cure, so long as the defaulting Party has commenced cure efforts within the initial ninety (90)-day period and is diligently and continuously pursuing cure to completion.

12.3 City Termination Rights. The City may terminate this Agreement upon: (a) a material breach by Developer that remains uncured after the expiration of the applicable cure period (including the Construction Lender’s cure rights under Article 15); (b) Developer’s failure to commence Phase I construction within six (6) months following conveyance, subject to extensions under Section 3.3 and Article 14; (c) Developer’s abandonment of the Project, evidenced by cessation of all construction activity for one hundred eighty (180) consecutive days (other than cessation caused by Force Majeure or City-caused delay); and (d) a Change of Control without the City’s prior written consent, subject to the cure period in Section 11.3.

12.4 Developer Termination Rights. Developer may terminate this Agreement upon: (a) the City’s failure to deliver marketable and insurable fee simple title to the Property at closing in accordance with Article 2; (b) the City’s failure to fund or complete its off-site infrastructure obligations ($12,500,000) in accordance with Section 4.3 and Exhibit E; (c) the City’s failure to complete rezoning or parcel consolidation in accordance with Article 6; (d) a condemnation or taking by eminent domain (by any entity other than the City) of more than fifteen percent (15%) of the Property; (e) the City’s failure to perform its TIF administration obligations under Section 5.2 in a manner that materially and adversely affects Developer’s TIF Reimbursement rights; and (f) the City’s material breach that remains uncured after the expiration of the applicable cure period.

[Drafting Note — Developer Termination Rights: Section 12.4 expands Developer’s termination rights beyond the Term Sheet (Section 15), which listed only (a) failure to deliver title, (b) failure to fund infrastructure, and (c) condemnation >15%. Section 12.4 adds termination rights for City failure to rezone/consolidate (protecting against the rezoning being a condition precedent to execution) and for City breach of TIF obligations. Open item: confirm the City accepts the expanded Developer termination rights.]

12.5 Remedies. Upon termination by a non-defaulting Party, the non-defaulting Party shall have all remedies available at law or in equity, including damages, specific performance, and injunctive relief, subject to the dispute resolution provisions of Article 17. Upon any termination by Developer for cause, Developer shall be entitled to recover its documented Project costs and expenses incurred prior to termination, to the extent permitted by law.

12.6 No Reversion Upon Termination. Upon any termination of this Agreement, fee simple title to the Property shall remain with Developer (if conveyed) or revert to the City only if the Property has not been conveyed, and in no event shall any termination trigger an automatic reversion of title to the City except as expressly provided in Section 9.3 (repurchase option) following satisfaction of the Construction Lender’s security interest.

[Drafting Note — Termination and Title: Section 12.6 reinforces that termination does not trigger automatic reversion of title, consistent with Section 2.3 and Article 9. Open item: confirm the City accepts that, post-conveyance, termination results in damages/contractual remedies rather than reversion of title.]

## ARTICLE 13. FORCE MAJEURE

13.1 Definition. “Force Majeure” means acts of God, fire, flood, earthquake, severe weather, pandemic, epidemic, quarantine, governmental health orders, war, terrorism, civil unrest, strikes or labor disputes (other than those caused by Developer’s labor practices), industry-wide supply chain disruptions beyond Developer’s reasonable control, governmental moratoria on construction, and actions or inactions of governmental authorities (other than the City in the performance of its obligations under this Agreement) that prevent or materially delay construction. Force Majeure shall not include financial inability to perform, changes in market conditions, increases in the cost of labor or materials (unless attributable to an industry-wide supply chain disruption), Developer’s failure to obtain financing, or any event caused by Developer’s negligence or willful misconduct.

13.2 Effect. Force Majeure events shall extend the applicable deadlines for commencement and Substantial Completion on a day-for-day basis for the duration of the Force Majeure event. Developer shall provide written notice to the City within fifteen (15) business days of the occurrence of a Force Majeure event and shall use commercially reasonable efforts to mitigate its effects.

13.3 Aggregate Cap. The maximum extension of time available under this Article 13 shall not exceed eighteen (18) months in the aggregate across the Project. Extensions under Section 3.3 (City-caused and regulatory delays) shall be in addition to, and shall not be counted against, this eighteen (18)-month cap.

[Drafting Notes — Force Majeure (Term Sheet Section 14; Loan Term Sheet Section 9): (1) The Term Sheet (Section 14) provides an 18-month aggregate cap, with Force Majeure defined to exclude financial inability, market changes, cost increases (unless industry-wide supply chain), and failure to obtain financing. (2) The Construction Loan Term Sheet (Section 9) provides force majeure extensions of up to 180 days (6 months) for the Phase I Substantial Completion default, plus Lender-approved extension periods. (3) Section 13.3 preserves the 18-month aggregate cap but expressly excludes City-caused and regulatory delays (Section 3.3) from the cap — favorable to Developer, given that rezoning, RAP approval, and NFR issuance timelines are outside Developer’s control. Open items: (i) confirm the City accepts that regulatory delays (IEPA, rezoning) and City-caused delays are excluded from the 18-month cap; (ii) reconcile the 18-month DA cap with the Loan’s 180-day force majeure extension and the Loan’s two 6-month extension options (Section 2.3) — ensure the DA deadlines are not shorter than the Loan’s cure/extension framework so Developer is not in DA default before the Lender’s cure expires.]

## ARTICLE 14. LENDER PROTECTIONS

14.1 Lender Review. This Agreement shall be delivered to the Construction Lender in draft form not less than fifteen (15) business days prior to its proposed execution date, and shall not be executed until the Construction Lender has confirmed in writing that it is in a Lender-Approved Form.

14.2 Lender Cure Rights. The Construction Lender shall have the right (but not the obligation) to receive prompt written notice of any Developer default under this Agreement and a reasonable opportunity to cure such default. The Construction Lender’s additional cure period shall be not less than thirty (30) days beyond Developer’s cure period for monetary defaults and not less than sixty (60) days beyond Developer’s cure period for non-monetary defaults, with such periods extended as necessary if the Construction Lender is diligently pursuing a cure that requires additional time (including time necessary to obtain possession of the Property through foreclosure or appointment of a receiver).

14.3 Lender Consent to Amendments. No material amendment, modification, supplement, or termination of this Agreement shall be effective without the Construction Lender’s prior written consent, which shall not be unreasonably withheld, conditioned, or delayed.

14.4 Subordination of City Interests. Any lien, encumbrance, or security interest that the City may hold or acquire in the Property (other than the completion-assurance mechanisms in Article 9, which are structured as contractual/financial remedies rather than property interests) shall be subordinated to the Construction Lender’s mortgage pursuant to a subordination agreement in a Lender-Approved Form.

14.5 Foreclosure / Deed-in-Lieu. Developer may assign this Agreement to a Construction Lender-designee or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, without the City’s prior consent, or if City consent is required, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within thirty (30) days of request.

14.6 Estoppel Certificates. The City shall deliver estoppel certificates to the Construction Lender upon reasonable request (not more than twice per calendar year), certifying the status of this Agreement, the existence or absence of any outstanding defaults, and such other customary matters as the Construction Lender may reasonably request.

[Drafting Notes — Lender Protections (Loan Term Sheet Section 12): The Construction Loan Term Sheet (Section 12) requires the Development Agreement to include each of the protections reflected in Article 14: (a) no reversionary interest (Section 2.3 / Article 9); (b) Lender cure rights (Section 14.2); (c) Lender consent to amendments (Section 14.3); (d) subordination of City interests (Section 14.4); (e) foreclosure/deed-in-lieu assignment (Section 14.5); and (f) estoppel certificates (Section 14.6). These are conditions to the Lender’s commitment. Open items: (i) confirm the City accepts each Lender protection — several (subordination of City interests, assignment to Lender-designee without City consent, estoppel obligations) may be points of City resistance; (ii) the Lakeshore Side Letter (Section 8.2) requires Developer to keep Lakeshore informed of all Construction Lender requirements affecting Lakeshore’s rights; (iii) coordinate the intercreditor/subordination agreement (Loan Term Sheet Section 7.1(17)) with the City.]

## ARTICLE 15. REPRESENTATIONS AND WARRANTIES

15.1 Developer Representations. Developer represents and warrants that: (a) it is a limited liability company duly organized, validly existing, and in good standing under Illinois law; (b) it has full power and authority to enter into this Agreement; (c) the execution and delivery of this Agreement has been duly authorized and will not conflict with its organizational documents or any material agreement; (d) its ownership structure is Pellegrini Family Trust (60%), Lakeshore Capital Partners Fund III LP (25%), and TransitWorks Equity Group LLC (15%); (e) it has the financial capacity, development experience, and organizational resources to complete the Project; (f) its entity-level net worth is approximately $185,000,000, with audited financials by Clearmont Accounting Group LLP, and bonding capacity of up to $75,000,000 through Ridgepoint Surety Corporation; and (g) there are no environmental conditions on the Property other than those disclosed in the Phase II ESA.

15.2 City Representations. The City represents and warrants that: (a) it has full power and authority to enter into this Agreement, acting through its City Manager pursuant to the Resolution; (b) it has good and marketable fee simple title to the Property, free and clear of all liens, encumbrances, and adverse claims (except Permitted Exceptions), and the legal authority to convey the Property to Developer; (c) the Property is located within the TIF District and TIF funds are legally available for the purposes described in this Agreement, subject to annual appropriation and the availability of increment; (d) the Property is the former site of the Lakemont Ironworks, and the environmental conditions described in the Phase II ESA are pre-existing and attributable to historical industrial operations that ceased in 2009; and (e) the City acquired the Property with knowledge of the environmental conditions described in the Phase II ESA.

[Drafting Note — City Representations on Environmental Conditions: Section 15.2(d)–(e) establishes the City’s knowledge of and responsibility for pre-existing contamination, supporting the indemnity in Section 5.1. The Phase II ESA (Section 4.2.4) confirms the City acquired Parcel 016 (and 017) with knowledge of the environmental conditions, referencing a prior Phase I ESA conducted for the City. Open item: confirm the City accepts these representations.]

## ARTICLE 16. INDEMNIFICATION

16.1 Mutual Indemnification. Each Party shall indemnify, defend, and hold harmless the other Party, and its officers, employees, agents, and representatives, from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to the indemnifying Party’s negligent acts or omissions, reckless conduct, or willful misconduct in connection with the performance of its obligations under this Agreement.

16.2 Developer Indemnification of City. Developer shall indemnify, defend, and hold harmless the City from and against all claims arising from or related to construction activities on the Property, including claims for personal injury, death, property damage, and workers’ compensation.

16.3 City Indemnification of Developer. The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims arising from or related to pre-existing environmental conditions on the Property, as set forth in Section 5.1.

16.4 Survival. The indemnification obligations in this Article 16 shall survive the expiration or termination of this Agreement.

## ARTICLE 17. DISPUTE RESOLUTION

17.1 Negotiation. The Parties shall first attempt to resolve any dispute arising under or related to this Agreement through good-faith negotiation between the City Manager (or designee) and Developer’s CEO (or designee) for a period of thirty (30) days following written notice of the dispute.

17.2 Mediation. If the dispute is not resolved through negotiation within the thirty (30)-day period, the dispute shall be submitted to non-binding mediation before the Lakemont Mediation Center, or such other neutral mediator as the Parties may agree upon. The costs of mediation shall be shared equally by the Parties.

17.3 Binding Arbitration. If the dispute is not resolved through mediation within sixty (60) days following submission to the mediator, the dispute shall be submitted to final and binding arbitration administered under the Commercial Arbitration Rules of the American Arbitration Association, conducted by a single arbitrator with experience in real estate development matters. The venue for any mediation or arbitration shall be Cook County or Lake County, Illinois.

17.4 Provisional Remedies. Nothing in this Article 17 shall prevent either Party from seeking temporary restraining orders, preliminary injunctions, or other provisional judicial relief where necessary to prevent irreparable harm, pending resolution of the dispute through the procedures set forth above.

[Drafting Note — Dispute Resolution (Term Sheet Section 17 vs. Lakeshore Side Letter Section 10.2): The Term Sheet provides negotiation (30 days) → mediation (Lakemont Mediation Center) → binding arbitration (AAA, single arbitrator, Cook or Lake County). The Lakeshore Side Letter provides negotiation (30 days) → mediation (AAA-administered) → binding arbitration (AAA Commercial Rules, Cook County). The mediation administrator differs (Lakemont Mediation Center vs. AAA). Section 17 follows the Term Sheet structure. Open item: reconcile the mediation administrator; confirm the venue (Cook or Lake County) is consistent with the county-of-record determination flagged in the Recitals.]

## ARTICLE 18. MISCELLANEOUS

18.1 Governing Law. This Agreement shall be governed by and construed in accordance with the laws of the State of Illinois, without regard to conflict-of-laws principles.

18.2 Notices. All notices shall be in writing and deemed delivered upon personal delivery, upon delivery by nationally recognized overnight courier, or three (3) business days following deposit in the U.S. mail, registered or certified, return receipt requested, postage prepaid, addressed as follows:

If to Developer: Granite City Development LLC, 900 West Monroe Street, Suite 2200, Chicago, IL 60607 Attn: Marcus J. Pellegrini, Manager/CEO With a copy to: Thornfield & Pratt LLP, 311 South Wacker Drive, Suite 5400, Chicago, IL 60606 Attn: Catherine M. Albrecht

If to City: City of Lakemont, Office of the City Manager, 200 Civic Center Drive, Lakemont, IL 60048 Attn: Gerald T. Fong, City Manager With a copy to: Office of Corporation Counsel, City of Lakemont, 200 Civic Center Drive, Lakemont, IL 60048 Attn: Rebecca A. Sinclair, Esq. With a copy to: Ashford, Keene & Mulvaney LLP, 150 North Michigan Avenue, Suite 3200, Chicago, IL 60601 Attn: Jonathan Ashford

18.3 Entire Agreement. This Agreement, together with its Exhibits, constitutes the entire agreement between the Parties with respect to the subject matter hereof and supersedes the Term Sheet and all prior negotiations, representations, and understandings. In the event of any conflict between this Agreement and the Term Sheet, this Agreement shall control.

18.4 Amendments. This Agreement may be amended, modified, or supplemented only by a written instrument executed by both Parties (and, with respect to material amendments, with the Construction Lender’s consent under Section 14.3 and Lakeshore’s consent under the Lakeshore Side Letter where required).

[Drafting Note — Lakeshore Consent Rights (Lakeshore Side Letter Sections 4.2, 4.3): The Lakeshore Side Letter requires Lakeshore’s prior written consent for any “Material Amendment” to the Development Agreement (defined to include changes to TIF cap, abatement schedule, phasing timelines extending beyond 2035, environmental obligations exceeding $3,140,000, performance bond/LC requirements, and assignment/change-of-control provisions), and enhanced consent over all amendments if the Pellegrini Interest falls below 51%. Section 18.4 acknowledges these consent rights. Open item: ensure the definition of “Material Amendment” in this Agreement is consistent with the Lakeshore Side Letter definition.]

18.5 Severability. If any provision of this Agreement is held invalid or unenforceable, such invalidity shall not affect other provisions that can be given effect without the invalid provision, and to this end the provisions are severable.

18.6 Confidentiality. The terms of this Agreement are confidential and shall not be disclosed by either Party to any third party, except: (a) to each Party’s legal counsel, financial advisors, accountants, lenders, and equity investors; (b) as required by applicable law, including the Illinois Freedom of Information Act (5 ILCS 140/) as applicable to the City; and (c) to the extent necessary for City Council proceedings and governmental approvals.

18.7 Counterparts; Electronic Signatures. This Agreement may be executed in counterparts, each of which shall be deemed an original, and signatures transmitted by electronic means shall be deemed original signatures.

18.8 TIF Compliance. Any use of TIF revenues in connection with the Project shall comply in all respects with the TIF Act and the Lakemont Central TIF District Redevelopment Plan and Project as adopted by Ordinance No. 2019-42, as amended.

18.9 Prevailing Wage Compliance. All construction work performed pursuant to this Agreement that constitutes “public works” within the meaning of the Illinois Prevailing Wage Act shall be subject to the prevailing wage requirements of said Act, including record-keeping, reporting, and certification requirements.

18.10 No Third-Party Beneficiaries. Except for the Construction Lender’s rights under Article 14 and the indemnification provisions in Article 16, this Agreement is for the sole benefit of the Parties and their permitted successors and assigns, and no third party shall have any enforceable right hereunder.

18.11 Further Assurances. Each Party shall execute and deliver such further documents and instruments as may be reasonably necessary to carry out the purposes of this Agreement.

## ARTICLE 19. EXHIBITS

The following Exhibits are attached to and incorporated into this Agreement:

- Exhibit A — Legal Description of the Property

- Exhibit B — Project Description and Phasing Plan (Phases I–IV: square footages, unit counts, parking, timelines, milestone dates, hard construction costs)

- Exhibit C — Permitted Exceptions to Title

- Exhibit D — Design Review and Approval Procedures

- Exhibit E — Infrastructure Improvement Schedule (City off-site and Developer on-site)

- Exhibit F — Performance Security (form, amount, draw mechanics, burn-down schedule)

- Exhibit G — Enhanced Completion Guaranty

- Exhibit H — Affordable Housing Covenant (form of restrictive covenant)

- Exhibit I — Environmental Remediation Plan and Cost Allocation

- Exhibit J — Sources and Uses of Funds

[Drafting Note — Exhibits: The Exhibits listed above are referenced but not yet prepared. Several require cross-document reconciliation: Exhibit B (phasing plan) must reconcile the Term Sheet and RFP program elements; Exhibit C (Permitted Exceptions) must be approved by the Construction Lender and exclude any reversionary interest; Exhibit F (Performance Security) must reconcile City and Lender interests; Exhibit I (Environmental Remediation) must address the cost-overrun allocation in Section 5.2 and the ESA’s 25–35% contingency recommendation; Exhibit J (Sources and Uses) must reconcile the Term Sheet, RFP, and Loan Term Sheet figures ($85M equity, $210M construction loan, up to $48M TIF, $9.2M land discount, $1.4M fee waivers, ~$58.4M additional later-phase financing). Open item: prepare each Exhibit and circulate for City, Construction Lender, and Lakeshore review.]

[SIGNATURE PAGE FOLLOWS]

SIGNATURE PAGE

DEVELOPMENT AGREEMENT — LAKEMONT STATION COMMONS

CITY OF LAKEMONT, ILLINOIS

By: _______________________

Name: Gerald T. Fong

Title: City Manager

Date: _______________________

APPROVED AS TO FORM:

Rebecca A. Sinclair, Esq., Corporation Counsel

Date: _______________________

GRANITE CITY DEVELOPMENT LLC

By: _______________________

Name: Marcus J. Pellegrini

Title: Manager and Chief Executive Officer

Date: _______________________

[Drafting Note — Summary of Principal Open Items and Cross-Document Conflicts for Negotiation:]

[1. Reversionary Interest / Clawback (CRITICAL): Resolution R-2025-017 Condition #8 requires a reversionary interest; the Construction Lender strictly prohibits any defeasible fee; Lakeshore requires consent. Article 9 proposes liquidated damages + a repurchase option exercisable only post-Lender-satisfaction + an enhanced completion guaranty as alternatives. Requires City Council acceptance, Construction Lender written approval, and Lakeshore consent.]

[2. Change-of-Control Threshold: 50% (Term Sheet/Loan) vs. 51% (Lakeshore Side Letter). Reconcile and confirm with City, Lender, and Lakeshore.]

[3. Environmental Remediation Cost/Overrun Allocation: ESA recommends 25–35% contingency (total exposure $3.8–4.2M). Section 5.2 allocates cost and overruns to the City. Confirm City acceptance; obtain Lakeshore consent if any cost shifts to Developer above $3,140,000.]

[4. NFR Letter Timing vs. Groundbreaking: 14–18 month remediation timeline vs. March 1, 2026 groundbreaking. Confirm phased conveyance (Section 2.5) and deadline extensions (Section 3.3).]

[5. TIF Reimbursement Risk: Corporation Counsel memo estimates $6–10M shortfall under abatement-adjusted scenario. Confirm priority structure, good-faith extension covenant, and shortfall-not-default provision (Section 5.2).]

[6. Land Write-Down / Infrastructure vs. TIF Cap: Confirm these are not charged against the $48M TIF cap (Sections 4.1, 4.3).]

[7. Prevailing Wage Scope: Term Sheet says “all construction”; Developer position limits to “public works.” Negotiate scope.]

[8. Community Benefits / Living Wage: Resolution mandates living wage for all retail/hotel employees; Developer limits binding obligation to its own employees. Negotiate.]

[9. Equity Demonstration Timing: April 19, 2025 (Resolution) vs. 60 days from DA approval (Term Sheet). Confirm.]

[10. Parcel Acreage / Acquisition History / County / RFP Number: Reconcile minor factual conflicts (Sections 2.4, Recitals).]

[11. Insurance Requirements: Align to Loan Term Sheet (higher CGL aggregate, professional and pollution coverage) (Section 7.6).]

[12. Lender Protections: Confirm City accepts cure rights, subordination, foreclosure assignment, estoppels (Article 14).]

[13. Performance Security: Reconcile City and Lender interests in the $15M bond/LC; confirm burn-down (Article 8).]

[14. Hotel Brand: “To be determined”; confirm PD-TOD use approval for hotel (Section 3.1).]

[15. Later-Phase Financing: ~$58.4M additional debt/mezzanine; confirm financing condition for later phases (Section 3.4) and Lender/Lakeshore consent requirements.]

[16. Community Center Conveyance: Clarify “fully furnished and equipped,” acceptance timing, and City operational responsibilities (Section 7.5).]

[17. Dispute Resolution: Reconcile mediation administrator (Lakemont Mediation Center vs. AAA) and venue (Article 17).]

[18. Exhibits: Prepare and reconcile all Exhibits (Article 19).]