# DEVELOPMENT AGREEMENT

## LAKEMONT STATION COMMONS MIXED-USE TRANSIT-ORIENTED DEVELOPMENT

by and between

GRANITE CITY DEVELOPMENT LLC (an Illinois limited liability company, “Developer”)

and

CITY OF LAKEMONT, ILLINOIS (an Illinois home rule municipality, “City”)

[Drafting Note — Purpose and posture of this draft. This Development Agreement (“Agreement”) is drafted by Developer’s counsel, Thornfield & Pratt LLP, on behalf of Granite City Development LLC, and reflects the Developer’s positions and interests. It is based principally on the non-binding Negotiated Term Sheet dated January 22, 2025 (the “Term Sheet”), as conditioned by City Council Resolution No. R-2025-017 adopted February 18, 2025 (the “Resolution”). Bracketed drafting notes in this format [Drafting Note — …] identify (i) cross-document conflicts among the Term Sheet, the Resolution, the First Prairie National Bank preliminary construction loan term sheet (the “Loan Term Sheet”), the Lakeshore Capital Partners Fund III LP side letter dated February 10, 2025 (the “Lakeshore Side Letter”), the Phase II Environmental Site Assessment executive summary prepared by Greenfield Environmental Consultants LLC dated November 8, 2024 (the “Phase II ESA”), the Developer’s RFP response narrative dated December 16, 2024 (the “RFP Response”), and the Corporation Counsel TIF district summary memorandum dated March 5, 2025 (the “TIF Memo”), and (ii) open items requiring further negotiation, third-party input, or factual confirmation. Drafting notes are not operative contract text and are intended to be deleted or converted to a separate issues list prior to execution.]

## ARTICLE 1. RECITALS AND DEFINITIONS

### Section 1.1 Recitals.

1.1.1 The City is the owner of certain real property commonly known as 1400–1550 Lakemont Station Boulevard, Lakemont, Illinois 60048, consisting of three (3) parcels of record identified by Parcel Identification Numbers 12-24-300-015, 12-24-300-016, and 12-24-300-017, totaling approximately 12.7 acres (553,212 square feet) (collectively, the “Property” or “Site”). The Property constitutes the former site of the Lakemont Ironworks manufacturing campus, which ceased industrial operations in 2009, and is situated immediately adjacent to the Lakemont Central Metra commuter rail station on the Metra Milwaukee District/North Line.

[Drafting Note — Conflict C4 (parcel acquisition history). The Resolution, the TIF Memo, and the RFP Response state that the City acquired Parcels 12-24-300-015 and 12-24-300-016 through tax forfeiture proceedings concluded in 2016, and acquired Parcel 12-24-300-017 by direct purchase in 2018. The Phase II ESA (Section 1.3) states that Parcel 12-24-300-015 was acquired by tax forfeiture in 2016, while Parcels 12-24-300-016 and 12-24-300-017 were acquired by direct purchase in 2018. This discrepancy is material because tax-forfeiture parcels may carry different title characteristics (e.g., unresolved tax claims, different warranty posture) than direct-purchase parcels, which affects the City’s ability to deliver insurable title and the scope of the City’s special warranty deed covenants. Confirm the acquisition history for each parcel and reconcile the recital accordingly. The Phase II ESA (Section 1.3) further recommends a comprehensive per-parcel title review before consolidation to identify any environmental liens, utility easements, unresolved tax claims, or mechanic’s liens arising from the City’s prior demolition/clearing work.]

[Drafting Note — Conflict C5 (parcel acreages). The RFP Response (Section 3.1) states Parcel 015 is approximately 3.8 acres, Parcel 016 approximately 4.1 acres, and Parcel 017 approximately 4.8 acres. The Phase II ESA (Section 1.3) states Parcel 015 is approximately 4.2 acres, Parcel 016 approximately 4.1 acres, and Parcel 017 approximately 4.4 acres. Both total approximately 12.7 acres. The per-parcel acreage should be confirmed by the ALTA/NSPS survey required under the Loan Term Sheet (Section 7.1(5)) and stated precisely in the legal description exhibit.]

[Drafting Note — Conflict C7 (county jurisdiction). The Phase II ESA (Section 1.3) refers to “Cook County Parcel Identification Numbers,” while the RFP Response (Section 3.1) refers to coordination with the “Lake County Recorder’s Office” and the TIF Memo (Section V.B) references prevailing wage rates for “Lake County.” The county in which the Property is located must be confirmed, as it determines the recording jurisdiction for the deed, consolidation plat, affordability covenants, environmental land use controls (“ELUCs”), and the mortgage, and the applicable Illinois Department of Labor prevailing wage schedule. Reconcile and state the correct county throughout.]

1.1.2 The Property is currently zoned M-2 (General Manufacturing) under the City of Lakemont Zoning Ordinance. The proposed mixed-use transit-oriented development requires rezoning of the Property to PD-TOD (Planned Development–Transit Oriented District).

1.1.3 The City conducted a competitive Request for Proposals process for the redevelopment of the Property.

[Drafting Note — Conflict C6 (RFP number). The RFP Response identifies the solicitation as “RFP No. 2024-CD-07,” while the Term Sheet (preamble) identifies it as “RFP No. 2024-CD-018.” Confirm the correct RFP number and state it consistently.]

Developer was selected as the preferred developer based upon its qualifications, experience, project proposal, and demonstrated financial capacity. Developer’s principal, Marcus J. Pellegrini, has completed projects including the Halsted Collection (Chicago), Riverside Crossing (Naperville), and Archer Park Residences (Chicago). Developer’s reported entity-level net worth is approximately $185,000,000 (audited by Clearmont Accounting Group LLP), with bonding capacity of up to $75,000,000 through Ridgepoint Surety Corporation.

1.1.4 The ownership structure of Developer is as follows: Pellegrini Family Trust — 60%; Lakeshore Capital Partners Fund III LP, a Delaware limited partnership whose general partner is Lakeshore Capital Management LLC (Managing Partner: Richard “Rick” Dominguez) — 25%; and TransitWorks Equity Group LLC — 15%.

1.1.5 Developer proposes a four-phase mixed-use transit-oriented development to be known as “Lakemont Station Commons” (the “Project”), with a total gross building area of approximately 1,620,000 square feet, total estimated hard construction cost of approximately $340,000,000, and total estimated Project cost (inclusive of soft costs) of approximately $412,000,000.

1.1.6 The Property was appraised at a fair market value of $18,400,000 on an as-is basis by Crossland Appraisal Services in an appraisal report dated January 15, 2025. The City proposes to convey the Property to Developer at a purchase price of $9,200,000, representing 50% of the appraised fair market value, resulting in a land write-down incentive of $9,200,000.

1.1.7 The Property is located within the Lakemont Central Tax Increment Financing District, established pursuant to Ordinance No. 2019-42, which expires on December 31, 2042. The City proposes to pledge up to $48,000,000 in tax increment financing revenues to reimburse Developer for eligible redevelopment project costs on a pay-as-you-go basis.

1.1.8 A Phase II Environmental Site Assessment was completed by Greenfield Environmental Consultants LLC in a report dated November 8, 2024, identifying environmental conditions on the Property as further described in Article 6.

1.1.9 The City Manager and Developer executed the non-binding Term Sheet dated January 22, 2025. The City Council adopted the Resolution on February 18, 2025, granting conditional approval and authorizing the City Manager to negotiate and execute this Agreement subject to the conditions set forth in Section 3 of the Resolution.

1.1.10 Developer has obtained a preliminary (non-binding) commitment from First Prairie National Bank (the “Construction Lender”) for a construction loan facility of up to $210,000,000, subject to execution of this Agreement in form and substance acceptable to the Construction Lender. Developer’s committed equity sources include the Pellegrini Family Trust ($34,000,000) and Lakeshore Capital Partners Fund III LP ($51,000,000), for total committed equity of $85,000,000.

### Section 1.2 Definitions.

In addition to terms defined elsewhere in this Agreement, the following terms have the meanings set forth below. Capitalized terms used but not defined herein have the meanings ascribed to them in the Term Sheet.

“Affordable Unit” means a residential dwelling unit restricted to occupancy by households earning at or below sixty percent (60%) of Area Median Income.

“AMI” means Area Median Income as published annually by the U.S. Department of Housing and Urban Development for the Chicago-Naperville-Elgin, IL-IN-WI Metropolitan Statistical Area, or any successor designation.

“BTEX” means benzene, toluene, ethylbenzene, and xylene compounds.

“Change of Control” has the meaning set forth in Section 15.2.

“Construction Lender” means First Prairie National Bank, or any successor construction lender approved in accordance with the Loan Documents and this Agreement.

“Construction Loan Documents” means the definitive loan agreements, mortgage, assignments, guaranties, and other instruments evidencing and securing the Construction Loan.

“Construction Loan” means the construction loan facility of up to $210,000,000 provided by the Construction Lender.

“ELUC” means an environmental land use control recorded against the Property in connection with the IEPA Voluntary Site Remediation Program.

“Force Majeure” has the meaning set forth in Section 12.3.

“IEPA” means the Illinois Environmental Protection Agency.

“Loan Term Sheet” means the preliminary construction loan term sheet provided by First Prairie National Bank, as the same may be amended, supplemented, or superseded by the Construction Loan Documents.

“NFR Letter” means a No Further Remediation letter issued by IEPA under the Voluntary Site Remediation Program.

“Pellegrini Interest” means the aggregate direct and indirect membership interest in Developer held by Marcus J. Pellegrini and/or the Pellegrini Family Trust, whether held of record or beneficially.

“Permitted Exceptions” means the title exceptions set forth in Exhibit [__], as agreed by the parties and acceptable to the Construction Lender and the title company.

“Phase” or “Project Phase” means each of Phase I, Phase II, Phase III, and Phase IV of the Project, as described in Article 3.

“Project Budget” means the detailed line-item budget for the Project set forth in Exhibit [__], including hard costs, soft costs, contingencies, environmental remediation, infrastructure, and interest reserve.

“RAP” means a Remedial Action Plan submitted to and approved by IEPA under the Voluntary Site Remediation Program.

“Substantial Completion” has the meaning set forth in Section 12.2.

“TIF” or “Tax Increment Financing” means tax increment financing administered under the Illinois Tax Increment Allocation Redevelopment Act, 65 ILCS 5/11-74.4-1 et seq. (the “TIF Act”).

“TIF District” means the Lakemont Central TIF District established by Ordinance No. 2019-42, expiring December 31, 2042.

“VSRP” means the IEPA Voluntary Site Remediation Program.

## ARTICLE 2. EFFECTIVENESS; CONDITIONS PRECEDENT TO EXECUTION

### Section 2.1 Effectiveness.

This Agreement shall become effective upon the date of its full execution by both parties and approval by the Lakemont City Council at a duly noticed public meeting (the “Effective Date”).

### Section 2.2 Conditions Precedent to Execution.

The execution and delivery of this Agreement by Developer is subject to the satisfaction (or waiver by Developer) of the following conditions precedent:

- Rezoning. The rezoning of the Property from M-2 (General Manufacturing) to PD-TOD (Planned Development–Transit Oriented District) shall have been approved by the City Council by ordinance and shall be final and effective, with the applicable appeal period expired without the filing of any appeal, or any appeal finally resolved in a manner that confirms the rezoning.

- Parcel Consolidation. The consolidation of Parcels 12-24-300-015, 12-24-300-016, and 12-24-300-017 into a single parcel of record shall have been completed or authorized by the applicable county authority, subject to the title review recommended in the Phase II ESA.

- IEPA Remedial Action Plan. IEPA shall have approved a RAP for Parcel 12-24-300-016 under the VSRP, addressing the BTEX and TCE contamination identified in the Phase II ESA.

- Equity Demonstration. Developer shall have demonstrated committed equity of not less than $85,000,000, in form and substance reasonably acceptable to the City, including executed commitment letters from equity partners, evidence of available and uncommitted capital, bank statements, or other documentation satisfactory to the City in its reasonable discretion, verified by an independent certification from Developer’s auditing firm, Clearmont Accounting Group LLP.

- City Council Approval. The Lakemont City Council shall have approved this Agreement.

- Construction Lender Confirmation. The Construction Lender shall have confirmed in writing that this Agreement is in form and substance acceptable to it as a condition of the Construction Loan commitment.

[Drafting Note — Conflict C16 (equity demonstration deadline). Resolution Condition #8(a) requires Developer to demonstrate $85,000,000 in committed equity within sixty (60) days of adoption of the Resolution (i.e., on or before April 19, 2025), verified by an independent certification from Clearmont Accounting Group LLP. The Term Sheet (Section 7) requires demonstration within sixty (60) days of City Council approval of the definitive Agreement (a later trigger). The Resolution’s earlier deadline controls as a condition of the City’s authorization. Developer should confirm whether the April 19, 2025 demonstration has been or will be timely made, and whether the City will accept the Term Sheet’s later trigger. The condition in Section 2.2(d) is stated generally; the timing should be reconciled. Developer’s preference is the later Term Sheet trigger, but the Resolution is the controlling City action.]

[Drafting Note — Conflict C15 (NFR vs. RAP as condition precedent; phased conveyance). Resolution Condition #8(b) requires that, prior to any conveyance of the Property, Developer shall have submitted and IEPA shall have approved a RAP for Parcel 12-24-300-016 (not a full NFR Letter). The Loan Term Sheet (Section 7.1(7)) is more flexible, permitting either (a) an NFR Letter, or (b) VSRP enrollment with an approved RAP plus an environmental escrow or insurance product of $3,500,000. The Phase II ESA (Section 5.2) estimates 14–18 months from VSRP enrollment to NFR Letter issuance and recommends a phased conveyance approach (conveying clean Parcels 015 and 017 first, with Parcel 016 conveyed after the NFR Letter) to allow Phase I construction to begin on clean portions while Parcel 016 remediation proceeds. Section 2.2(c) follows the Resolution (RAP approval, not full NFR) as the condition to Agreement execution; the condition to land conveyance is addressed in Article 4 and should expressly permit phased conveyance. Confirm with the City that RAP approval (rather than NFR Letter) is the operative condition and that phased conveyance is permitted.]

[Drafting Note — Open item O9 (Permitted Exceptions). The Permitted Exceptions to title must be agreed by the parties and acceptable to the Construction Lender and the title company. The Loan Term Sheet (Section 4.2) enumerates a specific list, including the Development Agreement, PD-TOD covenants, and environmental use controls/institutional controls recorded in connection with the IEPA VSRP NFR Letter and engineered barrier, in each case as reviewed and approved by the Construction Lender’s counsel. The form of Permitted Exceptions should be developed in parallel with the title commitment.]

## ARTICLE 3. THE PROJECT

### Section 3.1 Project Description.

The Project consists of a mixed-use, transit-oriented development organized in four phases, with a total gross building area of approximately 1,620,000 square feet, comprising the program elements set forth in this Article 3 and in Exhibit [__] (Project Description and Phasing Plan). The Project is designed as a cohesive, master-planned transit-oriented development serving as a catalyst for revitalization of the Lakemont Central station area.

### Section 3.2 Phase I — Residential Tower A and Retail Podium.

Phase I comprises: (a) three hundred twenty (320) residential dwelling units, consisting of two hundred fifty-six (256) market-rate units and sixty-four (64) Affordable Units; (b) forty-five thousand (45,000) square feet of ground-floor retail space; and (c) a four hundred eighty (480)-space structured parking facility. Phase I comprises approximately four hundred twenty thousand (420,000) square feet of gross building area, with an estimated hard construction cost of $105,000,000. Phase I groundbreaking shall occur no later than March 1, 2026, with Substantial Completion by September 30, 2028 (approximately thirty (30) months of construction).

### Section 3.3 Phase II — Office Building and Retail.

Phase II comprises: (a) two hundred eighty thousand (280,000) square feet of Class A office space; (b) eighteen thousand (18,000) square feet of retail space; and (c) a three hundred fifty (350)-space structured parking facility. Phase II comprises approximately three hundred eighty thousand (380,000) square feet of gross building area, with an estimated hard construction cost of $76,000,000. Phase II shall commence within twelve (12) months of Phase I Substantial Completion, with Substantial Completion within twenty-four (24) months of Phase II commencement.

### Section 3.4 Phase III — Residential Tower B and Hotel.

Phase III comprises: (a) two hundred ten (210) residential dwelling units, consisting of one hundred sixty-eight (168) market-rate units and forty-two (42) Affordable Units; and (b) a one hundred fifty (150)-room select-service hotel. Phase III comprises approximately four hundred forty thousand (440,000) square feet of gross building area, with an estimated hard construction cost of $88,000,000. Phase III shall commence within twelve (12) months of Phase II Substantial Completion, with Substantial Completion within thirty (30) months of Phase III commencement.

[Drafting Note — Open item O1 (hotel brand). The Term Sheet (Section 3.3) states the hotel brand affiliation is “to be determined” and that Developer is in discussions with two national hospitality flags. The Agreement should preserve Developer’s flexibility to select the hotel brand based on prevailing market conditions at the time of Phase III execution, subject only to compliance with the PD-TOD zoning and the LEED Gold commitment. No City approval of the specific brand should be required.]

### Section 3.5 Phase IV — Public Plaza, Community Center, and Parking Structure.

Phase IV comprises: (a) a 2.5-acre public plaza incorporating landscaping and public art installations; (b) a twenty-eight thousand (28,000) square foot community center facility to be conveyed to the City upon completion as provided in Section 3.7; and (c) a six hundred (600)-space public parking structure. Phase IV comprises approximately three hundred eighty thousand (380,000) square feet of gross building area, with an estimated hard construction cost of $71,000,000. Phase IV shall commence concurrently with Phase III, with Substantial Completion within twenty-four (24) months of Phase IV commencement.

### Section 3.6 Project Summary Totals.

In the aggregate, the Project shall include: five hundred thirty (530) residential dwelling units, of which one hundred six (106) shall be Affordable Units; sixty-three thousand (63,000) square feet of total retail space; two hundred eighty thousand (280,000) square feet of Class A office space; one hundred fifty (150) hotel rooms; one thousand four hundred thirty (1,430) structured parking spaces; a 2.5-acre public plaza; and a 28,000 square foot community center. The total estimated hard construction cost for all four phases is approximately $340,000,000, and the total estimated Project cost, inclusive of soft costs, is approximately $412,000,000.

[Drafting Note — Conflict C8 (affordable unit count). The Resolution and the detailed breakdown in Term Sheet Section 12 specify 106 Affordable Units (64 in Phase I + 42 in Phase III), representing 20% of 530 total residential units. The Term Sheet Section 3.5 summary table, however, states “at least 100 affordable units.” The Agreement states 106 units, which exceeds both the City’s 20% minimum (Resolution Condition #8(g)) and the “at least 100” floor in the Term Sheet summary. Confirm the City accepts 106 as the binding number and that the “at least 100” language in the Term Sheet summary is superseded.]

### Section 3.7 Community Center Conveyance.

The community center shall be designed in consultation with the City’s Parks and Recreation Department. Upon Substantial Completion of Phase IV, Developer shall convey the community center to the City in fee simple by special warranty deed, at no additional cost to the City beyond the costs included in the Project Budget. The community center shall be delivered in accordance with the design specifications agreed by the parties in Exhibit [__].

[Drafting Note — Conflict C29 (community center scope). The Term Sheet (Section 3.4) states the community center is “to be designed in consultation with the City’s Parks and Recreation Department and conveyed to the City upon completion at no additional cost.” The RFP Response (Section 5.5) states the community center will be conveyed “fully furnished and equipped per the agreed-upon specifications.” The scope of “furnished and equipped” and the meaning of “at no additional cost” (i.e., no cost beyond the Project Budget line item) must be precisely defined in the specifications exhibit to avoid open-ended Developer obligations. Open item O5 (community center design specifications/furnishings) must be resolved and attached as an exhibit. Developer’s position: the conveyance obligation is limited to the building shell and core and the furnishings/equipment expressly itemized in the agreed specifications, all within the Project Budget; “at no additional cost” means no cost beyond amounts already budgeted, not that Developer will absorb unbudgeted scope.]

### Section 3.8 Public Parking Structure.

The 600-space public parking structure in Phase IV shall serve Metra commuters, retail and restaurant patrons, community center and plaza visitors, and Project residents and workers, and shall be publicly accessible. The operating and access arrangements for the public parking structure shall be set forth in an access/operating agreement in Exhibit [__], which shall confirm the public character of the facility for TIF eligibility purposes.

[Drafting Note — Open item O6 (public parking operating arrangements). The TIF Memo (Section III.B) notes that the Phase IV public parking structure, public plaza, and community center are eligible as construction of public improvements and facilities, and that the Phase I (480-space) and Phase II (350-space) garages are “potentially eligible to the extent they are publicly accessible or contractually committed to public use,” requiring analysis of access agreements and deed restrictions. The operating/access agreements should be structured to maximize TIF eligibility while preserving Developer’s reasonable operational control. Developer should confirm the desired public-access commitments for each parking facility.]

### Section 3.9 Design Review.

Developer shall submit design plans for each Phase to the City’s Community Development Department for review and approval. The City’s review shall be limited to confirming consistency with the PD-TOD zoning standards, the Project Description, and applicable building codes. The City shall approve or provide written comments within thirty (30) business days of submission; approval shall be deemed given if the City does not respond within such period. The City’s approval rights shall not extend to aesthetic matters within Developer’s discretion or to matters that would increase Project cost or delay the schedule, in each case without the City bearing the resulting cost or extending equivalent schedule relief.

[Drafting Note — Developer-protective provision. The Term Sheet (Section 19) contemplates “design review and approval procedures” in the definitive Agreement. From the Developer’s perspective, design review should be (i) bounded to zoning/code consistency, (ii) subject to a deemed-approval default, and (iii) accompanied by cost/schedule protection so that City-requested changes are at City cost or with schedule relief. The City may seek broader design review authority; this is an open negotiation item.]

## ARTICLE 4. LAND CONVEYANCE

### Section 4.1 Conveyance; Purchase Price.

Following the Effective Date and satisfaction of the conditions precedent to closing set forth in Section 4.3, the City shall convey the Property (as consolidated into a single parcel, or in phased conveyances as provided in Section 4.2) to Developer by special warranty deed, free and clear of all liens, encumbrances, and exceptions except Permitted Exceptions. The purchase price is $9,200,000, representing 50% of the appraised as-is market value of $18,400,000 (Crossland Appraisal Services, dated January 15, 2025), resulting in a land write-down incentive of $9,200,000. The purchase price shall be due and payable at closing, and Developer may fund it from equity, Construction Loan proceeds, or a combination thereof.

### Section 4.2 Phased Conveyance.

Notwithstanding any other provision of this Agreement, Developer may elect, by notice to the City, to receive conveyance of the Property in phases: (a) Parcel 12-24-300-015 (which requires no remediation) and Parcel 12-24-300-017 (subject to completion of the engineered barrier) may be conveyed first; and (b) Parcel 12-24-300-016 may be conveyed after issuance of the NFR Letter for that parcel. A phased conveyance shall be coordinated with the PD-TOD rezoning, parcel consolidation, and the Construction Lender’s requirements regarding the scope and legal description of the mortgaged premises.

[Drafting Note — Conflict C15/C36 (phased conveyance). The Phase II ESA (Sections 4.1.3, 5.2, 8.2) recommends a phased conveyance approach to allow Phase I construction to begin on clean Parcels 015 and 017 while Parcel 016 remediation proceeds, noting that this requires (i) PD-TOD rezoning and consolidation to accommodate phased delivery or separate/interim land use approvals, (ii) resolution of per-parcel title issues, and (iii) coordination with the Construction Lender’s mortgage scope. Resolution Condition #8(b) requires IEPA approval of the RAP for Parcel 016 “prior to any conveyance of the Property or any portion thereof,” which on its face permits conveyance of clean parcels once the RAP is approved (it does not require the NFR Letter before conveyance of any parcel). The City should confirm that phased conveyance is permitted and that the rezoning/consolidation can accommodate it. This is a key schedule-risk mitigation for Developer.]

### Section 4.3 Conditions Precedent to Closing.

The obligation of each party to close the conveyance is subject to satisfaction (or waiver by the waiving party) of the following conditions precedent:

- Execution and delivery of this Agreement and City Council approval;

- Completion of rezoning of the Property from M-2 to PD-TOD;

- Completion or authorization of parcel consolidation (or, in the case of a phased conveyance, the applicable parcel(s));

- IEPA approval of the RAP for Parcel 12-24-300-016;

- Developer’s demonstration of committed equity of at least $85,000,000;

- Developer’s posting of the $15,000,000 Phase I performance security under Article 8;

- Delivery by the City of an owner’s title insurance commitment insuring marketable and insurable fee simple title in Developer, subject only to Permitted Exceptions, together with a current ALTA/NSPS land title survey; and

- Delivery by the City of the Construction Lender’s confirmation that this Agreement is in form acceptable to it.

### Section 4.4 Title; Insurability.

The City shall deliver marketable and insurable fee simple absolute title to the Property, free and clear of all liens, encumbrances, restrictions, reversionary interests, rights of re-entry, possibilities of reverter, defeasible conditions, and other title defects or exceptions, except Permitted Exceptions. The City shall provide a standard owner’s title insurance policy in the amount of the purchase price. The Property conveyed to Developer shall not be subject to any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other form of defeasible fee estate in favor of the City or any other party.

[Drafting Note — Conflict C1 (reversionary interest / defeasible fee). This Section 4.4, together with Article 14, implements the Construction Lender’s absolute requirement (Loan Term Sheet Sections 4.2, 7.1(1), 12(a)) that the Property not be subject to any reversionary or defeasible interest. The Construction Lender states that any such interest would render the title uninsurable, subordinate the mortgage to the City’s right to reclaim the property, prevent foreclosure, and render the Construction Loan unsecurable — and that incorporation of Resolution Condition #8(h)’s reversionary interest “as stated in the Resolution, would make the Loan impossible to close.” Resolution Condition #8(h), however, requires Developer to grant the City a reversionary interest with automatic reversion if Phase I is not Substantially Complete within 36 months of conveyance. This is the central cross-document conflict. Article 14 substitutes an alternative completion-assurance mechanism (a contractual repurchase option plus enhanced performance security) that is intended to satisfy the City’s policy objective of ensuring timely Phase I completion while preserving Developer’s fee simple absolute title and the Construction Lender’s first-priority security interest. The City must agree to deviate from the literal terms of Resolution Condition #8(h); this requires either (i) a further City Council action amending or superseding Condition #8(h), or (ii) a determination by Corporation Counsel that the alternative mechanism satisfies the condition. This is the single most important open item and must be resolved before execution.]

[Drafting Note — Conflict C2 (36-month reversion clock vs. 30-month construction). Even setting aside the title-insurability problem, Resolution Condition #8(h) measures the 36-month reversion period from the date of conveyance, while Phase I Substantial Completion is targeted for September 30, 2028 with groundbreaking no later than March 1, 2026. If conveyance occurs in mid-2025 (the Term Sheet’s target closing date), the 36-month period could expire before the Phase I Substantial Completion deadline, meaning the reversion could be triggered through no fault of Developer. This timing mismatch further supports substituting an alternative mechanism measured from groundbreaking (or aligned to the Substantial Completion deadline plus cure and Force Majeure extensions).]

### Section 4.5 Closing.

Closing shall occur within thirty (30) days following satisfaction or waiver of all conditions precedent to closing. The parties’ target closing date is mid-2025, subject to the timing of rezoning, IEPA approvals, and satisfaction of other conditions.

## ARTICLE 5. PUBLIC INCENTIVES

### Section 5.1 Land Write-Down.

The City conveys the Property at 50% of appraised as-is market value, resulting in a land write-down incentive of $9,200,000. The land write-down shall constitute a separate public incentive and shall not be charged against, or counted toward, the $48,000,000 TIF reimbursement cap set forth in Section 5.2.

[Drafting Note — Conflict C11 (land write-down vs. TIF cap). The TIF Memo (Section VII) notes that the land write-down is itself an eligible TIF cost and that, if the City records it as a TIF expenditure from the Special Tax Allocation Fund, it counts against the $48,000,000 cap — reducing the reimbursement available to Developer. The TIF Memo recommends the development agreement “clearly specify whether the land write-down is charged against the TIF cap or constitutes a separate incentive funded from another source.” Developer’s position, reflected in Section 5.1, is that the land write-down is a separate incentive funded from the City’s general/capital sources and is not charged against the TIF cap. The City should confirm the funding source. This is an open item.]

### Section 5.2 Tax Increment Financing.

- Pledge. The City shall pledge up to $48,000,000 in TIF increment over the remaining life of the TIF District to reimburse Developer for eligible TIF costs incurred in connection with the Project. Eligible TIF costs shall include, without limitation: public infrastructure improvements, environmental remediation costs, parking structure construction costs, the public plaza and community center, and other eligible project costs under the TIF Act and the Lakemont Central TIF District Redevelopment Plan and Project adopted by Ordinance No. 2019-42.

- Pay-As-You-Go. TIF reimbursement shall be on a pay-as-you-go basis. Developer shall front all eligible costs and shall be reimbursed from available TIF increment as generated by the Project and other developments within the TIF District. The City shall not issue TIF bonds or notes for the Project.

- No Guarantee; Shortfall Not a Default. TIF reimbursement is subject to the availability of increment. The City does not guarantee that the full $48,000,000 cap will be reached. A shortfall in TIF reimbursement, or the failure of cumulative increment to reach the $48,000,000 cap by the TIF District expiration, shall not constitute a default by the City or by Developer under this Agreement, and shall not give either party a right to terminate this Agreement.

- Priority of Reimbursement. TIF reimbursements shall be made in the following priority order: (i) first, environmental remediation costs for Parcels 12-24-300-016 and 12-24-300-017; (ii) second, public infrastructure costs, including the City’s off-site infrastructure commitment and Developer’s eligible on-site infrastructure expenditures; (iii) third, the Phase IV public parking structure, public plaza, and community center costs; and (iv) fourth, all other eligible costs, including professional services and financing costs.

- Good-Faith Effort to Seek Extension. If, as of December 31, 2038 (the “TIF Benchmark Date”), cumulative TIF reimbursement to Developer is tracking materially below the projections supporting the $48,000,000 cap, the City shall use good-faith efforts to explore and, if feasible, pursue an extension of the TIF District or the adoption of a successor TIF district, subject to applicable law and the availability of eligibility findings. The City’s obligation under this subsection is one of good-faith effort and does not guarantee any extension.

- Reimbursement Mechanics. Developer shall submit periodic reimbursement requests accompanied by certified cost documentation prepared by Clearmont Accounting Group LLP (or another nationally recognized accounting firm acceptable to the City). The City shall process reimbursement requests within sixty (60) days of receipt of complete documentation. The City shall have audit rights with respect to reimbursement claims upon reasonable notice. Interest shall accrue on undisputed reimbursement amounts not paid within ninety (90) days of a complete request at the rate of [__]% per annum.

[Drafting Note — Conflict C10 (TIF shortfall risk). The Term Sheet (Section 5.2) provides that TIF reimbursement is subject to availability of increment and that the City does not guarantee the full $48,000,000 cap. The TIF Memo (Section IV) concludes that, adjusted for the Phase I property tax abatement, cumulative increment through 2042 may be approximately $38,000,000 to $42,000,000 — potentially $6,000,000 to $10,000,000 short of the $48,000,000 cap — and that under a worst-case timing scenario (maximum permitted delays) the cap is unlikely to be reached. The TIF Memo recommends that the development agreement (i) make TIF reimbursement expressly contingent on actual increment collected, (ii) establish a reimbursement priority, (iii) include a good-faith extension covenant, and (iv) expressly state that a TIF shortfall does not constitute a City default. Sections 5.2(c), (d), and (e) implement these recommendations. From the Developer’s perspective, the priority structure (remediation and infrastructure first) protects the most critical reimbursements, and the good-faith extension covenant and interest-on-delay provision mitigate timing risk. Developer should nonetheless recognize that the TIF Memo (City counsel’s analysis) indicates material shortfall risk; the Developer bears the timing and shortfall risk under the pay-as-you-go structure. The Lakeshore Side Letter (Section 4.3(a)) requires Investor consent to any change to the TIF reimbursement cap or eligible cost categories, and Section 3.5 prohibits Developer from agreeing to terms materially impairing the 14% Minimum IRR without Investor consent — so the TIF structure is also constrained by Developer’s internal investor obligations.]

[Drafting Note — Open item. The interest rate in Section 5.2(f) and the precise documentation/audit procedures should be finalized. The TIF Memo (Section VIII.6) recommends certified cost documentation by Clearmont Accounting Group LLP and City audit rights.]

### Section 5.3 Infrastructure Cost-Sharing.

- City Off-Site Commitment. The City shall fund $12,500,000 for off-site infrastructure improvements, including: (i) widening of Lakemont Station Boulevard between Oak Street and Maple Avenue; (ii) installation of a new traffic signal at the Oak Street/Lakemont Station Boulevard intersection; (iii) extension of the water main along Lakemont Station Boulevard; and (iv) sanitary sewer upgrade and capacity expansion. The City’s off-site infrastructure funding shall be appropriated and disbursed according to a schedule set forth in Exhibit [__], coordinated with the phased construction timeline, and shall be funded from the City’s general revenue or capital improvement funds, not from the TIF Special Tax Allocation Fund.

- Developer On-Site Responsibility. Developer shall fund $8,300,000 for on-site infrastructure improvements, including internal roadways, utilities, stormwater management, pedestrian pathways, and landscape improvements within the Property, to the extent such improvements serve a documented public purpose and are eligible for TIF reimbursement.

- Total Infrastructure Budget. The total combined infrastructure budget is $20,800,000 ($12,500,000 City + $8,300,000 Developer).

[Drafting Note — Conflict C12 (City infrastructure funding source vs. TIF cap). The TIF Memo (Section VII) notes that, if the City’s $12,500,000 infrastructure commitment is funded from TIF, it counts against the $48,000,000 cap — reducing reimbursement available to Developer. The TIF Memo recommends the funding source be specified in the development agreement. Developer’s position, reflected in Section 5.3(a), is that the City’s off-site infrastructure commitment is funded from general revenue or capital improvement funds, not TIF, preserving the full $48,000,000 cap for Developer reimbursement. The City should confirm the funding source. This is an open item.]

### Section 5.4 Property Tax Abatement.

The City shall provide a twelve (12)-year declining property tax abatement on Phase I improvements only, as follows: Years 1–4 — 75% abatement; Years 5–8 — 50% abatement; Years 9–12 — 25% abatement; Year 13 and thereafter — 0% (full assessment). The abatement shall apply to the incremental increase in assessed value attributable to the Phase I improvements, measured from the pre-development base equalized assessed value. No property tax abatement is provided for Phase II, Phase III, or Phase IV under this Agreement.

[Drafting Note — Conflict C28 (abatement–TIF interaction; later-phase abatement). The TIF Memo (Sections IV.B, VII) identifies an internal tension: the Phase I abatement benefits Developer by reducing its property tax burden but simultaneously reduces the TIF increment available for Developer reimbursement (because the abatement reduces the assessed value of Phase I improvements during the abatement years). The TIF Memo recommends the development agreement acknowledge this interaction and consider structuring the abatement to minimize its impact on TIF-capturable increment, if legally permissible. Developer should consider whether to negotiate an abatement structure that applies only to the non-TIF-captured portion of the tax bill. Additionally, Term Sheet Section 18.4 states that no abatement is provided for later phases and that the parties’ positions on later-phase incentives “shall be addressed during negotiation of the definitive Agreement.” Developer may seek abatement or additional incentives for later phases; this is an open item. The Lakeshore Side Letter (Section 4.3(b)) requires Investor consent to any change to the abatement schedule.]

### Section 5.5 Building Permit Fee Waiver.

The City shall waive building permit fees for Phase I and Phase II, with an estimated combined value of $1,400,000 ($920,000 for Phase I and $480,000 for Phase II). No building permit fee waiver is contemplated for Phase III or Phase IV. The permit fee waivers shall constitute a separate incentive and shall not be charged against the $48,000,000 TIF reimbursement cap.

### Section 5.6 Summary of Public Incentives.

The public incentives are summarized as follows: land write-down $9,200,000; TIF reimbursement up to $48,000,000; City off-site infrastructure funding $12,500,000; Phase I property tax abatement (12-year declining); and permit fee waivers $1,400,000.

## ARTICLE 6. ENVIRONMENTAL MATTERS

### Section 6.1 Environmental Conditions.

The environmental conditions of the Property are as documented in the Phase II ESA prepared by Greenfield Environmental Consultants LLC, dated November 8, 2024, and are summarized as follows:

- Parcel 12-24-300-015. No environmental contamination requiring further action was identified; no further investigation or remediation is required.

- Parcel 12-24-300-016. BTEX contamination in soil and groundwater over approximately 1.8 acres, and localized TCE contamination, attributable to the former Lakemont Ironworks operations (former UST farm and metal finishing/degreasing operations). Remediation under the IEPA VSRP is required, at an estimated cost of $2,800,000 and an estimated timeline of fourteen (14) to eighteen (18) months, culminating in issuance of an NFR Letter.

- Parcel 12-24-300-017. Low-level metals contamination (primarily arsenic) in shallow fill material, suitable for residential use with installation of an engineered barrier (clean fill cap), at an estimated cost of $340,000.

The total estimated environmental remediation cost is $3,140,000.

### Section 6.2 City Indemnification of Pre-Existing Environmental Conditions.

The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to pre-existing environmental conditions on the Property (Parcels 12-24-300-015, 12-24-300-016, and 12-24-300-017), including without limitation third-party claims, governmental enforcement actions, contribution or cost-recovery actions under federal or state environmental laws, and any contamination attributable to the former Lakemont Ironworks operations that ceased in 2009. The contamination identified in the Phase II ESA is pre-existing and attributable to the former Lakemont Ironworks operations; the City acquired the affected parcels with knowledge of the environmental conditions. This indemnity shall survive the expiration or termination of this Agreement and the conveyance of the Property.

### Section 6.3 Remediation Responsibility and Cost Allocation.

- Performance. Developer shall perform, or contract for, the remediation of Parcel 12-24-300-016 under the VSRP and the engineered barrier installation on Parcel 12-24-300-017, using Greenfield Environmental Consultants LLC or another qualified environmental consultant. Developer shall be the named applicant on the VSRP enrollment and NFR Letter application for Parcel 12-24-300-016, except as the parties may otherwise agree.

- Base Cost. The base estimated environmental remediation cost is $3,140,000 ($2,800,000 for Parcel 016 and $340,000 for Parcel 017). Environmental remediation costs are eligible TIF costs and shall be reimbursed to Developer on a first-priority basis under Section 5.2(d).

- Cost Overruns. The Phase II ESA (Section 5.3) warns that actual remediation costs may exceed the base estimate by 25% to 35% (with total Parcel 016 cost exposure of approximately $3,500,000 to $3,800,000, and combined total exposure of approximately $3,800,000 to $4,200,000 in a significant-scope-expansion scenario), due to potential discovery of additional contamination, extended groundwater treatment, or supplemental regulatory requirements. Any environmental remediation cost exceeding the base estimate of $3,140,000 shall be borne by the City, or, at Developer’s election, shall be reimbursed to Developer as an eligible TIF cost on a first-priority basis. The City shall not be entitled to offset such overruns against any other incentive or against the purchase price.

- Vapor Intrusion. If the vapor intrusion screening evaluation recommended in the Phase II ESA (Sections 7.1, 8.1) indicates that vapor mitigation measures (such as sub-slab depressurization systems, vapor barriers, or passive venting systems) are warranted for structures on or adjacent to the contaminated area of Parcel 12-24-300-016, the cost of such vapor mitigation measures shall be borne by the City or reimbursed to Developer as an eligible TIF cost, as a pre-existing environmental condition.

- Off-Site Investigation. If IEPA requires off-site groundwater monitoring (including on or adjacent to the Lakemont Central Metra station property, as recommended in the Phase II ESA Section 8.3), the City shall assist Developer in obtaining any required access from Metra or other third parties, and the cost of such off-site investigation shall be borne by the City or reimbursed as an eligible TIF cost.

- Pre-Remediation Plume Delineation. The Phase II ESA (Section 8.3) recommends the advancement of six to eight (6–8) additional soil borings on the periphery of the Parcel 12-24-300-016 BTEX plume to refine the lateral and vertical boundaries of the excavation zone prior to finalization of the RAP, in order to reduce the risk of encountering unexpected contamination during excavation and to improve the reliability of the remediation cost estimate. The cost of such pre-remediation plume delineation shall be borne by the City or reimbursed to Developer as an eligible TIF cost, as a pre-existing environmental condition investigation cost.

[Drafting Note — Open item O16 (pre-remediation plume delineation). The Phase II ESA (Section 8.3) recommends 6–8 additional soil borings to refine the Parcel 016 plume boundaries before the RAP is finalized, and off-site groundwater monitoring points on or adjacent to the Metra station property to confirm the absence of off-site plume migration (the latter addressed in Section 6.3(e)). Section 6.3(f) allocates the plume-delineation cost to the City or as a first-priority TIF cost, consistent with the pre-existing nature of the contamination. The Phase II ESA (Section 8.3) notes that off-site monitoring requires coordination with Metra for access (open item O7). These additional investigation costs are not included in the $3,140,000 base estimate and should be treated as TIF-eligible/City-borne rather than Developer-borne; the Lakeshore Side Letter (Section 4.3(d)) requires Investor consent for environmental obligations exceeding $3,140,000 without offset, so any such costs allocated to Developer would require Lakeshore consent.]

[Drafting Note — Conflict C14 (environmental cost allocation / overruns). The Term Sheet (Section 6) provides that the City indemnifies Developer for pre-existing environmental conditions and that remediation costs are TIF-eligible, but is silent on (i) which party performs the remediation, (ii) who bears cost overruns, and (iii) vapor mitigation and off-site investigation costs. The Phase II ESA (Section 8.2) recommends the transactional documents clearly identify the responsible party, the cost-allocation mechanism, and a cost-overrun provision (recommending 25–35% contingency), and notes that the City bears primary responsible-party status under the Illinois Environmental Protection Act because the contamination is pre-existing and the City owned the property with knowledge of the conditions. The Lakeshore Side Letter (Section 4.3(d)) requires Investor consent for any acceptance of environmental remediation obligations exceeding $3,140,000 without a corresponding increase in TIF reimbursement or direct City funding sufficient to offset the excess. Sections 6.3(c), (d), and (e) allocate overruns, vapor mitigation, and off-site investigation costs to the City (or as first-priority TIF costs), consistent with the pre-existing nature of the contamination and the City’s indemnity. The City may resist bearing overruns directly; this is a key open negotiation item. Developer’s internal constraint: any allocation of environmental obligations above $3,140,000 to Developer (rather than the City or TIF) requires Lakeshore’s consent.]

### Section 6.4 NFR Letter; Institutional Controls.

- Developer shall use commercially reasonable efforts to obtain the NFR Letter for Parcel 12-24-300-016 and to complete the engineered barrier and obtain the NFR Letter for Parcel 12-24-300-017. The NFR Letter for Parcel 12-24-300-016 is a prerequisite to residential development on that parcel.

- Any ELUC or institutional control recorded against the Property in connection with the VSRP (including the groundwater use restriction for Parcel 016 and the engineered barrier restriction for Parcel 017) shall constitute a Permitted Exception, in form reviewed and approved by the Construction Lender’s counsel and the title company. The consolidation plat shall expressly reference the institutional control area by legal description.

- The development standards under the PD-TOD rezoning shall account for the engineered barrier on Parcel 017, restricting below-grade construction in the barrier area unless proper environmental protocols (including IEPA notification and an approved soil management plan) are followed.

- Environmental Covenants and Access Agreements. The parties shall enter into environmental covenants and access agreements (in form acceptable to the City, Developer, the Construction Lender, and IEPA as applicable) granting access to the Property for environmental remediation, monitoring, verification sampling, and institutional-control maintenance activities, including access by Greenfield Environmental Consultants LLC, remediation contractors, IEPA personnel, and (for off-site investigation) Metra or other third parties as provided in Section 6.3(e). Resolution Section 6 directs Corporation Counsel to prepare “environmental covenants and access agreements” as ancillary documents to this Agreement.

[Drafting Note — Open item O17 (environmental covenants and access agreements). Resolution Section 6 directs Corporation Counsel and outside counsel to prepare, as ancillary documents to the Development Agreement, “environmental covenants and access agreements” (in addition to the deed, performance security instruments, community benefits provisions, and restrictive covenants). The environmental covenants include the ELUCs addressed in Section 6.4(b) (open item O10). The access agreements (Section 6.4(d)) grant access for remediation, monitoring, and institutional-control maintenance, including off-site access to Metra property for groundwater monitoring (Phase II ESA Section 8.3, open item O7). These ancillary documents must be developed and approved by the Construction Lender’s counsel and the title company to ensure they do not impair title insurability or the Construction Lender’s security interest, and should be listed in the exhibits (Article 22).]

[Drafting Note — Conflict C31 (ELUCs as encumbrances). The Phase II ESA (Sections 4.3.3, 6.2) notes that the ELUCs to be recorded against Parcels 016 and 017 constitute encumbrances on title and recommends the consolidation plat reference the institutional control area by legal description. The Loan Term Sheet (Section 4.2) lists environmental use controls/institutional controls recorded in connection with the IEPA VSRP NFR Letter and engineered barrier as Permitted Exceptions, “in each case as reviewed and approved by Lender’s counsel.” Sections 6.4(b) and (c) implement these recommendations. Open item O10 (form of ELUCs) must be developed and approved by the Construction Lender’s counsel and the title company to ensure the ELUCs do not impair title insurability.]

### Section 6.5 Environmental Insurance.

Developer shall obtain pollution legal liability insurance in an amount not less than $10,000,000, naming the City and the Construction Lender as additional insureds, with a policy term covering the full construction period and a three-year extended reporting period, in form acceptable to the Construction Lender.

### Section 6.6 Reliance Letter.

To the extent the City, the Construction Lender, or the title company require reliance on the Phase II ESA, Developer shall use commercially reasonable efforts to obtain a reliance letter from Greenfield Environmental Consultants LLC on terms acceptable to GEC. The Phase II ESA (Section 9) provides that third-party reliance requires execution of a reliance letter.

## ARTICLE 7. PROJECT FINANCING

### Section 7.1 Sources of Funds.

Developer’s preliminary sources and uses for the Project are summarized as follows:

| Source | Amount |
| --- | --- |
| Lakeshore Capital Partners Fund III LP — Equity | $51,000,000 |
| Pellegrini Family Trust — Equity | $34,000,000 |
| Total Committed Equity | $85,000,000 |
| Construction Loan — First Prairie National Bank | $210,000,000 |
| TIF Reimbursement (over time, up to) | $48,000,000 |
| Land Discount Value | $9,200,000 |
| Permit Fee Waivers | $1,400,000 |
| Additional Debt/Mezzanine (later phases, to be determined) | $58,400,000 |
| Total Sources | $412,000,000 |

### Section 7.2 Construction Loan.

The Construction Loan of up to $210,000,000 is available for Phase I and Phase II hard and soft construction costs; availability for Phases III and IV is subject to a separate supplemental commitment or amendment. The Construction Loan is subject to execution of this Agreement in form acceptable to the Construction Lender, satisfactory due diligence, and customary loan conditions. The Construction Loan has an initial term of thirty-six (36) months with two (2) six-month extension options (maximum forty-eight (48) months), and the outstanding principal is due at maturity or upon conversion to permanent financing. Developer shall deliver an executed take-out commitment from a creditworthy permanent lender no later than six (6) months prior to the initial maturity date, as required by the Construction Lender.

[Drafting Note — Open items O13, O14, O15 (Construction Loan terms). The Loan Term Sheet (Section 2.3) provides an initial 36-month term with two 6-month extensions (max 48 months), subject to milestone, appraisal, and no-default conditions. Section 2.4 requires Developer to deliver an executed take-out commitment from a permanent lender no later than six months before the initial maturity, and provides for mandatory prepayment of casualty proceeds above $5,000,000, residential unit sale proceeds, and TIF reimbursement receipts in excess of amounts allocated to non-Lender-financed Project costs. Section 1 requires Guarantors (Marcus J. Pellegrini individually and the Pellegrini Family Trust) to provide a completion guaranty and a partial repayment guaranty under a burn-down structure, the specific terms of which are to be determined. Section 2.2 provides for an interest reserve funded from Loan proceeds (estimated 24-month reserve for Phase I). These are Construction Loan terms rather than Development Agreement terms, but they create financing dependencies and deadlines (e.g., the take-out commitment, the 48-month maximum loan term) that interact with the Project phasing schedule in Article 12. The mandatory prepayment of TIF receipts (Loan Term Sheet Section 2.4) interacts with the TIF reimbursement structure in Article 5 and should be coordinated so that TIF receipts applied to prepay the Construction Loan do not impair Developer’s ability to recover TIF-eligible costs. The guaranty terms (O14) and interest reserve (O15) are open items to be finalized in the Construction Loan Documents.]

### Section 7.3 Equity First.

All $85,000,000 of committed equity shall be contributed and expended prior to any draw on the Construction Loan (equity-in-first basis), as required by the Construction Lender.

### Section 7.4 Additional Financing for Later Phases.

Approximately $58,400,000 in additional debt or mezzanine financing will be required for Phases II through IV. Developer anticipates sourcing this capital through a combination of mezzanine loans, institutional co-investment, and cash flow from completed earlier phases. The structure and terms of this additional financing have not yet been determined. Any additional indebtedness secured by the Property or Project assets, and any equity raise that results in dilution of the Pellegrini Interest, shall be subject to the Construction Lender’s prior written consent and the consent rights of Lakeshore Capital Partners Fund III LP under the Lakeshore Side Letter.

[Drafting Note — Open item O3 (later-phase financing). The Term Sheet (Section 7), the Loan Term Sheet (Section 3), and the Lakeshore Side Letter (Sections 5, 7(a)) all acknowledge the approximately $58,400,000 additional capital need for later phases but the structure is undetermined. The Loan Term Sheet (Section 6.3) requires the Construction Lender’s prior written approval of any subordinate financing, and Section 8.1 provides that dilution of the Pellegrini Family Trust’s interest below [50]% may constitute a Change of Control requiring the Construction Lender’s consent. The Lakeshore Side Letter (Section 5) grants Lakeshore preemptive and anti-dilution rights in connection with any new equity issuance. The Agreement should preserve Developer’s flexibility to raise later-phase capital subject to these consents, and the assignment/change-of-control provisions in Article 15 should include carve-outs for capital raises approved by both Lakeshore and the City (per Lakeshore Side Letter Section 8.3).]

[Drafting Note — Conflict C43 (Lakeshore indebtedness cap and no-lien restriction). The Lakeshore Side Letter (Section 7(a)) prohibits Developer, without Investor consent, from incurring Project-level indebtedness in excess of $210,000,000 (the Construction Lender facility) plus $58,400,000 (anticipated additional debt and mezzanine financing for later phases), or $268,400,000 in the aggregate. The Lakeshore Side Letter (Section 7(b)) further prohibits Developer, without Investor consent, from granting any lien, mortgage, security interest, or encumbrance on any portion of the Property other than the Construction Lender’s mortgage, standard permitted encumbrances, and liens required by this Agreement. These are internal Developer constraints that interact with the financing provisions of Article 7 and the collateral assignment in Section 16.7: the $268,400,000 aggregate indebtedness cap means any later-phase debt structure exceeding that amount requires Lakeshore consent, and the no-lien restriction means the only permitted real-property encumbrance is the Construction Lender’s first-priority mortgage (consistent with the Loan Term Sheet Section 4.2 and this Agreement’s Permitted Exceptions). Developer should ensure the Project Budget and later-phase financing plan remain within the $268,400,000 cap or obtain Lakeshore consent for any excess.]

### Section 7.5 Financial Capacity.

Developer’s audited financials are prepared by Clearmont Accounting Group LLP. Developer’s entity-level net worth is approximately $185,000,000, and Developer’s bonding capacity through Ridgepoint Surety Corporation is up to $75,000,000.

## ARTICLE 8. PERFORMANCE SECURITY

### Section 8.1 Phase I Performance Security.

Prior to conveyance of the Property to Developer, Developer shall post a performance bond in the amount of $15,000,000, issued by Ridgepoint Surety Corporation or another surety company reasonably acceptable to the City, or an irrevocable standby letter of credit in the equivalent amount issued by a nationally recognized financial institution acceptable to the City, securing Developer’s obligation to commence and substantially complete Phase I in accordance with this Agreement. The performance security shall be maintained continuously from the date of conveyance until Phase I Substantial Completion, as evidenced by issuance of a temporary or final certificate of occupancy by the City. Upon Phase I Substantial Completion, the performance security shall be released and returned to Developer within thirty (30) days following written request and verification of Substantial Completion by the City.

### Section 8.2 Later-Phase Performance Security.

The amount, form, and conditions of performance security for Phases II, III, and IV shall be established by agreement of the parties prior to the commencement of each such Phase, taking into account the scope and cost of the applicable Phase and the requirements of the Construction Lender.

[Drafting Note — Open item O4 (later-phase performance security). The Resolution (Condition #8(d)) and the Term Sheet (Section 8) specify $15,000,000 for Phase I only; amounts for later phases are “to be established in the definitive Agreement” (per the Lakeshore Side Letter Section 4.3(e), which requires Investor consent to any modification of performance security requirements). The later-phase amounts are not yet determined. Developer’s position: later-phase security should be calibrated to the scope of each Phase and should not be required in amounts disproportionate to the work secured, and should be releasable upon Substantial Completion of the applicable Phase. The Construction Lender (Loan Term Sheet Section 4.1) takes a collateral assignment of any performance bonds/LCs posted under this Agreement.]

## ARTICLE 9. DEVELOPMENT OBLIGATIONS

### Section 9.1 Construction Standards.

Developer shall construct the Project in accordance with plans and specifications approved under Section 3.9, the Project Budget, and all applicable laws, codes, and ordinances. Developer shall maintain a construction budget that includes a minimum 5% hard-cost contingency for each Phase.

### Section 9.2 LEED Gold Certification.

All buildings constructed as part of the Project shall achieve LEED Gold certification, or an equivalent green building certification, as administered by the U.S. Green Building Council. Developer shall register each building with the USGBC prior to commencement of construction of the applicable building and shall submit documentation of certification status to the City upon receipt of certification. The determination of whether an alternative certification is “equivalent” shall be made against objective green-building standards and shall not be subject to any single official’s sole discretion.

[Drafting Note — Conflict C20 (LEED “or equivalent” acceptability). Resolution Condition #8(f) provides that LEED Gold “or an equivalent green building certification as determined acceptable by the Director of the Community Development Department, Paul R. Vasquez” satisfies the requirement. The Term Sheet (Section 11.2) provides for LEED Gold “or an equivalent green building certification as may be approved by the City in writing.” The Loan Term Sheet (Section 6.1) requires LEED Gold “or an equivalent green building standard.” Developer’s position, reflected in Section 9.2, is that equivalence should be determined against objective standards rather than a single official’s sole discretion, to avoid an unreasonable veto. The City may insist on the Resolution’s Director-determination language; this is an open item.]

### Section 9.3 Prevailing Wage.

- All construction work performed pursuant to this Agreement that constitutes “public works” within the meaning of the Illinois Prevailing Wage Act, 820 ILCS 130/0.01 et seq. (the “Prevailing Wage Act”), shall be subject to the prevailing wage requirements of the Prevailing Wage Act. This includes, without limitation, the off-site public infrastructure improvements, the on-site infrastructure improvements to the extent TIF-reimbursed, the environmental remediation to the extent TIF-reimbursed, and the Phase IV public parking structure, public plaza, and community center.

- Developer shall include prevailing wage requirements in all contracts and subcontracts for construction work subject to the Prevailing Wage Act, shall maintain certified payroll records and make them available to the City and the Illinois Department of Labor upon request, and shall post prevailing wage rate schedules at the construction site.

- The parties acknowledge that the scope of Prevailing Wage Act applicability to purely private components of the Project (including market-rate residential, private office, retail, and hotel construction) is a matter of statutory interpretation that may be debatable. The Term Sheet (Section 11.1) states that “all construction performed on the Project shall comply with the Illinois Prevailing Wage Act.” To the extent the parties agree to extend prevailing wage coverage beyond the statutorily-required scope as a contractual matter, such extension shall be expressly set forth in Exhibit [__] and Developer shall be entitled to seek corresponding adjustments to the public incentives to offset any incremental cost.

- Monitoring, Enforcement, and Remedies. Developer shall covenant that all general contractors and subcontractors comply with the Prevailing Wage Act for all Project construction subject to it, shall submit certified payroll records to the City on a monthly basis, and shall grant the City the right to audit contractor and subcontractor payroll records upon reasonable notice. Developer’s indemnification of the City for prevailing wage violations is set forth in Section 17.5. As a remedy for a material, uncured prevailing wage violation on TIF-reimbursed components, the City may withhold TIF reimbursement payments otherwise due to Developer under Article 5 until the violation is cured; provided, that (i) the City shall not withhold TIF payments for violations on components that are not subject to the Prevailing Wage Act by statute or by the parties’ contractual agreement in Exhibit [__], and (ii) the City shall not withhold more than the documented amount of the violation plus penalties, and shall release withheld amounts promptly upon cure.

[Drafting Note — Conflict C42 (TIF withholding as prevailing wage remedy). The TIF Memo (Section V.C) recommends that the development agreement include, among prevailing wage compliance provisions, “specified remedies for non-compliance, including withholding of TIF reimbursement payments,” together with a Developer covenant, monthly certified payroll submission, City audit rights, and a Developer indemnification of the City. Section 9.3(d) and Section 17.5 implement these recommendations. Developer’s position, reflected in Section 9.3(d), is to (i) limit the TIF-withholding remedy to TIF-reimbursed components where prevailing wage applies (by statute or by the parties’ express contractual agreement), (ii) cap the withholding at the documented violation amount plus penalties, and (iii) require prompt release upon cure — so that the City cannot withhold TIF reimbursement for the entire Project based on a violation on a single component, and cannot withhold for components outside the prevailing wage scope. The City may seek broader withholding rights; reconcile. The Resolution (Section 8) requires the Development Agreement to include prevailing wage “record-keeping, reporting, and certification requirements,” which Sections 9.3(b) and (d) address.]

[Drafting Note — Conflict C13 (prevailing wage scope). The Term Sheet (Section 11.1) states that “all construction performed on the Project shall comply with the Illinois Prevailing Wage Act.” The TIF Memo (Section V) concludes that, given the substantial public financial assistance (land write-down, TIF, abatement, fee waivers), the Prevailing Wage Act “likely applies to all construction activity on the project site, not merely the TIF-reimbursed components,” and recommends the development agreement specify the scope with precision. The TIF Memo notes that the Term Sheet’s “all construction” language “converts a potentially debatable statutory question into an unambiguous contractual obligation” and that the Developer “should understand that this provision may increase construction costs for components… that might otherwise be argued to fall outside the statutory mandate.” Developer’s position, reflected in Section 9.3, is to (i) comply with the Prevailing Wage Act where it applies by statute, (ii) flag the debatability of full-project coverage, and (iii) seek offsetting incentive adjustments if the parties contractually extend coverage to purely private components. The City’s strongest position (per the TIF Memo) is broad application. This is a significant cost open item; the Lakeshore Side Letter (Section 3.5) prohibits Developer from agreeing to terms materially increasing total Project costs beyond $412,000,000 without Investor consent, so any contractual extension of prevailing wage that materially increases cost may require Lakeshore consent.]

### Section 9.4 Insurance.

Developer shall maintain, or cause its general contractor to maintain, throughout the construction period for each Phase, the following minimum insurance coverages: (a) Commercial General Liability (CGL) — $10,000,000 per occurrence and $25,000,000 in the aggregate; (b) Umbrella/Excess Liability — $25,000,000; (c) Builder’s Risk — full replacement value of each Phase under construction; (d) Workers’ Compensation — statutory limits; (e) Automobile Liability — $5,000,000 combined single limit; and (f) Professional Liability (Architect/Engineer) — $5,000,000. The City and the Construction Lender shall be named as additional insureds/loss payees, as applicable. All carriers shall be rated A- VII or better by A.M. Best. All policies shall provide not less than 30 days’ prior written notice of cancellation or material modification.

[Drafting Note — Conflict C9 (CGL aggregate). The Term Sheet (Section 11.3) requires CGL coverage of $10,000,000 per occurrence and $20,000,000 in the aggregate. The Loan Term Sheet (Section 5) requires CGL coverage of $10,000,000 per occurrence and $25,000,000 in the aggregate. Section 9.4 adopts the higher aggregate ($25,000,000) required by the Construction Lender, which also satisfies the Term Sheet. The Term Sheet’s lower aggregate is superseded by the Construction Lender’s requirement. Confirm the City accepts the $25,000,000 aggregate.]

### Section 9.5 Construction Monitoring.

Developer shall submit monthly draw requests supported by AIA G702/G703 documentation to the Construction Lender and shall provide quarterly construction progress reports to the City’s Community Development Department, including percentage of completion, updated schedule, and identification of any delays, within thirty (30) days following the end of each calendar quarter during which active construction is occurring.

## ARTICLE 10. COMMUNITY BENEFITS

### Section 10.1 Local Hiring.

Developer shall use commercially reasonable efforts to achieve a goal of 35% Lakemont residents for construction workforce employment across all Phases of the Project, measured on a cumulative project-wide basis. Developer shall submit quarterly reports to the City’s Community Development Department documenting local hiring percentages within thirty (30) days following the end of each calendar quarter during which active construction is occurring. Failure to achieve the 35% local hiring goal in any given quarter or on a cumulative basis shall not, in and of itself, constitute a default under this Agreement, provided Developer demonstrates good-faith efforts to achieve the goal, including posting job openings with the City’s workforce development partners, attending local job fairs, and providing reasonable notice of hiring opportunities to the Community Development Department.

[Drafting Note — Conflict C19 (local hiring — goal vs. requirement). The Term Sheet (Section 9) frames the 35% local hiring commitment as a goal measured on a cumulative project-wide basis, with good-faith compliance and an express statement that failure to achieve the goal “shall not, in and of itself, constitute a default.” Resolution Condition #8(c)(i), however, refers to “a local hiring goal requiring that not less than thirty-five percent (35%).” Developer’s position, reflected in Section 10.1, is that the 35% commitment is a good-faith goal, not a hard requirement, and that missing the goal is not a default if good-faith efforts are demonstrated. The City may seek to tighten this; reconcile the language.]

### Section 10.2 Living Wage.

Developer shall use commercially reasonable efforts to require that all permanent employees employed at retail establishments and hotel operations within the Project be compensated at a wage rate of not less than $17.50 per hour, indexed annually for inflation pursuant to Exhibit [__]. This obligation shall apply to employees of commercial tenants and hotel operators, and Developer’s obligation shall be limited to including a living-wage covenant in leases and operating agreements with such tenants and operators and using commercially reasonable efforts to enforce it; Developer shall not be personally liable for wage obligations of tenants or operators.

[Drafting Note — Conflict C18 (living wage — new obligation). Resolution Condition #8(c)(ii) requires a Community Benefits Agreement or provisions mandating a living wage of not less than $17.50 per hour for “all permanent employees employed at retail establishments and hotel operations within the Project.” This living-wage obligation does not appear in the Term Sheet (which addresses only local hiring) or the RFP Response (which addresses first-source hiring and local hiring but not a living wage). This is a new obligation introduced by the Resolution. Developer’s position, reflected in Section 10.2, is to (i) limit the obligation to a lease/operating-agreement covenant enforced through commercially reasonable efforts (rather than direct Developer liability for tenant wages), (ii) index the rate to avoid a fixed nominal amount eroding over time, and (iii) limit scope to retail and hotel permanent employees as stated in the Resolution. The City may seek broader coverage or direct liability; this is an open item. The Lakeshore Side Letter (Section 3.5) constraint on materially increasing Project costs may be implicated.]

### Section 10.3 First-Source Hiring.

Developer and its commercial tenants shall partner with the Lakemont Workforce Center for the recruitment, training, and hiring of individuals to fill permanent employment positions created within the Project, by providing the Workforce Center with notice of available positions prior to broader recruitment. Developer’s obligation shall be to maintain a first-source referral relationship with the Workforce Center and to give good-faith consideration to referred candidates; it shall not require Developer to hire any particular candidate or to hire exclusively through the Workforce Center.

[Drafting Note — Conflict C18 (first-source hiring). Resolution Condition #8(c)(iii) requires a first-source hiring program under which Developer and its commercial tenants “shall partner with the Lakemont Workforce Center for the recruitment, training, and hiring of individuals to fill permanent employment positions.” The RFP Response (Section 6.2) commits to a first-source hiring program. The Term Sheet (Section 9) does not expressly include first-source hiring (it addresses only local hiring). Developer’s position, reflected in Section 10.3, is to frame first-source as a good-faith referral/priority-notice program rather than an exclusive or mandatory hiring channel. The City may seek a stronger commitment; reconcile.]

### Section 10.4 Community Benefits Agreement.

The community benefits provisions set forth in this Article 10 shall be deemed to constitute the Community Benefits Agreement or Community Benefits provisions required by Resolution Condition #8(c), and no separate Community Benefits Agreement with third parties shall be required unless the parties otherwise agree in writing.

## ARTICLE 11. AFFORDABLE HOUSING

### Section 11.1 Affordable Units.

Developer shall include 106 Affordable Units across the Project, restricted to households earning at or below 60% of AMI, representing 20% of the 530 total residential units. The Affordable Units shall be distributed as follows: 64 Affordable Units in Phase I (out of 320 total residential units) and 42 Affordable Units in Phase III (out of 210 total residential units).

### Section 11.2 Integration and Comparability.

Affordable Units shall be distributed proportionally across unit types (studio, one-bedroom, and two-bedroom) and shall not be segregated or concentrated on particular floors or in separate wings. Affordable Units shall be comparable in design, finishes, and amenity access to market-rate units within the same building, subject to reasonable variations consistent with industry practice.

### Section 11.3 Affordability Restriction Period.

Affordability restrictions shall remain in effect for a minimum of thirty (30) years from the date of issuance of the certificate of occupancy for the applicable Phase. The affordability restrictions shall be memorialized by a restrictive covenant recorded against the applicable parcel and running with the land, in a form to be set forth in Exhibit [__].

### Section 11.4 Compliance.

Developer shall comply with the City’s Affordable Housing Compliance Program and shall provide annual income certification documentation to the City’s Community Development Department for all Affordable Units throughout the affordability restriction period.

[Drafting Note — Conflict C8 (affordable unit count). See the drafting note to Section 3.6. The Agreement states 106 Affordable Units, exceeding the City’s 20% minimum (Resolution Condition #8(g)) and the “at least 100” floor in the Term Sheet summary. The affordability covenant form (open item) should be developed in coordination with the Construction Lender and title company to ensure it does not impair title insurability or the Construction Lender’s security.]

## ARTICLE 12. PHASING, TIMELINES, AND FORCE MAJEURE

### Section 12.1 Phasing Schedule.

The Project shall be constructed in four Phases in accordance with the following schedule:

| Phase | Commencement Deadline | Substantial Completion Deadline |
| --- | --- | --- |
| Phase I | Groundbreaking no later than March 1, 2026 | September 30, 2028 |
| Phase II | Within 12 months of Phase I Substantial Completion | Within 24 months of Phase II commencement |
| Phase III | Within 12 months of Phase II Substantial Completion | Within 30 months of Phase III commencement |
| Phase IV | Concurrent with Phase III commencement | Within 24 months of Phase IV commencement |

The commencement deadline for each subsequent Phase is measured from the Substantial Completion date of the immediately preceding Phase, as may be extended by Force Majeure. Developer shall provide quarterly construction progress reports to the City.

[Drafting Note — Conflict C44 (Lakeshore 2035 overall-completion consent trigger). The Lakeshore Side Letter (Section 4.3(c)) requires Investor consent for any modification to phasing timelines that would extend overall Project completion beyond calendar year 2035, and Section 7(c) prohibits Developer, without Investor consent, from modifying the Project phasing schedule in a manner that would defer Phase I Substantial Completion beyond September 30, 2028 (as extended by force majeure) or defer overall Project completion beyond calendar year 2035. Under the contractual maximum schedule in Section 12.1, Phase III Substantial Completion would extend to approximately March 2035 and Phase IV to approximately September 2034 (per the RFP Response Section 10), so the contractual maximums sit at the edge of the Lakeshore 2035 outer boundary. Any Force Majeure extension or delay that pushes overall Project completion beyond 2035 would require Lakeshore consent under the Side Letter, in addition to any City consent. Developer should track the 2035 boundary and obtain Lakeshore consent proactively if delays are anticipated. The Term Sheet (Section 13) and Resolution do not impose a 2035 overall-completion deadline, so the 2035 constraint is an internal Developer (investor) constraint, not a City-imposed one.]

### Section 12.2 Substantial Completion.

“Substantial Completion” of a Phase means the completion of construction of the applicable Phase to the point where the building or improvements can be occupied and used for their intended purpose, as evidenced by the issuance of a temporary or final certificate of occupancy by the City’s Building Department for the applicable building(s). Substantial Completion of a Phase shall not be delayed by punch-list items, cosmetic defects, or minor incomplete work that does not prevent occupancy and use of the building for its intended purpose.

[Drafting Note — Open item O8 (Substantial Completion definition). The Term Sheet (Section 13) states that Substantial Completion “shall be defined in the definitive Agreement” and generally means completion to the point of occupancy, evidenced by a temporary or final certificate of occupancy. Resolution Condition #8(h) references Substantial Completion “as such term shall be defined in the Development Agreement.” Section 12.2 defines Substantial Completion in Developer-favorable terms tied to certificate of occupancy issuance and excluding punch-list/cosmetic items. The City may seek a stricter definition; reconcile.]

### Section 12.3 Force Majeure.

- Definition. “Force Majeure” means acts of God, fire, flood, earthquake, hurricane, tornado, severe weather events, pandemic, epidemic, quarantine, governmental health orders, war, terrorism, civil unrest, insurrection, strikes or labor disputes (other than those caused by Developer’s labor practices or failure to comply with applicable labor laws), industry-wide supply chain disruptions beyond Developer’s reasonable control, governmental moratoria on construction, actions or inactions of governmental authorities (including IEPA delays in reviewing or approving the RAP or NFR Letter application, and delays in the rezoning or parcel consolidation process), and actions or inactions of the City of Lakemont that prevent or materially delay construction.

- Effect. Force Majeure events shall extend the applicable deadlines for commencement and Substantial Completion on a day-for-day basis for the duration of the Force Majeure event.

- Aggregate Cap. The maximum extension of time available under this Section 12.3 shall not exceed eighteen (18) months in the aggregate across the Project.

- Notice. Developer shall provide written notice to the City within fifteen (15) business days of the occurrence of a Force Majeure event, describing the nature, anticipated duration, and expected impact, with updated notices as circumstances change.

- Mitigation. Developer shall use commercially reasonable efforts to mitigate the effects of any Force Majeure event.

- Exclusions. Force Majeure shall not include financial inability to perform, changes in market conditions, increases in the cost of labor or materials (unless attributable to an industry-wide supply chain disruption), Developer’s failure to obtain financing, or any event caused by Developer’s negligence or willful misconduct.

[Drafting Note — Conflict C21 (force majeure cap). The Term Sheet (Section 14) provides an 18-month aggregate Force Majeure cap across the Project. The Loan Term Sheet (Section 9(9)) provides Force Majeure extensions of “up to 180 days” (six months) for the Phase I Substantial Completion default, plus any Construction Lender-approved extension periods under Section 2.3. There is a gap: the Agreement permits up to 18 months of Force Majeure relief, but the Construction Loan may default after only 180 days (six months) of Force Majeure delay for Phase I. Developer should negotiate with the Construction Lender to align the loan’s Force Majeure cap with the Agreement’s 18-month cap, or to obtain Construction Lender extension approvals as needed. This is an open item. Section 12.3(a) also expressly includes IEPA review delays and rezoning/consolidation delays as Force Majeure (addressing the Phase II ESA’s recommendation, Section 8.2(d), that the transactional documents address whether delay in NFR Letter issuance constitutes Force Majeure or a deadline extension).]

### Section 12.4 Schedule Buffer.

Developer maintains a target accelerated schedule approximately two years ahead of the contractual maximum deadlines set forth in Section 12.1. The contractual maximum deadlines govern for purposes of this Agreement and provide buffer for regulatory, market, and construction contingencies.

## ARTICLE 13. DEFAULT AND CURE; TERMINATION

### Section 13.1 Monetary Defaults.

In the event of a monetary default by either party (including Developer’s failure to pay the land purchase price or the City’s failure to fund committed infrastructure amounts), the non-defaulting party shall provide written notice specifying the nature and amount of the default. The defaulting party shall have sixty (60) days from receipt of such notice to cure the default.

### Section 13.2 Non-Monetary Defaults.

In the event of a non-monetary default by either party (including failure to commence construction within applicable deadlines, failure to comply with affordable housing requirements, or failure to maintain required insurance), the non-defaulting party shall provide written notice specifying the nature of the default in reasonable detail. The defaulting party shall have ninety (90) days from receipt of such notice to cure the default; provided, that if the nature of the default is such that it cannot reasonably be cured within ninety (90) days, the defaulting party shall have such additional time as is reasonably necessary to effect a cure, so long as the defaulting party has commenced cure efforts within the initial 90-day period and is diligently and continuously pursuing cure to completion.

### Section 13.3 Termination by City.

The City may terminate this Agreement upon: (a) a material breach by Developer that remains uncured after expiration of the applicable cure period (as extended by the Construction Lender’s cure rights under Article 16); (b) Developer’s failure to commence Phase I construction within six (6) months following land conveyance; (c) Developer’s abandonment of the Project, evidenced by cessation of all construction activity for a period of one hundred eighty (180) consecutive days (other than cessation caused by Force Majeure); and (d) such other events of default as specified in this Agreement. The City’s termination right is subject to the completion-assurance mechanism in Article 14 and the Construction Lender’s cure rights in Article 16, and shall not include any reversionary interest or automatic reversion of title.

### Section 13.4 Termination by Developer.

Developer may terminate this Agreement upon: (a) the City’s failure to deliver clean, marketable, and insurable fee simple title to the Property at closing in accordance with Article 4; (b) the City’s failure to fund its committed infrastructure obligations ($12,500,000) within the timelines specified in Exhibit [__]; (c) a condemnation or taking by eminent domain (by any entity, including the City) of more than 15% of the Property by area or value; (d) the City’s failure to complete the rezoning or parcel consolidation within the timelines agreed by the parties; (e) the City’s material breach that remains uncured after the applicable cure period; and (f) such other events of default as specified in this Agreement.

[Drafting Note — Conflict C23 (condemnation 15%). The Term Sheet (Section 15) permits Developer to terminate if a condemnation by “any entity other than the City” exceeds 15% of the Property. The Loan Term Sheet (Section 9(8)) treats condemnation of more than 15% of the Project site by area or value as an Event of Default under the loan. Section 13.4(c) extends Developer’s termination right to condemnation by any entity, including the City, to align with the Loan Term Sheet’s broader treatment and to protect Developer against a City-initiated taking. The City may resist including City condemnation; reconcile. The 15% threshold is consistent across documents.]

### Section 13.5 Remedies.

Upon termination by a non-defaulting party, the non-defaulting party shall have all remedies available at law or in equity, including damages, specific performance, and injunctive relief, subject to the dispute resolution provisions of Article 18 and the completion-assurance mechanism in Article 14. Neither party shall be liable for consequential, special, or punitive damages except as expressly provided in this Agreement.

## ARTICLE 14. COMPLETION ASSURANCE (ALTERNATIVE TO REVERSIONARY INTEREST)

### Section 14.1 No Reversionary Interest.

The parties acknowledge that the Construction Lender has advised that any reversionary interest, right of re-entry, possibility of reverter, or other defeasible fee estate in favor of the City would render Developer’s fee simple title uninsurable, subordinate the Construction Lender’s first-priority mortgage, prevent foreclosure, and render the Construction Loan unsecurable. Accordingly, notwithstanding Resolution Condition #8(h), the Property shall not be subject to any reversionary interest, right of re-entry, possibility of reverter, fee simple determinable, fee simple subject to condition subsequent, or any other form of defeasible fee estate in favor of the City or any other party. Developer’s fee simple title to the Property shall remain absolute and indefeasible, subject only to Permitted Exceptions.

### Section 14.2 Alternative Completion-Assurance Mechanism.

In lieu of the reversionary interest contemplated by Resolution Condition #8(h), the parties adopt the following alternative mechanism to satisfy the City’s policy objective of ensuring timely Phase I completion while preserving Developer’s fee simple absolute title and the Construction Lender’s first-priority security interest:

- Phase I Completion Deadline. Developer shall achieve Substantial Completion of Phase I by September 30, 2028, as such deadline may be extended by Force Majeure under Section 12.3 and by the Construction Lender-approved extension periods.

- Cure Periods. If Developer fails to achieve Phase I Substantial Completion by the deadline (as extended), the City shall provide written notice of such failure. Developer shall have the cure periods set forth in Section 13.2 (90 days, plus additional time if diligently pursuing cure), followed by the Construction Lender’s additional cure rights under Article 16 (not less than 60 days beyond Developer’s cure period for non-monetary defaults, with extension if the Construction Lender is diligently pursuing a cure, including time necessary to obtain possession through foreclosure or a receiver).

- Contractual Repurchase Option. If, after expiration of all cure periods (including the Construction Lender’s extended cure period), Developer has failed to achieve Phase I Substantial Completion and the Construction Lender has not cured or completed Phase I, the City shall have a contractual option to repurchase the Property, exercisable only upon (i) Developer’s failure to achieve Phase I Substantial Completion within the agreed timeframe, (ii) expiration of all cure periods (including the Construction Lender’s extended cure period), and (iii) the Construction Lender’s prior written consent or full satisfaction of the outstanding Construction Loan balance. The repurchase price shall be the lesser of (A) the original purchase price paid by Developer ($9,200,000) or (B) the then-current fair market value of the Property as determined by an independent MAI appraiser mutually selected by the parties. The repurchase option shall be subordinate to the Construction Lender’s mortgage and shall not be exercisable until the Construction Lender’s mortgage is satisfied or the Construction Lender consents.

- Enhanced Performance Security. The $15,000,000 Phase I performance security under Article 8 shall be available to the City as liquidated security for Developer’s Phase I completion obligation, in addition to the repurchase option. The performance security shall be the City’s primary financial remedy for a Phase I completion failure, to be drawn upon only after expiration of all cure periods.

- No Automatic Reversion. Title to the Property shall not automatically revert to the City under any circumstance. The City’s remedies for a Phase I completion failure are limited to the contractual remedies set forth in this Article 14 (the repurchase option and the performance security) and the termination and damage remedies under Article 13, in each case subject to the Construction Lender’s rights under Article 16.

[Drafting Note — Conflict C1 (reversionary interest — central conflict). This Article 14 is the most critical provision in this draft and the single most important open item. Resolution Condition #8(h) requires Developer to grant the City a reversionary interest with automatic reversion of fee simple title if Phase I is not Substantially Complete within 36 months of conveyance. The Construction Lender (Loan Term Sheet Sections 4.2, 7.1(1), 12(a), and the “Specific Concern” discussion in Section 12) states unequivocally that it “cannot commit to a loan secured by a mortgage on property that is subject to a reversionary interest or any form of defeasible fee estate” and that incorporation of the reversionary interest “as stated in the Resolution, would make the Loan impossible to close.” The Construction Lender suggests five alternative mechanisms: (i) a contractual repurchase option exercisable only after cure periods and Construction Lender consent/satisfaction; (ii) a performance escrow/additional letter of credit; (iii) liquidated damages; (iv) an enhanced completion guaranty; and (v) a right of first refusal subordinate to the mortgage. Section 14.2 adopts a combination of alternatives (i) and (ii) (repurchase option plus the existing $15,000,000 performance security), which the Construction Lender specifically identified as acceptable. The Lakeshore Side Letter (Section 7(d)) requires Investor consent to any clawback, reversionary interest, right of re-entry, repurchase option, or similar mechanism, and acknowledges that the parties “must negotiate terms compatible with the Construction Lender’s requirements and Investor’s interests.” Accordingly, this Article 14 requires both City agreement (to deviate from the literal terms of Resolution Condition #8(h), likely via a further City Council action or a Corporation Counsel determination that the alternative satisfies the condition) and Lakeshore consent. This must be resolved before execution; if the City insists on the literal reversionary interest, the Construction Loan cannot close and the Project financing fails.]

[Drafting Note — Conflict C2 (36-month clock). Resolution Condition #8(h) measures the 36-month period from the date of conveyance. Section 14.2(a) instead measures the completion obligation against the Phase I Substantial Completion deadline of September 30, 2028 (as extended by Force Majeure and Construction Lender extensions), which is tied to the March 1, 2026 groundbreaking. This avoids the timing mismatch under which a 36-month-from-conveyance clock could expire before the Substantial Completion deadline. The City should confirm acceptance of measuring the completion assurance against the Substantial Completion deadline rather than a fixed 36-month-from-conveyance period.]

[Drafting Note — Conflict C45 (Resolution “net of damages” refund vs. alternative repurchase price). Resolution Condition #8(h) provides that, upon reversion, the City’s obligation is to refund to Developer the purchase price paid “net of any damages incurred by the City as a result of the Developer’s failure to timely complete Phase I.” The alternative repurchase option in Section 14.2(c) instead sets the repurchase price at the lesser of the original purchase price ($9,200,000) or then-current fair market value (by MAI appraisal), and does not include a “net of damages” deduction. These mechanisms differ: the Resolution’s “net of damages” concept allows the City to offset its actual damages against the refund, while Section 14.2(c)’s “lesser of purchase price or FMV” could result in a repurchase price below the original purchase price if the Property’s value has declined, but does not separately deduct the City’s damages. If the City wishes to preserve a damages offset within the alternative mechanism, the parties should negotiate whether the City’s actual damages (above the performance security drawn under Section 14.2(d)) may be offset against the repurchase price, subject to a cap and the Construction Lender’s mortgage priority. This is an open item; Developer’s position is that the $15,000,000 performance security (Section 14.2(d)) is the City’s primary financial remedy and that the repurchase price should not be further reduced by a discretionary damages offset.]

[Drafting Note — Conflict C46 (loan default on imposition of lien/reversion). The Loan Term Sheet (Section 9(11)) provides that the “imposition, creation, or recording of any lien, encumbrance, or interest upon the Project site without Lender’s prior written consent, including without limitation any reversionary interest, right of re-entry, possibility of reverter, or defeasible condition in favor of the City of Lakemont or any other party,” constitutes an Event of Default under the Construction Loan. This is a distinct loan-default trigger that reinforces the prohibition in Article 14 and Section 4.4: even if the City were to record a reversionary interest (contrary to this Agreement), the act of recording would simultaneously default the Construction Loan. This underscores that no reversionary interest may be recorded against the Property. The Resolution (Condition #8(h)) contemplates that the reversionary interest “shall be recorded against the Property at the time of conveyance”; Section 4.4 and Article 14 prohibit any such recording, and the City must agree that no reversionary interest will be recorded.]

## ARTICLE 15. ASSIGNMENT AND CHANGE OF CONTROL

### Section 15.1 Restriction on Assignment.

Developer may not assign this Agreement, or any interest therein, in whole or in part, without the prior written consent of the City, which consent may be withheld in the City’s reasonable discretion; provided, that the City’s consent shall not be required, and shall not be unreasonably withheld, conditioned, or delayed, for the assignments described in Sections 15.1.1, 15.1.2, and 15.1.3. Any purported assignment in violation of this Article 15 shall be void and of no force and effect and shall constitute a material default. For purposes of this Article 15, “assignment” includes any direct or indirect transfer, conveyance, pledge, hypothecation, or other disposition of this Agreement or any interest therein, whether voluntary or involuntary, by operation of law or otherwise.

### Section 15.1.1 Permitted Assignment to Pellegrini-Controlled Entity.

Developer may assign this Agreement without the City’s prior written consent to an entity in which Marcus J. Pellegrini (or the Pellegrini Family Trust) holds at least a 50% controlling interest and which entity expressly assumes in writing all of Developer’s obligations under this Agreement. Developer shall provide the City with written notice of any such permitted assignment, together with a copy of the assignment and assumption agreement, within fifteen (15) days of the effective date.

### Section 15.1.2 Permitted Transfers Among Existing Members.

Transfers of membership interests in Developer among the existing members (Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, and TransitWorks Equity Group LLC), and transfers by Marcus J. Pellegrini for estate-planning purposes to family trusts or entities controlled by Pellegrini (provided Pellegrini retains management control), shall not require the City’s consent and shall not constitute a Change of Control, so long as the Pellegrini Interest is not reduced below the threshold set forth in Section 15.2.

### Section 15.1.3 Permitted Transfers for Approved Capital Raises.

Transfers of membership interests in Developer in connection with a capital raise (including for later Phases) that has been approved by both Lakeshore Capital Partners Fund III LP (pursuant to the Lakeshore Side Letter) and the City shall not require separate City consent for the assignment itself, provided the assignee expressly assumes Developer’s obligations in writing. The City shall respond to any request for consent to a capital raise within thirty (30) days and shall not unreasonably withhold, condition, or delay such consent.

### Section 15.1.4 Assignment to Construction Lender or Foreclosure Purchaser.

Notwithstanding Section 15.1, Developer may assign this Agreement to the Construction Lender or to a Construction Lender-designee, or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, without the City’s prior consent; or, if City consent is required, such consent shall not be unreasonably withheld, conditioned, or delayed, and the City shall respond within thirty (30) days of request. Any such assignee shall assume Developer’s obligations under this Agreement in writing.

### Section 15.2 Change of Control.

A “Change of Control” shall be deemed to occur upon any of the following events: (a) the Pellegrini Interest falls below [50]% of the total membership interests in Developer; (b) Marcus J. Pellegrini ceases to serve as Manager and Chief Executive Officer of Developer and is not replaced by a person reasonably approved by the City (and, where applicable, by Lakeshore Capital Partners Fund III LP and the Construction Lender) within sixty (60) days following such cessation; (c) any single person or entity (other than the Pellegrini Family Trust, Lakeshore Capital Partners Fund III LP, or TransitWorks Equity Group LLC) acquires 25% or more of the membership interests in Developer; or (d) Developer merges with, consolidates into, or is acquired by another entity. Any Change of Control that occurs without the City’s prior written consent shall constitute a material default under this Agreement, subject to the cure provisions of Section 13.2 and the 60-day replacement period in subsection (b).

[Drafting Note — Conflict C47 (Lakeshore Change-of-Control consequences). The Lakeshore Side Letter (Section 5.4) provides that, upon a Change of Control (as defined in the Side Letter, with the 51% threshold) occurring without Investor consent, Lakeshore may elect, by written notice within ninety (90) days of becoming aware of such Change of Control, to exercise one of two remedies: (a) a repurchase right requiring Developer to repurchase Lakeshore’s entire membership interest at the greater of (x) unreturned capital contributions plus the 14% Minimum IRR accrued thereon, or (y) fair market value (by independent MAI appraiser, or by arbitration if the parties cannot agree); or (b) a management right to assume the role of Manager or appoint a co-Manager alongside Pellegrini (or his successor), subject to obtaining any required consent from the City under this Agreement and the Construction Lender under the loan documents. These are investor-side remedies that operate independently of this Agreement, but they interact with the assignment/change-of-control provisions here: a Lakeshore repurchase right or management-right election could itself alter Developer’s ownership or management structure, potentially implicating the City’s change-of-control consent under Section 15.2 and the Construction Lender’s change-of-control provisions. The Lakeshore Side Letter (Section 5.4(b)) expressly conditions the management-right remedy on obtaining City and Construction Lender consent. Developer should ensure that any Lakeshore Change-of-Control remedy is coordinated with, and does not independently trigger, a City or Construction Lender default; the City may wish to be notified of any Lakeshore Change-of-Control election. This is an open item.]

### Section 15.3 Key Person Provision.

The parties acknowledge that the City’s selection of Developer was based, in substantial part, on the qualifications, experience, and financial capacity of Marcus J. Pellegrini. Accordingly, Marcus J. Pellegrini shall serve as Manager and Chief Executive Officer of Developer and shall exercise day-to-day management authority over the Project. The Key Person requirement in Section 15.2(b) is intended as an alternative or supplement to rigid percentage-of-interest thresholds, providing the City with assurance of Pellegrini’s active and material involvement while accommodating the internal transfers and approved capital raises contemplated by Sections 15.1.2 and 15.1.3.

[Drafting Note — Conflict C3 (assignment / change-of-control thresholds). Three different thresholds appear across the source documents: (i) the Term Sheet (Section 10) permits assignment without City consent only to an entity in which Pellegrini holds “at least a 50% controlling interest”; (ii) the Loan Term Sheet (Section 8.1) defines a Change of Control if Pellegrini ceases to hold “at least a [50]%” interest (bracketed, “subject to further discussion and negotiation”), or ceases as Manager/CEO, or a new investor acquires 25% or more; and (iii) the Lakeshore Side Letter (Section 5.2) defines a Change of Control if the Pellegrini Interest falls below 51%, or Pellegrini ceases as Manager/CEO (not replaced within 60 days by a person reasonably approved by Investor), or a new person acquires 25% or more, or a merger/consolidation/acquisition. The Lakeshore Side Letter (Section 4.4) expressly states that the 51% threshold is “intended to provide Investor with enhanced governance protections at a level above the assignment restriction threshold contemplated in the Term Sheet (which requires Pellegrini to hold at least fifty percent (50%) controlling interest).” Section 15.2 uses [50]% (bracketed) to track the Term Sheet and the Loan Term Sheet’s bracketed figure, but the Lakeshore Side Letter’s 51% threshold creates an internal Developer constraint: if the Pellegrini Interest falls below 51%, Lakeshore obtains enhanced consent rights over all amendments to this Agreement (not just Material Amendments) and a Change of Control remedy under the Side Letter. The three thresholds must be harmonized. The Lakeshore Side Letter (Section 8.3) commits Developer to negotiate Development Agreement assignment/change-of-control provisions that include (i) carve-outs for internal transfers among existing members, (ii) carve-outs for capital raises approved by both Investor and the City, (iii) a Key Person provision as an alternative/supplement to rigid percentage thresholds, and (iv) a reasonable cure period (not less than 60 days) before any assignment default. Sections 15.1.2, 15.1.3, 15.2(b), and 15.3 implement these commitments. Open items: (a) confirm whether the City will accept [50]% or insist on a different figure, and whether the Construction Lender’s bracketed [50]% is finalized; (b) reconcile the 51% Lakeshore threshold with the Agreement’s threshold (Developer may need to maintain the Pellegrini Interest at or above 51% to avoid triggering Lakeshore’s enhanced rights, even if the Agreement threshold is 50%); (c) confirm the City accepts the Key Person alternative and the carve-outs. The Loan Term Sheet (Section 8.1) also provides that dilution of the Pellegrini Family Trust’s interest below [50]%, “whether through additional equity raises, capital calls, anti-dilution adjustments, or admission of new members for Phases III and IV or otherwise, will require Lender’s prior written consent and may trigger a Change of Control” — so later-phase capital raises implicate both the Construction Lender’s and Lakeshore’s consent rights.]

## ARTICLE 16. CONSTRUCTION LENDER PROTECTIONS

### Section 16.1 Lender Notice and Cure Rights.

The City shall provide the Construction Lender with prompt written notice of any default by Developer under this Agreement, and the Construction Lender shall have the right (but not the obligation) to cure such default. The Construction Lender’s additional cure period shall be not less than thirty (30) days beyond Developer’s cure period for monetary defaults and not less than sixty (60) days beyond Developer’s cure period for non-monetary defaults, with such periods extended as necessary if the Construction Lender is diligently pursuing a cure that requires additional time (including time necessary to obtain possession of the Property through foreclosure or appointment of a receiver).

### Section 16.2 Lender Consent to Amendments.

No material amendment, modification, supplement, or termination of this Agreement shall be effective without the Construction Lender’s prior written consent, which shall not be unreasonably withheld, conditioned, or delayed. “Material amendment” has the meaning set forth in the Lakeshore Side Letter (Section 2) and includes, without limitation, amendments that reduce or restructure any public incentive, accelerate or extend any phase deadline by more than six (6) months, increase Developer’s financial obligations, modify affordable housing requirements, modify assignment or change-of-control restrictions, or alter any completion-assurance mechanism.

### Section 16.3 Subordination of City Interests.

Any lien, encumbrance, or security interest that the City may hold or acquire in the Property (other than the City’s rights under the completion-assurance mechanism in Article 14, which are structured as contractual remedies rather than real-property interests) shall be subordinated to the Construction Lender’s first-priority mortgage pursuant to a subordination and intercreditor agreement in form and substance acceptable to the Construction Lender.

### Section 16.4 Foreclosure; Assignment to Lender-Designee.

This Agreement shall be assignable to the Construction Lender or a Construction Lender-designee, or to a third-party purchaser at a foreclosure sale or pursuant to a deed-in-lieu of foreclosure, as provided in Section 15.1.4, without the City’s prior consent (or, if consent is required, such consent shall not be unreasonably withheld, conditioned, or delayed, with a 30-day response). The Construction Lender’s mortgage shall remain a first-priority lien on the Property and all improvements.

### Section 16.5 Estoppel Certificates.

The City shall deliver estoppel certificates to the Construction Lender upon reasonable request (not more than twice per calendar year), certifying the status of this Agreement, the existence or absence of any outstanding defaults by Developer, and such other customary matters as the Construction Lender may reasonably request.

### Section 16.6 Lender Review of Agreement.

This Agreement shall be delivered to the Construction Lender in draft form not less than fifteen (15) business days prior to its proposed execution date and shall not be executed until the Construction Lender has confirmed in writing that it is in form and substance acceptable to it.

[Drafting Note — Conflict C25 (Lender protections). This Article 16 implements the Construction Lender’s required Development Agreement provisions set forth in Loan Term Sheet Section 12: (a) no reversionary interest (implemented in Article 14); (b) Lender notice and cure rights (Section 16.1); (c) Lender consent to material amendments (Section 16.2); (d) subordination of City interests (Section 16.3); (e) foreclosure/deed-in-lieu assignment (Sections 15.1.4, 16.4); and (f) estoppel certificates (Section 16.5). These provisions are necessary for the Construction Loan to close. The City may resist certain provisions — particularly Section 16.3 (subordination of City interests to the Construction Lender’s mortgage) and Section 16.4 (assignment to a foreclosure purchaser without City consent) — as these limit the City’s control over the Project following a Developer default. These are open negotiation items with the City. The Lakeshore Side Letter (Section 4.2) also requires Lakeshore’s consent for Material Amendments, so amendments to this Agreement will require both Construction Lender and Lakeshore consent (Developer’s external and internal constraints). Section 16.2 cross-references the Lakeshore Side Letter’s definition of “Material Amendment” to promote consistency.]

[Drafting Note — Conflict C39 (cross-default DA↔Loan). The Loan Term Sheet (Section 9(5)) provides that a material default by Developer under this Agreement that is not cured within applicable cure periods, or any termination of this Agreement by the City for any reason, constitutes an Event of Default under the Construction Loan. The cure periods in Article 16.1 are intended to give the Construction Lender time to cure a Developer default before the loan defaults, but Developer should recognize that a City termination of this Agreement would cross-default the loan. Coordinate the cure periods and termination triggers accordingly.]

### Section 16.7 Collateral Assignment of Agreement and TIF Reimbursement Rights.

Notwithstanding Section 15.1, Developer may grant to the Construction Lender, as security for the Construction Loan, a collateral assignment of (a) this Agreement and all of Developer’s rights, title, and interest hereunder, and (b) Developer’s rights to receive TIF reimbursement payments under Article 5 (up to the $48,000,000 cap), in each case without the City’s prior written consent. The City shall reasonably cooperate with Developer and the Construction Lender in documenting such collateral assignment, including by acknowledging the assignment in a consent and acknowledgment agreement in form reasonably acceptable to the City. The City’s covenants and obligations under this Agreement shall run in favor of, and shall be enforceable by, the Construction Lender as an assignee to the extent of the collateral assignment. The City shall not be obligated to deal directly with the Construction Lender except upon notice of an enforcement action following a Developer default, and the City shall have no greater obligations to the Construction Lender than it has to Developer under this Agreement.

[Drafting Note — Conflict C41 (collateral assignment of DA and TIF rights). The Loan Term Sheet (Section 4.1) requires the Construction Lender to receive, as collateral for the Construction Loan, a “Collateral assignment of all construction contracts, architect agreements, development agreements (including the Development Agreement with the City of Lakemont), and other material Project contracts” and a “Collateral assignment of Borrower’s rights to receive TIF reimbursement payments under the Development Agreement (up to $48,000,000).” This collateral assignment is a condition of the Construction Loan and is distinct from the outright assignment to a foreclosure purchaser addressed in Sections 15.1.4 and 16.4. Section 16.7 expressly permits the collateral assignment of this Agreement and the TIF reimbursement rights to the Construction Lender without City consent, and requires the City to acknowledge the assignment. The City may seek to condition its acknowledgment or to limit the Construction Lender’s direct enforcement rights; this is an open negotiation item. The Lakeshore Side Letter (Section 7(b)) prohibits Developer from granting any lien, mortgage, security interest, or encumbrance on the Property other than the Construction Lender’s mortgage, standard permitted encumbrances, and liens required by this Agreement — so the collateral assignment of TIF rights (a contractual/financial right, not a lien on real property) is consistent with the Lakeshore Side Letter, but Developer should confirm that the collateral assignment of this Agreement does not implicate the Lakeshore no-lien restriction.]

## ARTICLE 17. INDEMNIFICATION

### Section 17.1 Mutual Indemnification.

Each party shall indemnify, defend, and hold harmless the other party, and its officers, employees, agents, and representatives, from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees and court costs) arising from or related to the indemnifying party’s negligent acts or omissions, reckless conduct, or willful misconduct in connection with the performance of its obligations under this Agreement.

### Section 17.2 Developer Indemnification of City.

Developer shall indemnify, defend, and hold harmless the City from and against all claims, demands, actions, damages, losses, costs, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to construction activities on the Property, including without limitation claims for personal injury, death, property damage, and workers’ compensation, regardless of whether such claims are brought by Developer’s employees, contractors, subcontractors, or third parties.

### Section 17.3 City Indemnification of Developer (Environmental).

The City shall indemnify, defend, and hold harmless Developer, its members, officers, employees, agents, contractors, and successors from and against all claims, demands, actions, losses, costs, damages, liabilities, and expenses (including reasonable attorneys’ fees) arising from or related to pre-existing environmental conditions on the Property, as provided in Section 6.2.

### Section 17.4 Survival.

The indemnification obligations set forth in this Article 17, and the environmental indemnity in Section 6.2, shall survive the expiration or termination of this Agreement.

### Section 17.5 Prevailing Wage Indemnification.

Developer shall indemnify the City for any claims, penalties, or liabilities arising from prevailing wage violations on the Project to the extent attributable to Developer’s or its contractors’ non-compliance with the Prevailing Wage Act, subject to the scope of prevailing wage applicability set forth in Section 9.3.

[Drafting Note — The Term Sheet (Section 16) provides mutual indemnification, Developer indemnification of the City for construction activities, and City indemnification of Developer for pre-existing environmental conditions, with survival. Section 17.5 adds a prevailing wage indemnity as recommended by the TIF Memo (Section V.C), scoped to the prevailing wage applicability in Section 9.3. Developer should seek to limit the prevailing wage indemnity to violations on components where prevailing wage is statutorily required or contractually agreed, rather than all Project components.]

## ARTICLE 18. DISPUTE RESOLUTION

### Section 18.1 Negotiation.

The parties shall first attempt to resolve any dispute arising under or related to this Agreement through good-faith negotiation between the City Manager (or designee) and Developer’s CEO (or designee) for a period of thirty (30) days following written notice of the dispute by either party.

### Section 18.2 Mediation.

If the dispute is not resolved through negotiation within the 30-day period, the dispute shall be submitted to non-binding mediation before the Lakemont Mediation Center, or such other neutral mediator as the parties may agree. The costs of mediation shall be shared equally by the parties, and each party shall bear its own attorneys’ fees.

### Section 18.3 Binding Arbitration.

If the dispute is not resolved through mediation within sixty (60) days following submission to the mediator, the dispute shall be submitted to final and binding arbitration administered under the Commercial Arbitration Rules of the American Arbitration Association, conducted by a single arbitrator with experience in real estate development matters. All mediation and arbitration proceedings shall be conducted in Cook County or Lake County, Illinois.

### Section 18.4 Provisional Remedies.

Nothing in this Article 18 shall prevent either party from seeking temporary restraining orders, preliminary injunctions, or other provisional judicial relief where necessary to prevent irreparable harm, pending resolution of the dispute through the procedures set forth above.

### Section 18.5 Governing Law.

This Agreement shall be governed by and construed in accordance with the laws of the State of Illinois, without regard to conflict-of-laws principles.

[Drafting Note — Conflict C22 (dispute resolution). The Term Sheet (Section 17) provides a three-step process: negotiation (30 days), mediation (Lakemont Mediation Center, 60 days), and binding AAA arbitration (single arbitrator, Cook or Lake County). The Lakeshore Side Letter (Section 10.2) uses a similar negotiation/mediation/arbitration structure under AAA rules in Cook County. The Loan Term Sheet (Section 13), by contrast, provides for litigation in Cook County state or federal courts (not arbitration). The dispute-resolution mechanisms in the different agreements can coexist because they govern different contracts, but Developer should be aware that a dispute could simultaneously proceed under this Agreement’s arbitration framework and the Construction Loan’s litigation framework if the same facts implicate both contracts. The Term Sheet’s arbitration framework is adopted here. Open item: confirm the City accepts AAA arbitration (some municipalities resist binding arbitration of public contracts); confirm venue county (Cook or Lake) consistent with the county determination in the drafting note to Section 1.1.1.]

## ARTICLE 19. REPRESENTATIONS AND WARRANTIES

### Section 19.1 Developer Representations.

Developer represents and warrants that: (a) it is a limited liability company duly organized, validly existing, and in good standing under the laws of the State of Illinois; (b) it has full power and authority to enter into this Agreement and to perform its obligations hereunder, and the execution and delivery of this Agreement has been duly authorized; (c) the execution and delivery of this Agreement will not conflict with or violate Developer’s organizational documents, the Construction Loan Documents, or any other material agreement to which Developer is a party; (d) the ownership structure of Developer is as set forth in Section 1.1.4; (e) Developer has the financial capacity, development experience, and organizational resources necessary to complete the Project; (f) Developer’s entity-level net worth is approximately $185,000,000 and its bonding capacity is up to $75,000,000; and (g) there are no environmental conditions on the Property other than those disclosed in the Phase II ESA.

### Section 19.2 City Representations.

The City represents and warrants that: (a) it has full power and authority to enter into this Agreement and to perform its obligations hereunder, and the execution and delivery of this Agreement has been duly authorized, including by the City Council; (b) the City has good and marketable fee simple title to the Property, free and clear of all liens, encumbrances, and adverse claims (except Permitted Exceptions), and has the legal authority to convey the Property to Developer; (c) the Property is located within the TIF District and TIF funds are legally available for the purposes described in this Agreement, subject to annual appropriation and the availability of increment; (d) the rezoning and parcel consolidation will be completed as provided in Article 2; and (e) the City has disclosed all known environmental conditions on the Property through the Phase II ESA and other materials provided to Developer.

[Drafting Note — The Term Sheet (Section 18.1) contemplates customary representations and warranties, including the City’s representation of good and marketable fee simple title and the availability of TIF funds subject to annual appropriation and increment availability. Section 19.2(e) adds a City representation regarding disclosure of known environmental conditions, supporting the City’s indemnity for pre-existing environmental conditions in Sections 6.2 and 17.3. The Phase II ESA (Section 4.2.4) notes that the City acquired Parcels 016 and 017 in 2018 “with knowledge of the environmental conditions” and that the City’s 2018 purchase records reference a prior Phase I ESA identifying the UST farm and metal finishing operations as potential contamination sources.]

## ARTICLE 20. REPORTING AND ACCESS

### Section 20.1 Reports to the City.

Developer shall provide the City with: (a) quarterly construction progress reports within thirty (30) days following the end of each calendar quarter during active construction; (b) quarterly local hiring reports within thirty (30) days following the end of each calendar quarter; and (c) annual income certification documentation for Affordable Units throughout the affordability restriction period.

### Section 20.2 Reports to Equity Investors and Lender.

Developer shall provide Lakeshore Capital Partners Fund III LP and the Construction Lender with the reports required under the Lakeshore Side Letter and the Construction Loan Documents, respectively, including monthly construction progress reports, quarterly and annual financial statements, copies of material correspondence with the City and IEPA, and prompt notice of any default or alleged default under this Agreement.

### Section 20.3 Access.

The City shall have reasonable access to the Property during normal business hours upon not fewer than three (3) business days’ advance written notice for inspection and monitoring purposes, subject to safety and security requirements.

[Drafting Note — Conflict C38 (reporting overlap). The Term Sheet, the Lakeshore Side Letter (Section 6), and the Loan Term Sheet (Sections 6.1, 6.2) each impose overlapping reporting obligations with different frequencies and recipients: the Term Sheet requires quarterly construction and local-hiring reports to the City; the Lakeshore Side Letter requires monthly construction reports (within 15 days of month-end), quarterly unaudited financials (within 45 days), annual audited financials (within 90 days), copies of all material City/Construction Lender/IEPA correspondence, prompt notice (within 5 business days) of any default, and copies of all TIF reimbursement requests; and the Loan Term Sheet requires monthly draw requests, annual audited financials (within 120 days), and quarterly unaudited financials (within 45 days). Sections 20.1 and 20.2 allocate reports by recipient. Developer should seek to harmonize the financial-statement deadlines (the Lakeshore Side Letter’s 90-day annual deadline is shorter than the Loan Term Sheet’s 120-day deadline) and to avoid duplicative reporting burdens where possible. This is an open item.]

## ARTICLE 21. MISCELLANEOUS

### Section 21.1 Notices.

All notices shall be in writing and deemed delivered upon personal delivery, upon delivery by nationally recognized overnight courier, or three (3) business days following deposit in the U.S. mail, registered or certified, return receipt requested, postage prepaid, addressed as follows:

If to Developer: Granite City Development LLC, 900 West Monroe Street, Suite 2200, Chicago, IL 60607, Attn: Marcus J. Pellegrini, Manager/CEO; with a copy to Thornfield & Pratt LLP, 311 South Wacker Drive, Suite 5400, Chicago, IL 60606, Attn: Catherine M. Albrecht.

If to City: City of Lakemont, Office of the City Manager, 200 Civic Center Drive, Lakemont, IL 60048, Attn: Gerald T. Fong, City Manager; with a copy to Office of Corporation Counsel, City of Lakemont, 200 Civic Center Drive, Lakemont, IL 60048, Attn: Rebecca A. Sinclair, Esq.; and with a copy to Ashford, Keene & Mulvaney LLP, 150 North Michigan Avenue, Suite 3200, Chicago, IL 60601, Attn: Jonathan Ashford.

Either party may change its notice address by written notice to the other party.

### Section 21.2 Confidentiality; FOIA.

The terms and contents of this Agreement are confidential and shall not be disclosed by either party to any third party, except: (a) to each party’s legal counsel, financial advisors, accountants, lenders, and equity investors, as reasonably necessary; (b) as required by applicable law or governmental regulation, including the Illinois Freedom of Information Act, 5 ILCS 140/, as applicable to the City; and (c) to the extent necessary for City Council proceedings, committee meetings, and other governmental approvals. The parties acknowledge that, as a public contract, this Agreement may be subject to disclosure under the Illinois Freedom of Information Act.

### Section 21.3 Amendments.

This Agreement may be amended, modified, or supplemented only by a written instrument executed by both parties, subject to the Construction Lender’s consent rights under Section 16.2 and Lakeshore Capital Partners Fund III LP’s consent rights under the Lakeshore Side Letter.

### Section 21.4 Severability.

If any provision of this Agreement is held invalid or unenforceable, such invalidity shall not affect other provisions that can be given effect without the invalid provision, and the provisions are severable.

### Section 21.5 Entire Agreement; Supersession.

This Agreement, together with its exhibits and the documents referenced herein, constitutes the entire agreement between the parties with respect to the subject matter hereof and supersedes the Term Sheet in its entirety upon execution. In the event of any conflict between this Agreement and the Term Sheet, this Agreement controls.

### Section 21.6 Counterparts; Electronic Signatures.

This Agreement may be executed in counterparts, each deemed an original, and signatures transmitted by electronic means shall be deemed original signatures.

### Section 21.7 No Third-Party Beneficiaries.

Except for the Construction Lender’s rights under Article 16, this Agreement is for the sole benefit of the parties and does not confer rights on any other person.

### Section 21.8 Expenses.

Each party shall bear its own costs and expenses incurred in connection with the negotiation and preparation of this Agreement, including legal fees, consultant fees, and other professional expenses.

### Section 21.9 Compliance with Laws.

Each party shall comply with all applicable laws, codes, and ordinances in the performance of its obligations under this Agreement, including the TIF Act, the Prevailing Wage Act, and the Illinois Environmental Protection Act.

### Section 21.10 TIF Compliance.

Any use of TIF revenues in connection with the Project shall comply in all respects with the TIF Act and the Lakemont Central TIF District Redevelopment Plan and Project as adopted by Ordinance No. 2019-42, as amended. All TIF-eligible redevelopment project costs shall be determined and reimbursed in accordance with applicable Illinois law and this Agreement.

## ARTICLE 22. EXHIBITS AND SCHEDULES

The following exhibits are attached to and incorporated into this Agreement:

- Exhibit A — Legal Description of the Property and ALTA/NSPS Survey [to be attached]

- Exhibit B — Project Description and Phasing Plan [to be attached]

- Exhibit C — Project Budget (Sources and Uses) [to be attached]

- Exhibit D — Permitted Exceptions to Title [to be agreed; see Loan Term Sheet Section 4.2]

- Exhibit E — Form of Phase I Performance Bond / Letter of Credit [to be attached]

- Exhibit F — Form of Affordability Restrictive Covenant [to be attached]

- Exhibit G — Community Center Design Specifications [to be developed; open item O5]

- Exhibit H — Public Parking Access/Operating Agreement [to be developed; open item O6]

- Exhibit I — City Off-Site Infrastructure Schedule [to be attached]

- Exhibit J — Form of Subordination and Intercreditor Agreement [to be developed; open item]

- Exhibit K — Form of ELUC / Institutional Controls [to be developed; open item O10]

- Exhibit L — Prevailing Wage Scope and Compliance Exhibit [to be developed; open item C13]

- Exhibit M — Living Wage Indexing Schedule [to be developed; open item C18]

- Exhibit N — Environmental Covenants and Access Agreements [to be developed; open item O17]

- Exhibit O — Form of Collateral Assignment and Consent/Acknowledgment Agreement [to be developed; open item C41]

[Drafting Note — Open items O9, O10, O11, O12. Several exhibits remain to be developed and are flagged as open items: the Permitted Exceptions (Exhibit D, to be agreed with the Construction Lender and title company per Loan Term Sheet Section 4.2); the ELUC forms (Exhibit K, to be approved by the Construction Lender’s counsel and title company); the GMP/stipulated-sum construction contract terms (referenced in Loan Term Sheet Section 7.1(12), not yet executed); and the final Sources and Uses / Project Budget (Exhibit C, with soft-cost allocation per Loan Term Sheet Section 2.1). These should be developed in parallel with negotiation of this Agreement.]

## SIGNATURE PAGE

IN WITNESS WHEREOF, the parties have executed this Development Agreement as of the Effective Date.

GRANITE CITY DEVELOPMENT LLC

By: _______________________________ Name: Marcus J. Pellegrini Title: Manager and Chief Executive Officer Date: _____________________________

CITY OF LAKEMONT, ILLINOIS

By: _______________________________ Name: Gerald T. Fong Title: City Manager Date: _____________________________

APPROVED AS TO FORM:

Rebecca A. Sinclair, Esq. Corporation Counsel, City of Lakemont, Illinois Date: _____________________________

Jonathan Ashford Ashford, Keene & Mulvaney LLP Outside Municipal Counsel Date: _____________________________

[Drafting Note — Consolidated summary of cross-document conflicts and open items. The following is a consolidated index of the bracketed drafting notes throughout this Agreement, for ease of reference and conversion to a separate issues list prior to execution.

Cross-document conflicts: - C1 (Section 14, central): Reversionary interest required by Resolution Condition #8(h) vs. prohibited by Loan Term Sheet §§4.2, 12; requires City agreement to alternative mechanism + Lakeshore consent. - C2 (Sections 14.2(a), 4.4): 36-month-from-conveyance reversion clock vs. Phase I 30-month construction / Sept. 30, 2028 deadline. - C3 (Section 15): Assignment/change-of-control thresholds — 50% (Term Sheet) vs. [50]% (Loan Term Sheet) vs. 51% (Lakeshore Side Letter). - C4 (Section 1.1.1): Parcel acquisition history — Resolution/TIF Memo/RFP (015+016 forfeiture 2016; 017 purchase 2018) vs. Phase II ESA (015 forfeiture 2016; 016+017 purchase 2018). - C5 (Section 1.1.1): Parcel acreages — RFP (3.8/4.1/4.8) vs. Phase II ESA (4.2/4.1/4.4). - C6 (Section 1.1.3): RFP number — 2024-CD-07 (RFP) vs. 2024-CD-018 (Term Sheet). - C7 (Section 1.1.1): County — Cook County (Phase II ESA) vs. Lake County (RFP, TIF Memo). - C8 (Sections 3.6, 11.1): Affordable unit count — 106 (Resolution, Term Sheet detail) vs. “at least 100” (Term Sheet summary). - C9 (Section 9.4): CGL aggregate — $20M (Term Sheet) vs. $25M (Loan Term Sheet). - C10 (Section 5.2): TIF shortfall risk — Term Sheet (no guarantee) vs. TIF Memo ($38–42M adjusted, $6–10M short). - C11 (Section 5.1): Land write-down vs. TIF cap — TIF Memo recommends specifying funding source. - C12 (Section 5.3): City infrastructure funding source vs. TIF cap — TIF Memo. - C13 (Section 9.3): Prevailing wage scope — Term Sheet (“all construction”) vs. TIF Memo (broad; Developer may resist private components). - C14 (Section 6.3): Environmental cost allocation/overruns — Term Sheet silent; Phase II ESA recommends overrun provision; Lakeshore consent if >$3.14M. - C15 (Sections 2.2, 4.2): NFR vs. RAP as condition precedent; phased conveyance — Resolution (RAP) vs. Loan Term Sheet (NFR or RAP+escrow) vs. Phase II ESA (phased conveyance). - C16 (Section 2.2): Equity demonstration deadline — Resolution (60 days from adoption, by 4/19/2025) vs. Term Sheet (60 days from DA approval). - C17 (Section 8.2): Performance security for later phases — not yet established. - C18 (Sections 10.2, 10.3): Living wage + first-source hiring — Resolution Condition #8(c) introduces living wage not in Term Sheet/RFP. - C19 (Section 10.1): Local hiring — goal/good-faith (Term Sheet) vs. “requiring not less than 35%” (Resolution). - C20 (Section 9.2): LEED “or equivalent” acceptability — Director discretion (Resolution) vs. City in writing (Term Sheet) vs. objective standard (Developer). - C21 (Section 12.3): Force majeure cap — 18 months (Term Sheet) vs. 180 days (Loan Term Sheet). - C22 (Section 18): Dispute resolution — arbitration (Term Sheet, Lakeshore) vs. litigation (Loan Term Sheet). - C23 (Section 13.4): Condemnation 15% — Developer termination (Term Sheet, non-City) vs. loan default (Loan Term Sheet); City-condemnation gap. - C24 (Section 12.2): Substantial Completion definition — to be defined. - C25 (Article 16): Lender protections — Loan Term Sheet §12 requirements vs. City control interests. - C26 (Sections 16.2, 21.3): Lakeshore consent rights over DA — Lakeshore Side Letter §4. - C27 (Sections 5.2, 6.3, 9.3): Minimum IRR 14% — Lakeshore Side Letter §3 constrains Developer negotiation. - C28 (Section 5.4): Abatement–TIF interaction; later-phase abatement — TIF Memo; Term Sheet §18.4. - C29 (Section 3.7): Community center scope — “at no additional cost” / “fully furnished and equipped.” - C30 (Section 6.3(d)): Vapor intrusion/mitigation — Phase II ESA §§7.1, 8.1; not in Term Sheet/Resolution. - C31 (Section 6.4): ELUCs as encumbrances — Phase II ESA; Loan Term Sheet permitted exceptions. - C32 (Section 6.3(e)): Off-site groundwater monitoring on Metra property — Phase II ESA §8.3. - C33 (Section 2.2): Rezoning before DA execution — consistent across documents. - C34 (Section 2.2): Parcel consolidation — Phase II ESA title review recommendation. - C35 (Sections 6.2, 17.3): City environmental indemnity scope/survival. - C36 (Section 4.2): Phased conveyance feasibility. - C37 (Section 5.2(e)): TIF extension good-faith covenant — TIF Memo recommendation. - C38 (Section 20): Reporting overlap — Term Sheet / Lakeshore / Loan Term Sheet. - C39 (Section 16): Cross-default DA↔Loan — Loan Term Sheet §9(5). - C40 (Section 13): Loss of entitlements — Loan Term Sheet §9(10); City-caused loss. - C41 (Section 16.7): Collateral assignment of DA and TIF reimbursement rights to Lender — Loan Term Sheet §4.1; City acknowledgment; Lakeshore no-lien interaction (SL §7(b)). - C42 (Section 9.3(d)): TIF withholding as prevailing wage non-compliance remedy — TIF Memo §V.C; scope-limited to TIF-reimbursed components. - C43 (Section 7.4): Lakeshore indebtedness cap $268,400,000 and no-lien restriction — Lakeshore Side Letter §§7(a), 7(b). - C44 (Section 12.1): Lakeshore 2035 overall-completion consent trigger — Lakeshore Side Letter §§4.3(c), 7(c); contractual maximums sit at edge of 2035. - C45 (Section 14.2(c)): Resolution “net of damages” refund vs. alternative “lesser of purchase price or FMV” repurchase price — Resolution Condition #8(h). - C46 (Section 14): Loan default on imposition/recording of lien or reversionary interest — Loan Term Sheet §9(11); reinforces no-recording. - C47 (Section 15.2): Lakeshore Change-of-Control consequences (repurchase right / management right, 90-day election) — Lakeshore Side Letter §5.4; interaction with City/Lender CoC consent.

Open items (unresolved terms): - O1 (Section 3.4): Hotel brand/flag — to be determined. - O2 (Section 9.5): Architect & GC selection — Lender-approved; not yet selected. - O3 (Section 7.4): Later-phase financing $58.4M — not secured; Lender + Lakeshore consent. - O4 (Section 8.2): Performance security amounts Phases II–IV. - O5 (Section 3.7, Exhibit G): Community center design specs/furnishings. - O6 (Section 3.8, Exhibit H): Public parking operating/access arrangements. - O7 (Section 6.3(e)): Metra access for off-site monitoring. - O8 (Section 12.2): Substantial Completion precise definition. - O9 (Section 2.2, Exhibit D): Permitted Exceptions to title. - O10 (Section 6.4, Exhibit K): Form of ELUCs. - O11 (Article 22): GMP/stipulated-sum construction contract terms. - O12 (Exhibit C): Final Sources & Uses / soft-cost allocation. - O13 (Section 7.2): Take-out/permanent financing commitment (Loan Term Sheet §2.4). - O14 (Section 7.2): Guaranty terms — completion + partial repayment burn-down (Loan Term Sheet §1). - O15 (Section 7.2): Interest reserve funding (Loan Term Sheet §2.2). - O16 (Section 6.3(f)): Pre-remediation plume delineation (6–8 additional borings) cost allocation — Phase II ESA §8.3. - O17 (Section 6.4(d), Exhibit N): Environmental covenants and access agreements — Resolution §6.]

[END OF DRAFT]